## Sheet1
CAP Nr | SMB/ NVSA | Recording Date | Issuer | Dpt | Customer | Supplier | CAP TYPE | Recuring | Compt Nr | Project Nr | Techno* | Description | Scope | Process | Step of Process | 7M | OE Tool | Enlarged Treatment | Leader | Action plan definition date | Est. closure date | Closure Date | Closed under 3 months | Claim Date | Cust. Information Date | Estimated date of action plan closure | Date of action plan closure | closed in delay? | Hours (€) | Eqmt (€) | TOTAL (€) | Efficient Action ? | Date of effic. measure | Comments | CAP_label | Label_CODIR
23006 | NVSA | 2023-02-10 | ESH | IER | Natureworks | Wuxi fandesi/FDS | Pdt unconformity |  |  | 16753 |  |  | SYSTEMS | I&R process | QC | Method / Méthode |  | YES | ESH | 2023-02-10 | 2023-05-10 | 2023-02-24 | YES |  |  | 2023-02-21 | 2023-02-20 | N/A | 1500 | 0 | 1500 |  |  |  | 23006 Natureworks | 23006 Natureworks :
23010 | NVSA | 2023-03-03 | ESH | IER | LEKAI | FDS | Supplier Dysfonctionning |  | 2137 | 18080 | SSMB | Piping fabrication quality | SYSTEMS | I&R process | Commissioning | Material / Matière |  | YES | ESH | 2023-03-03 | 2023-06-03 | 2023-05-05 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 23010 LEKAI | 23010 LEKAI : Piping fabrication quality
23013 | NVSA | 2023-04-11 | ESH | QC | Cofco Tangshan |  | Internal Anomaly |  |  | 23013_16608 |  | Cofco_issue control valve on drawing | SYSTEMS | I&R process | Design | Method / Méthode |  | YES | ESH | 2023-04-10 | 2023-07-11 | 2023-05-04 | YES |  |  |  |  | N/A |  | 278 | 278 |  |  |  | 23013 Cofco Tangshan | 23013 Cofco Tangshan : Cofco_issue control valve on drawing
23014 | NVSA | 2023-04-11 | ESH | QC | Huitong SSMB | FDS | Claim |  |  | 10.1779 |  | SSMB internals material (SS304 instead of SS316) | SYSTEMS | I&R process | Pre-Mouting | Material / Matière |  | YES | ESH | 2023-04-10 | 2023-07-11 | 2023-05-04 | YES | 2023-03-29 | 2023-03-29 | 2023-07-31 | 2023-05-04 | YES | 1000 |  | 1000 |  |  |  | 23014 Huitong SSMB | 23014 Huitong SSMB : SSMB internals material (SS304 instead of SS316)
23015 | NVSA | 2023-04-11 | ESH | QC | Ensign 2 | SPA | Claim |  |  | 18251 Ensign IEX |  | Ensign site issues rubber lining leakage | SYSTEMS | I&R process | Commissioning | Material / Matière |  | YES | ESH | 2023-04-10 | 2023-07-11 | 2023-06-12 | YES | 2023-03-08 | 2023-03-08 | 2023-07-31 | 2023-06-12 | YES | 2500 | 2583 | 5083 |  |  |  | 23015 Ensign 2 | 23015 Ensign 2 : Ensign site issues rubber lining leakage
23018 | NVSA | 2023-05-15 | MYU | CS | HUAKANG | Finex | Claim |  |  | 15333 | SSMB | Poor performance of Xylose ML SSMB/Resin issue | Cust. Sce | After sales process | project closed | Material / Matière |  | YES | MYU | 2023-05-15 | 2023-08-15 | 2023-07-19 | YES | 2023-04-14 | 2023-04-17 | 2023-08-31 | 2023-07-19 | YES | 0 | 3000 | 3000 |  |  |  | 23018 HUAKANG | 23018 HUAKANG : Poor performance of Xylose ML SSMB/Resin issue
23019 | NVSA | 2023-06-02 | MYU | CS | DYG | Inopor | Claim | X |  | 75.2269 | MF | Alpha KBW 0.1U membranes abrasion issue | Cust. Sce | After sales process | project closed | Material / Matière |  | YES | MYU | 2023-06-02 | 2023-09-02 | 2023-07-19 | YES | 2023-02-05 | 2023-02-05 | 2023-10-31 | 2023-07-19 | YES | 0 | 130000 | 130000 |  |  |  | 23019 DYG | 23019 DYG : Alpha KBW 0.1U membranes abrasion issue
23030 | NVSA | 2023-10-28 | MPE | IER | SQ Nansha | Runlu | Supplier Dysfonctionning |  | 2128 | 17951 | IEX | Loose nozzles found inside columns of SQ20 on Site | SYSTEMS | I&R process | Commissioning | Method / Méthode |  | YES | ESH | 2023-11-17 | 2024-01-28 | 2024-01-12 | YES |  |  |  |  | N/A | 3000 | 1892 | 4892 |  |  |  | 23030 SQ Nansha | 23030 SQ Nansha : Loose nozzles found inside columns of SQ20 on Site
23031 | NVSA | 2023-11-06 | MHA | IER | Lier | Xiangming | Internal Anomaly |  | 2151 | 18281 | MF/UF | Unproper MF housings site installation | SYSTEMS | I&R process | Installation | Method / Méthode |  | YES | ESH | 2023-12-06 | 2024-02-06 | 2024-02-01 | YES |  |  |  |  | N/A | 250 | 139 | 389 |  |  |  | 23031 Lier | 23031 Lier : Unproper MF housings site installation
23032 | NVSA | 2023-11-06 | MHA | IER | Rousselot | kaiyuan/Biteng | Claim |  | 2150 | 18178 | IEX | Painting damage during transportation | SYSTEMS | I&R process | Delivery | Method / Méthode |  | YES | ESH | 2023-11-27 | 2024-02-06 | 2024-04-26 | NO | 2023-08-04 | 2023-08-04 | 2024-04-30 | 2024-04-26 | YES | 938 | 0 | 938 |  |  |  | 23032 Rousselot | 23032 Rousselot : Painting damage during transportation
24002 | NVSA | 2024-01-16 | ESH | IER | Xinlv | FDS | Supplier Dysfonctionning |  |  | 18418 | SSMB | Xinlv SSMB cell height | SYSTEMS | I&R process | QC at client site | Method / Méthode |  | YES | ESH | 2024-03-01 | 2024-04-16 | 2024-04-15 | YES |  |  |  |  | N/A | 750 | 0 | 750 |  |  |  | 24002 Xinlv | 24002 Xinlv : Xinlv SSMB cell height
24003 | NVSA | 2024-01-22 | TWI | IER | SQ13 | GREE | Claim |  | 2097 | 16108 | IEX | SQ13 LS MB140 column internals deformation | SYSTEMS | I&R process | commissioning | Method / Méthode |  | YES | TWI | 2024-01-30 | 2024-04-22 | 2024-05-06 | NO | 2024-01-13 | 2024-01-13 | 2024-05-31 | 2024-05-06 | YES | 7000 | 3832 | 10832 |  |  |  | 24003 SQ13 | 24003 SQ13 : SQ13 LS MB140 column internals deformation
24005 | NVSA | 2024-02-20 | ESH | IER | Huitong |  | Internal Anomaly |  | 2136 | 17789 | SSMB | Backwashing tank volume issue | SYSTEMS | I&R process | Meca Design | Method / Méthode |  | YES | ESH | 2024-03-28 | 2024-05-20 | 2024-05-20 | YES |  |  |  |  | N/A | 1278 |  | 1278 |  |  |  | 24005 Huitong | 24005 Huitong : Backwashing tank volume issue
24014 | NVSA | 2024-04-02 | MHA | IER | SQ CQ | FDS/Runjia | Internal Anomaly |  | 3022 | 18448 | SSMB | Unproper internals manufacturing and installation for SSMB | SYSTEMS | I&R process | QC | Equipment / Matériel |  | YES | ESH | 2024-04-10 | 2024-07-02 | 2024-07-01 | YES |  |  |  |  | N/A | 5139 |  | 5139 |  |  |  | 24014 SQ CQ | 24014 SQ CQ : Unproper internals manufacturing and installation for SSMB
24016 | NVSA | 2024-04-18 | MYU | CS | Fufeng Qiqihaer | Mitsubishi | Claim |  | 3087 | 75.2406 | IEX | Fufeng Qiqihaer- Frozen lysine resin | Cust. Sce | After sales process | Logistic | Environment / Milieu |  | YES | MYU | 2024-04-22 | 2024-07-18 | 2024-06-20 | YES | 2024-04-06 | 2024-04-06 | 2024-07-31 | 2024-06-20 | YES | 1333 | 0 | 1333 |  |  |  | 24016 Fufeng Qiqihaer | 24016 Fufeng Qiqihaer : Fufeng Qiqihaer- Frozen lysine resin
24019 | NVSA | 2024-06-11 | YLI | IER | SQ Nansha | SPA | Claim |  | 2128 | 17951 | IEX | SQ20 F55MB CL6510 Rubber Lining Issue of Insert Tube | SYSTEMS | I&R process | QC | Equipment / Matériel |  | YES | YLI | 2024-06-24 | 2024-09-11 | 2024-09-05 | YES | 2024-04-27 | 2024-04-28 | 2024-09-30 | 2024-09-05 | YES | 500 |  | 500 |  | A faire 12/25 |  | 24019 SQ Nansha | 24019 SQ Nansha : SQ20 F55MB CL6510 Rubber Lining Issue of Insert Tube
24022 | NVSA | 2024-06-20 | TWI | IER | Huaantang |  | Internal Anomaly |  | 3123 | 18323 | SSMB | Functional Analysis assignement and workload France-Asia | SYSTEMS | I&R process | Process Design | Management / Management |  | YES | TWI | 2024-06-27 | 2024-09-20 | 2024-09-19 | YES |  |  |  |  | N/A | 250 | 0 | 250 |  | A faire 12/25 |  | 24022 Huaantang | 24022 Huaantang : Functional Analysis assignement and workload France-Asia
24030 | NVSA | 2024-08-02 | RRU | CS | Lesaffre | INOPOR | Claim |  | 2142 | 18146 | MF/UF | KBE alpha Membrane Abrasion | Cust. Sce | After sales process | After sales | Material / Matière |  | YES | TWI | 2024-08-27 | 2024-11-02 | 2025-01-22 | NO | 2024-07-25 | 2024-07-25 | 2024-12-31 | 2025-01-22 | NO | 3920 |  | 3920 |  |  |  | 24030 Lesaffre | 24030 Lesaffre : KBE alpha Membrane Abrasion
24036 | NVSA | 2024-10-18 | RRU | CS | GXSF 2 | Mitsubishi | Claim |  |  | 10.702 | IEX | High Pressure Drop in C120A upper cell | Cust. Sce | After sales process | commissioning | Material / Matière |  | YES | MYU | 2024-10-29 | 2025-01-18 | 2025-04-03 | NO | 2024-09-16 | 2024-09-18 | 2025-06-30 | 2025-04-03 | YES | 6389 | 156111 | 162500 |  |  |  | 24036 GXSF 2 | 24036 GXSF 2 : High Pressure Drop in C120A upper cell
24038 | NVSA | 2024-11-18 | RRU | CS | Yinmore | Mitsubishi | Claim |  |  | 9801 | IEX | Large deviation in resin particle size distribution | Cust. Sce | After sales process | Purchase | Management / Management |  | YES | MYU | 2024-11-29 | 2025-02-18 | 2025-02-20 | NO | 2024-09-10 | 2024-11-07 | 2025-06-30 | 2025-02-20 | YES |  | 83333.33 | 83333.33 |  |  |  | 24038 Yinmore | 24038 Yinmore : Large deviation in resin particle size distribution
24039 | NVSA | 2024-11-19 | YLI | IER | Huaantang | SPA | Supplier Dysfonctionning | X | 3123 | 18323 | SSMB | Columns Name plate & Tag No. Installation Mistake | SYSTEMS | I&R process | QC | Method / Méthode |  | YES | YLI | 2024-11-28 | 2025-02-19 | 2025-01-16 | YES |  |  |  |  | N/A | 625 | 486 | 1111 |  |  |  | 24039 Huaantang | 24039 Huaantang : Columns Name plate & Tag No. Installation Mistake
24040 | NVSA | 2024-11-19 | YLI | IER | Huaantang | FDS | Supplier Dysfonctionning |  | 3123 | 18323 | SSMB | Column-B Resin Nozzle Orientation Mistake | SYSTEMS | I&R process | QC | Method / Méthode |  | YES | YLI | 2024-11-28 | 2025-02-19 | 2025-01-16 | YES |  |  |  |  | N/A | 625 |  | 625 |  |  |  | 24040 Huaantang | 24040 Huaantang : Column-B Resin Nozzle Orientation Mistake
24041 | NVSA | 2024-11-20 | MHA | IER | LIER | Runyuan | Claim |  | 3165 | 18466 | CA | The carbon backwashing is not efficient | SYSTEMS | I&R process | Meca Design | Method / Méthode |  | YES | ACH | 2024-11-27 | 2025-02-20 | 2025-01-24 | YES | 2024-09-19 | 2024-09-19 | 2025-03-31 | 2025-01-24 | YES | 2188 | 1388 | 3576 |  |  |  | 24041 LIER | 24041 LIER : The carbon backwashing is not efficient
24042 | NVSA | 2024-11-20 | MHA | IER | LIER | LongYU, Ziyou | Internal Anomaly |  | 3165 | 18466 | CA | Mismatching of Nozzle A1 and A2 between column and front piping | SYSTEMS | I&R process | Meca Design | Method / Méthode |  | YES | ACH | 2024-11-27 | 2025-02-20 | 2025-02-18 | YES |  |  |  |  | N/A | 1876 | 1416 | 3292 |  |  |  | 24042 LIER | 24042 LIER : Mismatching of Nozzle A1 and A2 between column and front piping
24043 | NVSA | 2024-11-25 | MYU | CS | SQ18 | Dupont | Internal Anomaly |  |  | 17093 | IEX | SQ18 IRA458 Resin missing in SHA warehouse | Cust. Sce | After sales process | stock | Management / Management |  | YES | MYU | 2024-11-29 | 2025-02-25 | 2025-02-18 | YES |  |  |  |  | N/A |  | 105944.44 | 105944.44 |  |  |  | 24043 SQ18 | 24043 SQ18 : SQ18 IRA458 Resin missing in SHA warehouse
24044 | NVSA | 2024-12-02 | TWI | IER | PLIITH HUITONG | ZIMA | Claim |  | 2135 | 18103 | CA | GAC revamping program delay | SYSTEMS | I&R process | automation | Management / Management |  | YES | TWI | 2024-12-11 | 2025-03-02 | 2025-03-07 | NO | 2024-11-28 | 2024-11-29 | 2025-03-31 | 2025-03-07 | YES | 3068 | 0 | 3068 |  |  |  | 24044 PLIITH HUITONG | 24044 PLIITH HUITONG : GAC revamping program delay
24045 | NVSA | 2024-12-02 | MHA | IER | SQ1 Nansha |  | Internal Anomaly |  | 3075 | 45.0037 | SSMB | SQ1 revamping program didn't complete on time | SYSTEMS | I&R process | automation | Management / Management |  | YES | TWI | 2024-12-06 | 2025-03-02 | 2025-01-16 | YES |  |  |  |  | N/A | 1000 |  | 1000 |  |  |  | 24045 SQ1 Nansha | 24045 SQ1 Nansha : SQ1 revamping program didn't complete on time
25008 | NVSA | 2025-03-26 | YLI | IER | Eppen | kaiyuan | Claim |  |  | 18589 | SSMB | Non-conformity of QC during the client visiting | SYSTEMS | I&R process | QC | Management / Management |  | YES | YLI | 2025-04-03 | 2025-06-26 | 2025-05-13 | YES | 27/02/2025 | 2025-02-28 | 2025-06-30 | 2025-05-13 | YES | 437.5 | 0 | 437.5 |  |  |  | 25008 Eppen | 25008 Eppen : Non-conformity of QC during the client visiting
25009 | NVSA | 2025-03-26 | YLI | IER | SQ26 | kaiyuan | Claim |  | 3236 | 18637 | IEX | Rubber lining defect & Nozzle loose issue | SYSTEMS | I&R process | QC | Manpower / Main d'œuvre |  | YES | YLI | 2025-04-11 | 2025-06-26 | 2025-05-28 | YES | 2025-03-11 | 2025-03-12 | 2025-06-30 | 2025-05-28 | YES | 2381.94 |  | 2381.94 |  |  |  | 25009 SQ26 | 25009 SQ26 : Rubber lining defect & Nozzle loose issue
25011 | NVSA | 2025-04-07 | DWA | IER | HUAKANG | Jacobi | Claim |  | 3041 |  | SSMB | Internal communication issue led to resin late delivery to client-Huakang | S&C | I&R process | Delivery | Method / Méthode |  | YES | DWA | 2025-04-10 | 2025-07-07 | 2025-06-11 | YES | 24/03/2025 | 24/03/2025 | 2025-07-31 | 2025-06-11 | YES | 784 |  | 784 |  |  |  | 25011 HUAKANG | 25011 HUAKANG : Internal communication issue led to resin late delivery to client-Huakang
25014 | NVSA | 2025-04-25 | MPE | S&C | Taiyixin (DUOWEI) |  | Claim |  |  | 45.0038 | MF | TAIYIXIN lawsuit due to miscommunication of MYU( former S&C Director) | S&C | After sales process | breach of contract | Manpower / Main d'œuvre |  | YES | MPE | 2025-05-13 | 2025-07-25 | 2025-11-19 | NO | 2025-03-07 | 2025-03-10 | 2025-12-31 | 2025-11-19 | YES | 986 | 37791 | 38777 |  |  |  | 25014 Taiyixin (DUOWEI) | 25014 Taiyixin (DUOWEI) : TAIYIXIN lawsuit due to miscommunication of MYU( former S&C Director)
25018 | NVSA | 2025-05-28 | MPE | S&C | Lesaffre | CORUN | Claim |  | 75.2474 | 18873 | MF | Breakage of Beta membrane | S&C | After sales process | purchasing | Material / Matière |  | YES | MPE/RLU | 2025-05-28 | 2025-08-28 |  | NO | 2025-05-07 | 2025-05-07 | 2025-12-31 |  | NO |  |  | 0 |  |  |  | 25018 Lesaffre | 25018 Lesaffre : Breakage of Beta membrane
25019 | NVSA | 2025-06-27 | YLI | IER | Eppen | Kaiyuan | Supplier Dysfonctionning |  |  | 18589 | SSMB | CH5200A column deformation issue at Eppen | SYSTEMS | I&R process | QC | Method / Méthode |  | YES | YLI | 2025-06-27 | 2025-09-27 | 2025-12-15 | NO |  |  |  |  | N/A | 2589 |  | 2589 |  |  |  | 25019 Eppen | 25019 Eppen : CH5200A column deformation issue at Eppen
25020 | NVSA | 2025-06-27 | MPE | S&C | Yinmore | Mitsubishi | Claim |  |  | 75.2401/2450 | Decolo | Yinmore decolor resin issue | S&C | After sales process | delivery | Material / Matière |  | NO |  |  | 2025-09-27 | 2025-07-28 | YES | 2025-03-31 | 2025-03-31 | 2025-12-31 | 2025-07-28 | YES | 0 | 286529.67 | 286529.67 |  |  |  | 25020 Yinmore | 25020 Yinmore : Yinmore decolor resin issue
25027 | NVSA | 2025-08-15 | YLI | IER | Abbott | FDS | Claim |  |  | 18780 | IEX | Hastelloy box female thread issue | SYSTEMS | I&R process | QC | Method / Méthode |  | YES | YLI | 2025-08-26 | 2025-11-15 | 2025-09-10 | YES | 2025-07-23 | 2025-07-23 | 2025-10-01 | 2025-09-10 | YES | 493 |  | 493 |  |  |  | 25027 Abbott | 25027 Abbott : Hastelloy box female thread issue
25030 | NVSA | 2025-09-02 | MHA | IER | Eppen | Endress+Hauser | Internal Anomaly |  |  | 18589 | SSMB | Electromagnetic flowmeter does not meet client requirement | SYSTEMS | I&R process | Meca design | Method / Méthode |  | YES | MHA | 2025-09-02 | 2025-12-02 | 2025-11-18 | YES |  |  |  |  | N/A | 1233 |  | 1233 |  |  |  | 25030 Eppen | 25030 Eppen : Electromagnetic flowmeter does not meet client requirement
25031 | NVSA | 2025-09-05 | FMH | S&C | Dongya Sugar |  | Internal Anomaly |  |  | 19498 & 19511 |  | Issue in following the internal process for contract review and ordering process | S&C | After sales process | Contract validation | Method / Méthode |  | YES | SSH | 2025-09-10 | 2025-12-05 | 2025-12-05 | YES |  |  |  |  | N/A | 493 |  | 493 |  | A faire 06/26 |  | 25031 Dongya Sugar | 25031 Dongya Sugar : Issue in following the internal process for contract review and ordering process
Note on L2: Codes Techno : ED (Electrodialyse) SSMB (Chromato) IEX (Echange Ions) MF/UF (Micro/Ultrafiltation) NF (Nanofiltration) OI (Osmose Inverse) EVAPO (Evaporation) CA (Charbon Actif)
Note on AA12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Postpone from client : mail ALI "client haven’t asked us for delivery till now, probably will happen in one or two months"
Note on P15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mis à jour suite bilan CAP 2024 SHA
Note on P18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mis à jour suite bilan CAP 2024 SHA
Note on Q19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mis à jour suite bilan CAP 2024 SHA
Note on Q28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mis à jour suite bilan CAP 2024 SHA
Note on Q29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mis à jour suite bilan CAP 2024 SHA