## Chrono CAP
Fichier | CAP Nr | SMB/ NVSA | Recording Date | Issuer | Dpt | Customer | Supplier | CAP TYPE | Recuring | Compt Nr | Project Nr | Techno* | Description | Scope | Process | Step of Process | 7M | OE Tool | Supplier litigation | Enlarged Treatment | Leader | Action plan definition date | Est. closure date | Closure Date | Closed under 3 months | Claim Date | Cust. Information Date | Acting Plan est. Closure date | Date of acting plan closure | closed in delay? | Hours (€) | Eqmt (€) | TOTAL (€) | Efficient Action ? | Date of effic. measure | Comments | CAP_label | Label_CODIR
CAP Sheets Follow up | [34 empty] | 2025-10-29
[11 empty] | Project |  |  | Cause Study |  |  |  |  | Action Plan | [12 empty] | NQ Costs |  |  | 2026-01-29
[19 empty] | 1st step |  | ENLARGED TREATMENT |  |  | CLOSURE |  |  | CLAIM |  |  |  |  | NQ Costs |  |  | EFFICIENCY
Fichier | CAP Nr | SMB/ NVSA | Recording Date | Issuer | Dpt | Customer | Supplier | CAP TYPE | Recuring | Compt Nr | Project Nr | Techno* | Description | Scope | Process | Step of Process | 7M | OE Tool | Supplier litigation | 1st action planned date | Enlarged Treatment | Leader | Action plan definition date | Est. closure date | Closure Date | Closed under 3 months | Claim Date | Cust. Information Date | Estimated date of action plan closure | Date of action plan closure | closed in delay? | Hours (€) | Eqmt (€) | TOTAL (€) | Efficient Action ? | Date of effic. measure | Comments | CAP_label | Label_CODIR
| xxxxx | [22 empty] | 1900-03-31 | 2011-01-01 | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | xxxxx | xxxxx :
| 11011 | SMB | 2011-04-01 | JPV |  | INDENA |  | Internal Anomaly |  |  | Pilote K07.04 |  | Commande | SYSTEMS | PPD Process | Pilot | Method / Méthode |  |  | 2011-03-31 | NO |  |  | 2011-07-01 | 2011-04-29 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11011 INDENA | 11011 INDENA : Commande
| 11012 | SMB | 2011-04-05 | EWI |  | Beldem |  | Claim |  |  | 10.7248 |  | Casses mécaniques / Performances | SYSTEMS | I&R process |  | Equipment / Matériel |  |  | 2010-11-30 | NO |  |  | 2011-07-05 | 2014-02-27 | NO | [7 empty] | 0 |  |  |  | 11012 Beldem | 11012 Beldem : Casses mécaniques / Performances
| 11013 | SMB | 2011-04-07 | EWI |  | CJ Liaocheng GMP |  | Claim |  |  | 10.7382 |  | Performances | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2011-01-06 | NO |  |  | 2011-07-07 | 2011-10-12 | NO | [7 empty] | 0 |  |  |  | 11013 CJ Liaocheng GMP | 11013 CJ Liaocheng GMP : Performances
| 11014 | SMB | 2011-04-07 | LPR |  | OTIME |  | Supplier Dysfonctionning |  |  | 10.6903 |  | Mauvais positionnement des clarinettes skid UF/MF | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2011-04-22 | NO |  |  | 2011-07-07 | 2011-05-27 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11014 OTIME | 11014 OTIME : Mauvais positionnement des clarinettes skid UF/MF
| 11015 | SMB | 2011-04-14 | FCA |  | Parry India |  | Claim |  |  | 10.6682 |  | Débit mètre diafiltration sous air, en défaut | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2011-04-15 | NO |  |  | 2011-07-14 | 2011-05-31 | YES | [7 empty] | 0 |  |  |  | 11015 Parry India | 11015 Parry India : Débit mètre diafiltration sous air, en défaut
| 11016 | SMB | 2011-04-18 | PBO |  | Roquette Lestrem/CTI |  | Claim |  |  | CV-1103-0008 |  | Diamètre membrane hors spec | Cust. Sce | After sales process |  | Equipment / Matériel |  |  | 2011-04-18 | NO |  |  | 2011-07-18 | 2011-06-15 | YES | [7 empty] | 0 |  |  |  | 11016 Roquette Lestrem/CTI | 11016 Roquette Lestrem/CTI : Diamètre membrane hors spec
| 11017 | SMB | 2011-05-16 | JPV |  | ARD |  | Internal Anomaly |  |  | Pilote O-01 |  | Oubli envoi pièces / Pilotage | SYSTEMS | PPD Process | Pilot | Method / Méthode |  |  | 2011-05-09 | NO |  |  | 2011-08-16 | 2011-08-02 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11017 ARD | 11017 ARD : Oubli envoi pièces / Pilotage
| 11018 | SMB | 2011-05-18 | EWI |  | De Smet |  | Internal Anomaly |  |  | 10.7410 |  | Oubli commande rotamètre | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2011-05-13 | NO |  |  | 2011-08-18 | 2011-08-02 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11018 De Smet | 11018 De Smet : Oubli commande rotamètre
| 11019 | SMB | 2011-06-21 | GTH |  | FACEO |  | Internal Anomaly |  |  | EN2683 |  | Coupure électricité/Arrêt gpe froid/Chambre froide | SYSTEMS | PPD Process | Pilot | Method / Méthode |  |  | 2011-06-15 | NO |  |  | 2011-09-21 | 2011-08-02 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11019 FACEO | 11019 FACEO : Coupure électricité/Arrêt gpe froid/Chambre froide
| 11020 | SMB | 2011-06-21 | GTH |  | FACEO / E2MI |  | Internal Anomaly |  |  | EN2683 |  | Perçage cuve par chariot élévateur | SYSTEMS | PPD Process | Pilot | Method / Méthode |  |  | 2011-06-15 | NO |  |  | 2011-09-21 | 2011-08-02 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11020 FACEO / E2MI | 11020 FACEO / E2MI : Perçage cuve par chariot élévateur
| 11021 | SMB | 2011-06-23 | SMR |  | CJ Indonesia-PROSEL 2 |  | Internal Anomaly |  |  | 10.8042 |  | Griffes for modules have not been ordered | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2011-06-16 | YES | SMR |  | 2011-09-23 | 2012-01-26 | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 11021 CJ Indonesia-PROSEL 2 | 11021 CJ Indonesia-PROSEL 2 : Griffes for modules have not been ordered
| 11022 | SMB | 2011-06-28 | SOV |  | JOHNSON |  | Supplier Dysfonctionning |  |  | 10.7748 |  | Diamètre crépines pas respecté / plans | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2011-07-20 | NO |  |  | 2011-09-28 | 2011-09-22 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11022 JOHNSON | 11022 JOHNSON : Diamètre crépines pas respecté / plans
| 11023 | SMB | 2011-06-28 | SOV |  | IANSA |  | Internal Anomaly |  |  | 10.7748 |  | Vérif plans / Diamètre externe de tige | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2011-08-11 | NO |  |  | 2011-09-28 | 2011-09-20 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11023 IANSA | 11023 IANSA : Vérif plans / Diamètre externe de tige
| 11024 | SMB | 2011-06-28 | SOV |  | IANSA |  | Internal Anomaly |  |  | 10.7748 |  | Vérification plans / connexion des soupapes | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2011-08-11 | NO |  |  | 2011-09-28 | 2011-09-20 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11024 IANSA | 11024 IANSA : Vérification plans / connexion des soupapes
| 11025 | SMB | 2011-07-01 | SOV |  | IANSA / VAPOR INDUSTRIAL |  | Supplier Dysfonctionning |  |  | 10.7748 | IEX | Pb orientation axiale fond colonne / Tuyauterie | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2011-06-23 | NO |  |  | 2011-10-01 | 2011-09-20 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11025 IANSA / VAPOR INDUSTRIAL | 11025 IANSA / VAPOR INDUSTRIAL : Pb orientation axiale fond colonne / Tuyauterie
| 11026 | SMB | 2011-07-08 | DCI |  | Mantequerias Arias |  | Claim |  |  | CV-1107-0056 | MF/UF | Casse mbne nette longitudinale | Cust. Sce | After sales process |  | Equipment / Matériel |  |  | 2011-07-26 | NO |  |  | 2011-10-08 | 2011-08-10 | YES | [7 empty] | 0 |  |  |  | 11026 Mantequerias Arias | 11026 Mantequerias Arias : Casse mbne nette longitudinale
| 11027 | SMB | 2011-07-11 | DBA/DCI |  | GARDOVIAL |  | Claim |  |  | 10.6163 | IEX | Pb de coloration / moût de raisin | Cust. Sce | After sales process |  | Equipment / Matériel |  |  | 2011-03-15 | NO |  |  | 2011-10-11 | 2011-09-21 | YES | [7 empty] | 0 |  |  |  | 11027 GARDOVIAL | 11027 GARDOVIAL : Pb de coloration / moût de raisin
| 11028 | SMB | 2011-07-20 | SMR |  | FRIENDLINK |  | Supplier Dysfonctionning |  |  |  |  | CRANE valves sold to NVS by FRIENDLINK | SYSTEMS | I&R process |  | Equipment / Matériel |  |  | 2011-10-14 | NO |  |  | 2011-10-20 | 2011-10-19 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11028 FRIENDLINK | 11028 FRIENDLINK : CRANE valves sold to NVS by FRIENDLINK
| 11029 | SMB | 2011-07-20 | SMR |  | MERSEN XIANDA |  | Supplier Dysfonctionning |  |  | 10.8166 | SSMB | Wrong size of gaskets manhole | SYSTEMS | I&R process |  | Equipment / Matériel |  |  | 2011-07-08 | NO |  |  | 2011-10-20 | 2011-10-19 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11029 MERSEN XIANDA | 11029 MERSEN XIANDA : Wrong size of gaskets manhole
| 11030 | SMB | 2011-08-02 | EWI |  | CJ Liaocheng Lysine |  | Claim |  |  | 10.8121 | SSMB | Flange corrosion | SYSTEMS | I&R process |  | Material / Matière |  |  | 2011-08-01 | YES | HPI |  | 2011-11-02 | 2011-12-14 | NO | [7 empty] | 0 |  |  |  | 11030 CJ Liaocheng Lysine | 11030 CJ Liaocheng Lysine : Flange corrosion
| 11031 | SMB | 2011-08-11 | SMR |  | LIVIC |  | Supplier Dysfonctionning |  |  | 10.8042 | MF/UF | Scrapped filter does not work | SYSTEMS | I&R process |  | Equipment / Matériel |  |  | 2011-07-28 | YES | SMR |  | 2011-11-11 | 2012-01-26 | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 11031 LIVIC | 11031 LIVIC : Scrapped filter does not work
| 11032 | SMB | 2011-09-22 | ELO |  | TEREOS SYRAL / GE WATER |  | Supplier Dysfonctionning |  |  | CV-1107-0012 | NF | Retard livraison | Cust. Sce | After sales process |  | Method / Méthode |  |  | 2011-09-26 | NO |  |  | 2011-12-22 | 2012-01-20 | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 11032 TEREOS SYRAL / GE WATER | 11032 TEREOS SYRAL / GE WATER : Retard livraison
| 11033 | SMB | 2011-09-30 | CHP |  | Scecs internes SMB |  | Internal Anomaly |  |  | PTT |  | Mise en œuvre PTT | SYSTEMS | Order acquirement process |  | Method / Méthode |  |  | 2011-09-30 | YES | CHP |  | 2011-12-30 | 2012-01-26 | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 11033 Scecs internes SMB | 11033 Scecs internes SMB : Mise en œuvre PTT
| 11034 | SMB | 2011-10-11 | PBO |  | TEREOS SYRAL / GE WATER |  | Claim |  |  | CV-1103-0058 | NF | performance rétention / Tube perméat hors spec | Cust. Sce | After sales process |  | Method / Méthode |  |  | 2011-09-15 | YES | DCI |  | 2012-01-11 | 2012-07-26 | NO | [7 empty] | 0 |  | 2012-07-26 |  | 11034 TEREOS SYRAL / GE WATER | 11034 TEREOS SYRAL / GE WATER : performance rétention / Tube perméat hors spec
| 11035 | SMB | 2011-10-20 | DBA |  | Great Ocean Ingredients |  | Claim |  |  | 10.6760 | IEX | Etanchéité ramification réseau / Déformation réseau | Cust. Sce | After sales process | IER | Equipment / Matériel |  |  | 2011-06-17 | YES | SMR/DBA |  | 2012-01-20 | 2012-01-26 | NO | [7 empty] | 0 |  |  |  | 11035 Great Ocean Ingredients | 11035 Great Ocean Ingredients : Etanchéité ramification réseau / Déformation réseau
| 11036 | SMB | 2011-10-20 | DBA |  | BENEO ORAFTI |  | Claim |  |  | 10.6954 | IEX | Déformation réseau | Cust. Sce | After sales process | IER | Equipment / Matériel |  |  | 2011-08-03 | YES | SMR/DBA |  | 2012-01-20 | 2012-01-26 | NO | [7 empty] | 0 |  |  |  | 11036 BENEO ORAFTI | 11036 BENEO ORAFTI : Déformation réseau
| 11037 | SMB | 2011-10-21 | JPV |  | Finorga |  | Internal Anomaly |  |  | Pilote NOI-02 | NF | Pompe Pilote alimentation fuyarde | SYSTEMS | PPD Process |  | Equipment / Matériel |  |  | 2011-10-19 | NO |  |  | 2012-01-21 | 2012-01-06 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 11037 Finorga | 11037 Finorga : Pompe Pilote alimentation fuyarde
| 11038 | SMB | 2011-10-24 | FRU |  | ILLOVO |  | Internal Anomaly |  |  | 10.5815 | NF | Cales pour mbres NF non commandées ou non livrées | SYSTEMS | I&R process | Purchase | Method / Méthode |  |  | 2011-10-04 | YES | JNJ |  | 2012-01-24 | 2012-01-24 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-01-23 | Doc AQ 6.1 rev 9 | 11038 ILLOVO | 11038 ILLOVO : Cales pour mbres NF non commandées ou non livrées
| 11039 | SMB | 2011-11-08 | SOV |  | OTIME / DANISCO |  | Supplier Dysfonctionning |  |  | 10.6506 | MF/UF | Tenue en pression / note de calcul | SYSTEMS | I&R process | Purchase | Method / Méthode |  |  | 2011-07-30 | YES | LDU |  | 2012-02-08 | 2012-02-07 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-02-06 |  | 11039 OTIME / DANISCO | 11039 OTIME / DANISCO : Tenue en pression / note de calcul
| 11040 | SMB | 2011-11-08 | SOV |  | DANISCO |  | Internal Anomaly |  |  | 10.6506 | MF/UF | Mise à jour / plan guide PG06 | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2011-09-30 | NO |  |  | 2012-02-08 | 2012-01-24 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-01-24 |  | 11040 DANISCO | 11040 DANISCO : Mise à jour / plan guide PG06
| 11041 | SMB | 2011-11-08 | SMR |  | OTIME / ORAFTI CHILI |  | Supplier Dysfonctionning |  |  | 10.7965 | IEX | Oubli Fabrication pièces | SYSTEMS | I&R process | Purchase | Method / Méthode |  |  | 2011-09-30 | YES | LDU |  | 2012-02-08 | 2012-02-01 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-02-01 |  | 11041 OTIME / ORAFTI CHILI | 11041 OTIME / ORAFTI CHILI : Oubli Fabrication pièces
| 11042 | SMB | 2011-12-15 | EWI |  | DONGYAO / CTI |  | Internal Anomaly |  |  | 10.8041 | MF/UF | Extrémitées membranes ébréchées | Cust. Sce | I&R process |  | Equipment / Matériel |  |  | 2011-11-07 | YES | LTR |  | 2012-03-15 | 2012-03-13 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-03-13 |  | 11042 DONGYAO / CTI | 11042 DONGYAO / CTI : Extrémitées membranes ébréchées
| 12001 | SMB | 2012-01-06 | SMR |  | TTCA / SPA |  | Claim |  |  | 10.8166 | SSMB | Corrosion piping rubber-lining | SYSTEMS | I&R process |  | Material / Matière |  |  | 2011-11-24 | YES | SMR |  | 2012-04-06 | 2012-05-02 | NO | [7 empty] | 0 |  | 2012-05-02 | Material / Matière modifié en matériel le 20/03/12 selon nvelle déf JCR | 12001 TTCA / SPA | 12001 TTCA / SPA : Corrosion piping rubber-lining
| 12002 | SMB | 2012-01-23 | TEB |  | RENNOVIA |  | Safety |  |  | EN2712 | IEX | Projection acide |  | PPD Process |  | Manpower / Main d'œuvre |  |  | 2012-01-10 | YES | TEB |  | 2012-04-23 | 2013-01-15 | NO |  |  |  |  | N/A |  |  | 0 | YES | 2013-01-15 |  | 12002 RENNOVIA | 12002 RENNOVIA : Projection acide
| 12003 | SMB | 2012-02-03 | SMR |  | CJ L5 LIAOCHENG / KSB |  | Supplier Dysfonctionning |  |  | 10.8168 | MF/UF | Leakage mechanical sealings pumps | SYSTEMS | I&R process | Purchase | Material / Matière |  |  | 2012-01-13 | NO |  |  | 2012-05-03 | 2012-04-25 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-04-25 | Material / Matière modifié en matériel le 13/03/12 selon nvelle déf JCR | 12003 CJ L5 LIAOCHENG / KSB | 12003 CJ L5 LIAOCHENG / KSB : Leakage mechanical sealings pumps
| 12004 | SMB | 2012-02-27 | SMR |  | SCENTS / SULZER |  | Claim |  |  | 10.8199 | SSMB | Leakage mechanical sealings pumps | SYSTEMS | I&R process |  | Material / Matière |  |  | 2012-01-30 | YES | SMR |  | 2012-05-27 | 2012-06-25 | NO | [7 empty] | 0 |  | 2012-06-25 |  | 12004 SCENTS / SULZER | 12004 SCENTS / SULZER : Leakage mechanical sealings pumps
| 12005 | SMB | 2012-03-13 | CCA |  | CJ Shenyang |  | Internal Anomaly |  |  | 10.8399 | SSMB | Forgotten specification & order for material | SYSTEMS | I&R process |  | Manpower / Main d'œuvre |  |  | 2012-01-27 | YES | SOV |  | 2012-06-13 | 2012-05-02 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-05-02 |  | 12005 CJ Shenyang | 12005 CJ Shenyang : Forgotten specification & order for material
| 12006 | SMB | 2012-03-16 | SOV |  | COSUMAR / ACDN |  | Internal Anomaly |  |  | 10.8053 | IEX | Ecart entre notre plan 3D et les tuyauteries fabriquées | SYSTEMS | I&R process | Purchase | Manpower / Main d'œuvre |  |  | 2012-03-13 | YES | SOV |  | 2012-06-16 | 2012-06-11 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-06-11 |  | 12006 COSUMAR / ACDN | 12006 COSUMAR / ACDN : Ecart entre notre plan 3D et les tuyauteries fabriquées
| 12007 | SMB | 2012-04-10 | NLA |  | CARGILL TURQUIE |  | Internal Anomaly |  |  | 10.8825 | IEX | Dimensionnement viroles et oubli soupapes de sécurité au budget | SYSTEMS | I&R process | Acquisition de Cde | Manpower / Main d'œuvre |  |  | 2012-03-26 | YES | CHP - NLA |  | 2012-07-10 | 2012-07-05 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-07-05 |  | 12007 CARGILL TURQUIE | 12007 CARGILL TURQUIE : Dimensionnement viroles et oubli soupapes de sécurité au budget
| 12008 | SMB | 2012-04-10 | LTR |  | CJ Jombang Indonesia |  | Internal Anomaly |  |  | 10.8334 | MF/UF | Conditioning and storage of chinese doc/delayed delivery | SYSTEMS | I&R process |  | Manpower / Main d'œuvre |  |  | 2012-03-14 | YES | HPI |  | 2012-07-10 | 2012-06-26 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-06-26 |  | 12008 CJ Jombang Indonesia | 12008 CJ Jombang Indonesia : Conditioning and storage of chinese doc/delayed delivery
| 12009 | SMB | 2012-04-20 | NPA |  | DANISCO / ONEX |  | Supplier Dysfonctionning |  |  | 10.6506 | SSMB | Réseaux de Chromato fuyard | SYSTEMS | I&R process | Purchase | Material / Matière |  |  | 2012-04-02 | YES | JMR |  | 2012-07-20 | 2012-07-20 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-07-20 |  | 12009 DANISCO / ONEX | 12009 DANISCO / ONEX : Réseaux de Chromato fuyard
| 12010 | SMB | 2012-05-03 | DCI |  | GOI / GE |  | Claim |  |  | CV-1007-0072 | NF | 50 Mbre NF moisies | Cust. Sce | After sales process |  | Material / Matière |  |  | 2012-04-24 | YES | DCI |  | 2012-08-03 | 2012-07-26 | YES | [7 empty] | 0 |  | 2012-07-26 |  | 12010 GOI / GE | 12010 GOI / GE : 50 Mbre NF moisies
| 12011 | SMB | 2012-05-11 | CPI |  | Fisher Bioblock Scientific |  | Internal Anomaly |  |  | RD 2653 | SSMB | Retard Livraison | SYSTEMS | Purchase |  | Manpower / Main d'œuvre |  |  | 2012-04-13 | YES | JMR |  | 2012-08-11 | 2012-07-17 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-07-17 |  | 12011 Fisher Bioblock Scientific | 12011 Fisher Bioblock Scientific : Retard Livraison
| 12012 | SMB | 2012-05-16 | SMR |  | OUEST IMPORT / DIATRANS |  | Internal Anomaly |  |  | 10.7709/ 10/7839 | IEX | Cde silex non livré | SYSTEMS | Purchase | IER | Manpower / Main d'œuvre |  |  | 2012-05-02 | YES | JMR |  | 2012-08-16 | 2012-07-17 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-07-17 |  | 12012 OUEST IMPORT / DIATRANS | 12012 OUEST IMPORT / DIATRANS : Cde silex non livré
| 12013 | SMB | 2012-05-16 | SMR |  | ENSIGN / KCH |  | Claim | YES |  | 10.8282 | SSMB | Leakage on rubber lined pipes | SYSTEMS | I&R process |  | Material / Matière |  |  | 2012-05-11 | YES | CCA |  | 2012-08-16 | 2013-03-21 | NO | [7 empty] | 0 | NO | 2013-03-21 | Ouverture CAP N° 13009 | 12013 ENSIGN / KCH | 12013 ENSIGN / KCH : Leakage on rubber lined pipes
| 12014 | SMB | 2012-06-07 | CVO |  | ADM / BRANT |  | Internal Anomaly |  |  | 10.8590 | IEX | Diameters of holes are too large / nozzles | SYSTEMS | I&R process |  | Manpower / Main d'œuvre |  |  | 2011-12-07 | YES | SOV |  | 2012-09-07 | 2012-09-06 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-09-06 |  | 12014 ADM / BRANT | 12014 ADM / BRANT : Diameters of holes are too large / nozzles
| 12015 | SMB | 2012-06-07 | CVO |  | Frisland / LABBE |  | Supplier Dysfonctionning |  |  | 10.8024 | SSMB | Hauteur de cellule < cote | SYSTEMS | I&R process | Purchase | Material / Matière |  |  | 2012-06-07 | YES | JMR |  | 2012-09-07 | 2012-08-10 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-08-10 |  | 12015 Frisland / LABBE | 12015 Frisland / LABBE : Hauteur de cellule < cote
| 12016 | SMB | 2012-06-07 | CVO |  | Frisland / MTCI |  | Internal Anomaly |  |  | 10.8024 | SSMB | Montage échangeur à plaque sur skid | SYSTEMS | I&R process | Purchase | Manpower / Main d'œuvre |  |  | 2012-05-15 | YES | SOV |  | 2012-09-07 | 2012-09-06 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-09-06 | Material / Matière modifié Manpower / Main d'œuvre le 09/07/12 | 12016 Frisland / MTCI | 12016 Frisland / MTCI : Montage échangeur à plaque sur skid
| 12017 | SMB | 2012-06-07 | CVO |  | Frisland / Euroslot |  | Supplier Dysfonctionning |  |  | 10.8024 | SSMB | Etat surface crépines / Retard livraison | SYSTEMS | I&R process | Purchase | Material / Matière |  |  | 2012-04-20 | YES | JNJ |  | 2012-09-07 | 2012-07-17 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-07-17 |  | 12017 Frisland / Euroslot | 12017 Frisland / Euroslot : Etat surface crépines / Retard livraison
| 12018 | SMB | 2012-06-07 | CCA |  | Meihua 6 |  | Claim |  |  | 10.8232 | MF/UF | Broken Membranes | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2012-06-07 | YES | CCA |  | 2012-09-07 | 2012-09-14 | NO | [7 empty] | 0 |  | 2012-09-14 | Material / Matière modifié Method le 09/07/12 | 12018 Meihua 6 | 12018 Meihua 6 : Broken Membranes
| 12019 | SMB | 2012-06-07 | CCA |  | Glory |  | Internal Anomaly |  |  | 10.8650 | MF/UF | Non delivery of lock nuts | SYSTEMS | I&R process |  | Manpower / Main d'œuvre |  |  | 2012-06-26 | NO |  |  | 2012-09-07 | 2012-07-17 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-07-17 |  | 12019 Glory | 12019 Glory : Non delivery of lock nuts
| 12020 | SMB | 2012-06-12 | BBS |  | projet STEVIA |  | Safety |  |  | EN PPD |  | Trouble de la vision œil gauche |  | PPD Process |  | Manpower / Main d'œuvre |  |  | 2012-05-15 | YES | BBS |  | 2012-09-12 | 2012-08-29 | YES |  |  |  |  | N/A |  |  | 0 |  | 2012-08-29 |  | 12020 projet STEVIA | 12020 projet STEVIA : Trouble de la vision œil gauche
| 12021 | SMB | 2012-07-24 | SOV |  | METIDJI/ACDN/OTIME |  | Supplier Dysfonctionning |  |  | 10.7835 | IEX | Fab tube UB6 collecteur/ Fab et montage tubes de ramification | SYSTEMS | I&R process | Purchase | Material / Matière |  |  | 2012-06-15 | YES | JMR/SOV |  | 2012-10-24 | 2012-10-24 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2012-10-24 |  | 12021 METIDJI/ACDN/OTIME | 12021 METIDJI/ACDN/OTIME : Fab tube UB6 collecteur/ Fab et montage tubes de ramification
| 12022 | SMB | 2012-07-24 | SOV |  | METIDJI |  | Internal Anomaly |  |  | 10.7835 | IEX | Pb fuite clapet+montage / Pb raccord tuyauteries entre brides | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2012-07-08 | YES | SOV |  | 2012-10-24 | 2012-10-24 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2012-10-24 |  | 12022 METIDJI | 12022 METIDJI : Pb fuite clapet+montage / Pb raccord tuyauteries entre brides
| 12023 | SMB | 2012-07-24 | APS |  | PROLACTAL |  | Claim |  |  | 10.8616 | IEX | Perte de charges/ non atteinte de perfomance | SYSTEMS | Order acquirement process | IER | Method / Méthode |  |  | 2012-06-15 | YES | APS/CHP |  | 2012-10-24 | 2012-11-22 | NO | [7 empty] | 0 | YES | 2012-11-22 |  | 12023 PROLACTAL | 12023 PROLACTAL : Perte de charges/ non atteinte de perfomance
| 12024 | SMB | 2012-08-03 | SGU |  | GSK Biologicals |  | Internal Anomaly |  |  | CV-1204-0014 | MF/UF | Spec des joints Kalrez / Diamètre de joints trop large | Cust. Sce | After sales process |  | Manpower / Main d'œuvre |  |  | 2012-07-19 | YES | DCI/SGU/MMA |  | 2012-11-03 | 2012-10-26 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2012-10-26 |  | 12024 GSK Biologicals | 12024 GSK Biologicals : Spec des joints Kalrez / Diamètre de joints trop large
| 12025 | SMB | 2012-08-08 | LPR |  | CARGILL TURQUIE / ACDN |  | Supplier Dysfonctionning |  |  | 10.8825 | IEX | Cote entraxe de perçage de la colonne différent/plan | SYSTEMS | Purchase | IER | Material / Matière |  |  | 2012-06-29 | YES | JMR/MLA |  | 2012-11-08 | 2012-11-05 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2012-11-05 |  | 12025 CARGILL TURQUIE / ACDN | 12025 CARGILL TURQUIE / ACDN : Cote entraxe de perçage de la colonne différent/plan
| 12026 | SMB | 2012-08-23 | TAL |  | CJ Shenyang/Technord |  | Supplier Dysfonctionning |  |  | 10.8399 | SSMB | Dysfonctionnement prestation automation | SYSTEMS | I&R process | Purchase | Material / Matière |  |  | 2012-08-24 | NO |  |  | 2012-11-23 | 2012-11-19 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2012-11-19 |  | 12026 CJ Shenyang/Technord | 12026 CJ Shenyang/Technord : Dysfonctionnement prestation automation
| 12027 | SMB | 2012-09-18 | RCO |  | SYRAL / MTCI / ALPHA LAVAL |  | Internal Anomaly |  |  | 10.7885 | MF/UF | pb de dimension et orientation de la tuyauterie/la pompe d'alimentation | SYSTEMS | I&R process |  | Manpower / Main d'œuvre |  |  | 2012-09-27 | YES | SOV |  | 2012-12-18 | 2012-11-05 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2012-11-05 |  | 12027 SYRAL / MTCI / ALPHA LAVAL | 12027 SYRAL / MTCI / ALPHA LAVAL : pb de dimension et orientation de la tuyauterie/la pompe d'alimentation
| 12028 | SMB | 2012-09-18 | RCO |  | SYRAL / Alphatrad |  | Internal Anomaly |  |  | 10.7885 | MF/UF | Mise en forme PR 06 traduit en espagnol | SYSTEMS | I&R process | Purchase | Manpower / Main d'œuvre |  |  | 2012-09-05 | NO |  |  | 2012-12-18 | 2012-11-05 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2012-11-05 |  | 12028 SYRAL / Alphatrad | 12028 SYRAL / Alphatrad : Mise en forme PR 06 traduit en espagnol
| 12029 | SMB | 2012-09-18 | GTI |  | Armor Proteines |  | Internal Anomaly |  |  | 10.7985-RD 2010-43 | SSMB | Retour pilote pas nettoyé | SYSTEMS | PPD Process |  | Material / Matière |  |  | 2012-03-28 | NO |  |  | 2012-12-18 | 2012-12-06 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2012-12-06 |  | 12029 Armor Proteines | 12029 Armor Proteines : Retour pilote pas nettoyé
| 12030 | SMB | 2012-10-05 | XDE |  | PURIFONCTION / CTI |  | Supplier Dysfonctionning |  |  | RD 2740 | IEX | Défaut fabrication / Pièces manquantes | SYSTEMS | Purchase | IER | Material / Matière |  |  | 2012-09-21 | YES | JMR/MLA/SOV |  | 2013-01-05 | 2012-12-21 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2012-12-21 |  | 12030 PURIFONCTION / CTI | 12030 PURIFONCTION / CTI : Défaut fabrication / Pièces manquantes
| 12031 | SMB | 2012-10-26 | SMR |  | METIDJI |  | Claim |  |  | 10.7835 | IEX | Couleur sirop | SYSTEMS | Order acquirement process | IER | Method / Méthode |  |  | 2012-08-21 | YES | CHP/JLG |  | 2013-01-26 | 2013-02-19 | NO | [7 empty] | 0 | YES | 2013-02-19 |  | 12031 METIDJI | 12031 METIDJI : Couleur sirop
| 12032 | SMB | 2012-12-04 | EWI |  | CJ GMP2 / REYES |  | Internal Anomaly |  |  | 10.8506 | IEX | Modification schémas électriques | SYSTEMS | Purchase | IER | Manpower / Main d'œuvre |  |  | 2012-11-19 | YES | JMR |  | 2013-03-04 | 2013-02-19 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-02-19 | Material / Matière modifié Manpower / Main d'œuvre le 19/02/13 | 12032 CJ GMP2 / REYES | 12032 CJ GMP2 / REYES : Modification schémas électriques
| 12033 | SMB | 2012-12-21 | DCI |  | SA Citrique Belge / DOW |  | Claim |  |  | CV-1202-0002 | IEX | Résines teintées mauve | Cust. Sce | After sales process |  | Material / Matière |  | DOW | 2013-01-03 | YES | DCI |  | 2013-03-21 | 2013-04-15 | NO | [7 empty] | 0 | YES | 2013-04-15 | Attente retour analyse fournisseur suite reprise big bag | 12033 SA Citrique Belge / DOW | 12033 SA Citrique Belge / DOW : Résines teintées mauve
| 13001 | SMB | 2013-01-07 | ELO |  | Galactic | / ROHM HAAS | Claim |  |  | CV-1210-0035 | IEX | Pb délai livraison résines | Cust. Sce | After sales process |  | Material / Matière |  | ROHM HAAS | 2013-01-15 | NO |  |  | 2013-04-07 | 2013-03-29 | YES | [7 empty] | 0 | YES | 2013-03-29 |  | 13001 Galactic | 13001 Galactic : Pb délai livraison résines
| 13002 | SMB | 2013-01-08 | GTI |  | projet NORSK |  | Safety |  |  | EN CUST |  | Coupure pouce/index |  | PPD Process |  | Manpower / Main d'œuvre |  |  | 2013-01-08 | YES | BBS |  | 2013-04-08 | 2013-03-14 | YES |  |  |  |  | N/A |  |  | 0 | YES |  |  | 13002 projet NORSK | 13002 projet NORSK : Coupure pouce/index
| 13003 | SMB | 2013-01-09 | JGO |  | CJ US | / HUAMING | Internal Anomaly |  |  | 10.8573 | IEX | Purchase WF / Choice of EPDM or VITON gasket | SYSTEMS | I&R process | Purchase | Method / Méthode |  |  | 2012-08-28 | NO |  |  | 2013-04-09 | 2013-03-20 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-03-20 |  | 13003 CJ US | 13003 CJ US : Purchase WF / Choice of EPDM or VITON gasket
| 13004 | SMB | 2013-01-09 | JGO |  | CJ US | ENSIVAL MORET | Supplier Dysfonctionning |  |  | 10.8573 | IEX | Pb Norme moteurs IE3/Nema Premium | SYSTEMS | I&R process | Purchase | Material / Matière |  | ENSIVAL MORET | 2012-07-19 | NO |  |  | 2013-04-09 | 2013-03-20 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-03-20 |  | 13004 CJ US | 13004 CJ US : Pb Norme moteurs IE3/Nema Premium
| 13005 | SMB | 2013-01-16 | SGU |  | HILMAR CHEESE | EUROSOLT | Supplier Dysfonctionning |  |  | CA1206-0057/CA1207-0312 | IEX | Retard livraison / Diam des pièces hors spec + slot sales | Cust. Sce | After sales process |  | Material / Matière |  | EUROSLOT | 2012-11-22 | YES | SGU |  | 2013-04-16 | 2013-03-29 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-03-29 |  | 13005 HILMAR CHEESE | 13005 HILMAR CHEESE : Retard livraison / Diam des pièces hors spec + slot sales
| 13006 | SMB | 2013-01-16 | SGU |  | Nestlé | Purifonction/TIA | Supplier Dysfonctionning |  |  | CA1207-0279 / CA1208-0154 | MF/UF | Retard livraison | Cust. Sce | After sales process |  | Material / Matière |  | TIA | 2013-01-18 | YES | SGU |  | 2013-04-16 | 2013-09-03 | NO |  |  |  |  | N/A |  |  | 0 | YES | 2013-09-03 |  | 13006 Nestlé | 13006 Nestlé : Retard livraison
| 13007 | SMB | 2013-01-23 | JPL |  | SHUANGQIAO6 |  | Internal Anomaly |  |  | 10.9122 | MF | Erreur affectation vannes dans coffrets locaux | SYSTEMS | I&R process |  | Manpower / Main d'œuvre |  |  | 2013-01-11 | NO |  |  | 2013-04-23 | 2013-04-15 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-04-15 |  | 13007 SHUANGQIAO6 | 13007 SHUANGQIAO6 : Erreur affectation vannes dans coffrets locaux
| 13008 | SMB | 2013-01-31 | PBO |  | AGRANA | HANGZHOU | Claim |  |  | 10.8755 | MF/UF | Griffes de fixation modules trop longues | Cust. Sce | After sales process |  | Material / Matière |  |  | 2012-12-18 | YES | PBO |  | 2013-04-30 | 2013-04-24 | YES | [7 empty] | 0 | YES | 2013-04-24 |  | 13008 AGRANA | 13008 AGRANA : Griffes de fixation modules trop longues
| 13009 | SMB | 2013-02-06 | SMR |  | TTCA / ENSIGN / | Yixing | Claim | YES |  | 10.8166 - 10.8282 | SSMB | Corrosion rubber-lining columns | SYSTEMS | I&R process | Purchase | Material / Matière |  |  | 2012-12-17 | YES | SMR |  | 2013-05-06 | 2016-06-10 | NO |  |  | dépassé |  | YES |  |  | 0 | YES | 2016-06-10 |  | 13009 TTCA / ENSIGN / | 13009 TTCA / ENSIGN / : Corrosion rubber-lining columns
| 13010 | SMB | 2013-02-14 | JGO |  | CJ GMP2 | COMPOSITES VEC | Internal Anomaly |  |  | 10.8506 | IEX | Certificat ACS de crépines non fournit | SYSTEMS | I&R process | Purchase | Manpower / Main d'œuvre |  |  | 2012-07-18 | NO |  |  | 2013-05-14 | 2013-05-13 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-05-13 |  | 13010 CJ GMP2 | 13010 CJ GMP2 : Certificat ACS de crépines non fournit
| 13011 | SMB | 2013-02-14 | JGO |  | CJ GMP2 | JINLONG | Supplier Dysfonctionning |  |  | 10.8506 | IEX | Deviation on box assembly | SYSTEMS | I&R process | Purchase | Material / Matière |  |  | 2012-10-22 | NO |  |  | 2013-05-14 | 2013-05-13 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-05-13 |  | 13011 CJ GMP2 | 13011 CJ GMP2 : Deviation on box assembly
| 13012 | SMB | 2013-02-26 | CVO |  | ADM Columbus |  | Internal Anomaly |  |  | 10.8590 | IEX | EPDM gaskets are not food grade | SYSTEMS | I&R process | Purchase | Manpower / Main d'œuvre |  |  | 2013-02-28 | YES | SOV |  | 2013-05-26 | 2013-05-14 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-05-14 |  | 13012 ADM Columbus | 13012 ADM Columbus : EPDM gaskets are not food grade
| 13013 | SMB | 2013-04-08 | DCI |  | MEIHUA | CTI | Claim |  |  | CV-1210-0073 | UF | Défaufts d'aspect mbres Kerasep BW 150 KD | Cust. Sce | After sales process |  | Material / Matière |  |  | 2013-05-27 | YES | DCI |  | 2013-07-08 | 2013-07-04 | YES | [7 empty] | 0 | YES | 2013-06-28 |  | 13013 MEIHUA | 13013 MEIHUA : Défaufts d'aspect mbres Kerasep BW 150 KD
| 13014 | SMB | 2013-04-08 | PBO |  | AGRANA |  | Claim |  |  | CV-1210-0003 | MF | Casses membranes en extrémité | Cust. Sce | After sales process |  | Material / Matière |  |  | 2013-05-15 | YES | PBO |  | 2013-07-08 | 2013-10-10 | NO | [7 empty] | 0 | YES | 2013-10-10 |  | 13014 AGRANA | 13014 AGRANA : Casses membranes en extrémité
| 13015 | SMB | 2013-04-22 | JPL |  | SHUANGQIAO6 | /BURKERT | Supplier Dysfonctionning |  |  | 10.9122 | MF | Nombre d'électrovannes assemblés dans îlot | SYSTEMS | Purchase | IER | Material / Matière |  | BURKERT | 2013-03-21 | NO |  |  | 2013-07-22 | 2013-07-17 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-07-12 |  | 13015 SHUANGQIAO6 | 13015 SHUANGQIAO6 : Nombre d'électrovannes assemblés dans îlot
| 13016 | SMB | 2013-04-25 | MBY |  | GOS SWW |  | Safety |  |  | EN CUST |  | Brûlure doigts main gauche |  | PPD Process |  | Manpower / Main d'œuvre |  |  | 2013-04-18 | YES | BBS |  | 2013-07-25 | 2013-06-25 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-06-25 |  | 13016 GOS SWW | 13016 GOS SWW : Brûlure doigts main gauche
| 13017 | SMB | 2013-05-07 | NLA |  | METIDJI |  | Claim | YES |  | 10.7835 | IEX | Couleur sirop et capacité nominale non atteinte | SYSTEMS | Order acquirement process | IER | Method / Méthode |  |  | 2013-04-15 | YES | NLA |  | 2013-08-07 | 2016-04-28 | NO |  |  | dépassé |  | YES |  |  | 0 |  |  |  | 13017 METIDJI | 13017 METIDJI : Couleur sirop et capacité nominale non atteinte
| 13018 | SMB | 2013-05-27 | LLR |  | Fisher Bioblock Scientific |  | Internal Anomaly |  |  | CA-1304-0265 |  | pb organisation gestion des réappro | Cust. Sce | PPD Process | Purchase | Method / Méthode |  |  | 2013-04-18 | YES | BBS |  | 2013-08-27 | 2013-08-20 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-08-20 |  | 13018 Fisher Bioblock Scientific | 13018 Fisher Bioblock Scientific : pb organisation gestion des réappro
| 13019 | SMB | 2013-05-30 | NPA |  | Roquette | ACDN | Internal Anomaly |  |  | 1941/10.8947 | IEX | Erreur de côtes sur plan de détail | SYSTEMS | I&R process | Purchase | Material / Matière |  | ACDN | 2013-06-03 | YES | JMR |  | 2013-08-30 | 2013-08-26 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-08-26 |  | 13019 Roquette | 13019 Roquette : Erreur de côtes sur plan de détail
| 13020 | SMB | 2013-05-31 | JGO |  | Prolactal | ACDN | Supplier Dysfonctionning |  |  | 1954/10.8787 | IEX | Erreurs chaudronnerie | SYSTEMS | I&R process | Purchase | Material / Matière |  | ACDN | 2013-05-31 | YES | JMR |  | 2013-08-31 | 2013-08-26 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-08-26 |  | 13020 Prolactal | 13020 Prolactal : Erreurs chaudronnerie
| 13021 | SMB | 2013-06-04 | SMR |  | Prolactal |  | Claim |  |  | 1954/10.8787 | IEX | Limite de fourniture/ Retard | SYSTEMS | I&R process | Purchase | Method / Méthode |  |  | 2013-05-15 | YES | SMR |  | 2013-09-04 | 2013-12-05 | NO | [7 empty] | 0 | YES | 2013-12-05 |  | 13021 Prolactal | 13021 Prolactal : Limite de fourniture/ Retard
| 13022 | SMB | 2013-06-04 | JNJ |  | Prolactal | API Schmidt | Supplier Dysfonctionning |  |  | 1954/10.8787 | IEX | Retard livraison | SYSTEMS | Purchase |  | Material / Matière |  | API SCHMIDT | 2013-06-11 | NO |  |  | 2013-09-04 | 2013-09-03 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-09-03 |  | 13022 Prolactal | 13022 Prolactal : Retard livraison
| 13023 | SMB | 2013-06-06 | PBO |  | N&A |  | Claim |  |  | CV-1301 0016 | MF/UF | fuite enveloppe K19 | Cust. Sce | After sales process |  | Material / Matière |  |  | 2013-06-05 | NO |  |  | 2013-09-06 | 2013-09-03 | YES | [7 empty] | 0 | YES | 2013-09-03 |  | 13023 N&A | 13023 N&A : fuite enveloppe K19
| 13024 | SMB | 2013-06-11 | ELO |  | GOI |  | Claim |  |  | CV-1210-0040 | IEX | Big bag résine percé | Cust. Sce | After sales process |  | Material / Matière |  |  | 2013-06-11 | NO |  |  | 2013-09-11 | 2013-08-23 | YES | [7 empty] | 0 | YES | 2013-08-23 |  | 13024 GOI | 13024 GOI : Big bag résine percé
| 13025 | SMB | 2013-07-04 | DCI |  | Quantum II/ | LANXESS | Supplier Dysfonctionning |  |  | 10.8364 | SSMB | couleur résines, pigment, pb hydrolyse FOS | Cust. Sce | After sales process | IER | Material / Matière |  | LANXESS | 2013-07-08 | YES | CCA |  | 2013-10-04 | 2013-10-16 | NO |  |  |  |  | N/A |  |  | 0 | YES | 2013-10-16 |  | 13025 Quantum II/ | 13025 Quantum II/ : couleur résines, pigment, pb hydrolyse FOS
| 13026 | SMB | 2013-07-08 | DCI |  | Galactic / | ROHM HAAS | Claim |  |  | CV-1301-0006 | IEX | Conditionnement résines | Cust. Sce | After sales process |  | Material / Matière |  | ROHM HAAS | 2013-07-09 | NO |  |  | 2013-10-08 | 2013-08-26 | YES | [7 empty] | 0 | YES | 2013-08-26 |  | 13026 Galactic / | 13026 Galactic / : Conditionnement résines
| 13027 | SMB | 2013-07-08 | DCI |  | HEC PHARMA |  | Claim |  |  | CV-1303-0091 | MF/UF | Pb expédition groupage Chine | Cust. Sce | After sales process |  | Method / Méthode |  |  | 2013-07-11 | NO |  |  | 2013-10-08 | 2013-10-02 | YES | [7 empty] | 0 | YES | 2013-10-02 |  | 13027 HEC PHARMA | 13027 HEC PHARMA : Pb expédition groupage Chine
| 13028 | SMB | 2013-08-19 | DCI |  | GSK Bio Hamilton (NVS Inc) |  | Claim |  |  | CV-1305-0061 | MF/UF | Casse de 21 membranes à réception | Cust. Sce | After sales process |  | Material / Matière |  |  | 2013-09-16 | NO |  |  | 2013-11-19 | 2013-10-02 | YES | [7 empty] | 0 | YES | 2013-10-02 |  | 13028 GSK Bio Hamilton (NVS Inc) | 13028 GSK Bio Hamilton (NVS Inc) : Casse de 21 membranes à réception
| 13029 | SMB | 2013-08-22 | DCI |  | HEC PHARMA |  | Internal Anomaly |  |  | CV-1303-0091 | MF/UF | palettes plastiques cassées/ tordues | Cust. Sce | After sales process |  | Material / Matière |  |  | 2013-09-16 | NO |  |  | 2013-11-22 | 2013-10-02 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-10-02 |  | 13029 HEC PHARMA | 13029 HEC PHARMA : palettes plastiques cassées/ tordues
| 13030 | SMB | 2013-08-22 | DCI |  | CJ USA/ | LANXESS | Claim |  |  | CV-1212-0055 | IEX | Big bag résine déchiré | Cust. Sce | After sales process |  | Material / Matière |  | LANXESS | 2013-10-02 | NO |  |  | 2013-11-22 | 2014-03-31 | NO | [7 empty] | 0 | NO | 2014-01-07 | CAP 14002 | 13030 CJ USA/ | 13030 CJ USA/ : Big bag résine déchiré
| 13031 | SMB | 2013-08-26 | NPA |  | Roquette | ACDN | Supplier Dysfonctionning |  |  | 1941/10.8947 | IEX | Erreurs chaudronnerie | SYSTEMS | I&R process | Purchase | Material / Matière |  | ACDN | 2013-09-04 | NO |  |  | 2013-11-26 | 2013-11-06 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-11-06 |  | 13031 Roquette | 13031 Roquette : Erreurs chaudronnerie
| 13032 | SMB | 2013-09-13 | ELO |  | Great Ocean Ingredients |  | Claim |  |  | CV-1301-0055 | IEX | Emballage résines moisies à réception | Cust. Sce | After sales process |  | Material / Matière |  | DIATRANS | 2013-10-22 | NO |  |  | 2013-12-13 | 2013-11-26 | YES | [7 empty] | 0 | YES | 2015-02-16 | nvelle expé GOI fin 14, à faire début 2015 à récept° client | 13032 Great Ocean Ingredients | 13032 Great Ocean Ingredients : Emballage résines moisies à réception
| 13033 | SMB | 2013-09-18 | FMG |  | GSK Bio Hamilton (NVS Inc) |  | Claim | YES |  | CV-1308-0033 | MF/UF | pb livraison : conditionnement détérioré | Cust. Sce | After sales process |  | Material / Matière |  |  | 2013-10-04 | NO |  |  | 2013-12-18 | 2013-12-10 | YES | [7 empty] | 0 | YES | 2013-12-10 |  | 13033 GSK Bio Hamilton (NVS Inc) | 13033 GSK Bio Hamilton (NVS Inc) : pb livraison : conditionnement détérioré
| 13034 | SMB | 2013-10-25 | FRU |  | VITALUS |  | Internal Anomaly |  |  | AJO-0239 | IEX/NF/OI | Validation RC3, offre 20-9825-0 | R&D | PPD Process |  | Method / Méthode |  |  | 2013-10-25 | NO |  |  | 2014-01-25 | 2014-01-21 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-01-21 |  | 13034 VITALUS | 13034 VITALUS : Validation RC3, offre 20-9825-0
| 13035 | SMB | 2013-10-30 | EWI |  | Tereos Roumanie / | Moret | Supplier Dysfonctionning |  |  | 1959/10.9292 | IEX | Retard de livraison | SYSTEMS | I&R process | Purchase | Material / Matière |  | MORET | 2013-10-30 | YES | JMR |  | 2014-01-30 | 2014-01-21 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-01-21 |  | 13035 Tereos Roumanie / | 13035 Tereos Roumanie / : Retard de livraison
| 13036 | SMB | 2013-11-04 | LPR |  | CARGILL Russie |  | Internal Anomaly |  |  | 1936/10.8526 | IEX | Incompatibilité norme brides | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2013-12-17 | YES | SOV |  | 2014-02-04 | 2014-01-20 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-01-20 |  | 13036 CARGILL Russie | 13036 CARGILL Russie : Incompatibilité norme brides
| 13037 | SMB | 2013-11-04 | LPR |  | CJ USA |  | Internal Anomaly |  |  | 1931/10.8573 | SSMB | Erreur modélisation colonne | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2013-11-04 | YES | SOV |  | 2014-02-04 | 2013-12-18 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2013-12-18 |  | 13037 CJ USA | 13037 CJ USA : Erreur modélisation colonne
| 13038 | SMB | 2013-11-08 | LPR |  | CJ USA | SPA | Supplier Dysfonctionning | YES |  | 1931/10.8573 | SSMB | Défauts d'ébonitage sur colonnes | SYSTEMS | I&R process |  | Material / Matière |  |  | 2013-11-08 | YES | SMR |  | 2014-02-08 | 2014-05-26 | NO |  |  |  |  | N/A |  |  | 0 | YES | 2014-05-26 |  | 13038 CJ USA | 13038 CJ USA : Défauts d'ébonitage sur colonnes
| 13039 | SMB | 2013-11-12 | NLA |  | ANGEL 2 |  | Claim |  |  | 1933/10.8771 | EVAPO | Qualité de condensat | SYSTEMS | I&R process |  | Material / Matière |  |  | 2013-10-01 | NO |  |  | 2014-02-12 | 2014-11-28 | NO | [7 empty] | 0 | YES | 2014-11-28 |  | 13039 ANGEL 2 | 13039 ANGEL 2 : Qualité de condensat
| 13040 | SMB | 2013-11-13 | EWI |  | Fengning/ | LANXESS | Supplier Dysfonctionning | YES |  | 1938/10.8392 | SSMB | Problème acidité résine | Cust. Sce | After sales process |  | Material / Matière |  | LANXESS | 2013-11-12 | NO |  |  | 2014-02-13 | 2014-02-12 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-02-12 |  | 13040 Fengning/ | 13040 Fengning/ : Problème acidité résine
| 13041 | SMB | 2013-11-22 | WWE |  | CARGILL (Spain/Russie) |  | Internal Anomaly |  |  | 10.9310/10.8526 | IEX | pb orientation entrée/sortie produit sur colonne | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2013-11-25 | YES | SOV |  | 2014-02-22 | 2014-02-20 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-02-20 |  | 13041 CARGILL (Spain/Russie) | 13041 CARGILL (Spain/Russie) : pb orientation entrée/sortie produit sur colonne
| 13042 | SMB | 2013-11-25 | JMR |  | Sunoko2/ | SDV | Supplier Dysfonctionning |  | 1953 | A7629/10.9263 |  | Retard livraison | SYSTEMS | Purchase |  | Material / Matière |  | SDV | 2013-11-25 | YES | JMR |  | 2014-02-25 | 2014-02-05 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-02-05 |  | 13042 Sunoko2/ | 13042 Sunoko2/ : Retard livraison
| 13043 | SMB | 2013-11-26 | JNJ |  | ZUOYAN/ | SDV | Supplier Dysfonctionning |  | 1964 | A7307/10.9602 | SSMB | Détérioration de big bag lors de l'empotage | SYSTEMS | Purchase | After sales | Material / Matière |  | SDV | 2013-11-08 | YES | JNJ |  | 2014-02-26 | 2014-01-28 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-09-10 |  | 13043 ZUOYAN/ | 13043 ZUOYAN/ : Détérioration de big bag lors de l'empotage
| 13044 | SMB | 2013-12-05 | SGU |  | MEIHUA / | CTI | Claim | YES | NA | CV-1310-0020 | MF/UF | Défaufts d'aspect mbres Kerasep BW 150 KD | Cust. Sce | After sales process | PMP Purchase | Material / Matière |  | CTI | 2014-01-09 | NO |  |  | 2014-03-05 | 2014-02-27 | YES | [7 empty] | 0 | YES | 2014-09-04 | Suivi réception 20 nvelles mbres par NVS Asia/client final | 13044 MEIHUA / | 13044 MEIHUA / : Défaufts d'aspect mbres Kerasep BW 150 KD
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14001 Syral.doc | 14001 | SMB | 2014-01-10 | EWI |  | TEREOS SYRAL / | GE | Claim |  | NA | CV-1304-0074 | NF | Performances/Déformations membranes NF | Cust. Sce | After sales process | PMP Purchase | Material / Matière |  | GE | 2014-02-04 | YES | EWI |  | 2014-04-10 | 2014-07-16 | NO |  | 2014-02-26 | [5 empty] | 0 | YES | 2015-09-02 | A faire 9 mois après MES NF3, au 28/11 (5 mois après) ça tourne bien | 14001 TEREOS SYRAL / | 14001 TEREOS SYRAL / : Performances/Déformations membranes NF
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14002 CJ US Big bag résine déchiré.doc | 14002 | SMB | 2014-01-10 | EWI |  | CJ US | LANXESS / SDV | Supplier Dysfonctionning | YES | NA | CV-1212-0055 | SSMB | 1 Big bag résine déchiré | Cust. Sce | After sales process | logistic | Material / Matière |  | LANXESS | 2014-01-10 | YES | EWI |  | 2014-04-10 | 2014-03-31 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-11-28 | Nvelle livraison BB Lanxess pour CJ fin sept. | 14002 CJ US | 14002 CJ US : 1 Big bag résine déchiré
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14003 De Smet fonctionnement skid NF.doc | 14003 | SMB | 2014-01-28 | EWI |  | De Smet Yemen |  | Internal Anomaly |  | 1872 | 1872/10.7410 | NF | Fonctionnement skid NF (débit perméat élevé) | SYSTEMS | IER : démarrage prdt | Purchase mbre SMB | Method / Méthode |  | ALTING | 2014-02-04 | YES | EWI |  | 2014-04-28 | 2014-04-18 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-09-02 | Mise en route nvelle unité NF en NP30 OK, fonctionnement hydraulique correct. | 14003 De Smet Yemen | 14003 De Smet Yemen : Fonctionnement skid NF (débit perméat élevé)
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14004 CARGILL Russie valves damages.doc | 14004 | SMB | 2014-02-12 | LPR |  | CARGILL Russie |  | Internal Anomaly |  | 1936 | 1936/10.8526 | IEX | Dommages sur vannes papillon | SYSTEMS | IER : CTR récept° | Purchase :CTR fnr | Material / Matière |  |  | 2014-03-19 | YES | SOV |  | 2014-05-12 | 2014-05-12 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-09-11 | Suivre ADM project (SOV) | 14004 CARGILL Russie | 14004 CARGILL Russie : Dommages sur vannes papillon
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14005 CJ US piping leakage.doc | 14005 | SMB | 2014-02-12 | LPR |  | CJ USA |  | Internal Anomaly |  | 1931 | 1931/10.8573 | SSMB | Fuites sur tuyauterie ébonitée | SYSTEMS | IER : CTR récept° | Purchase : CTR fnr | Material / Matière |  |  | 2014-03-21 | NO |  |  | 2014-05-12 | 2014-05-12 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-09-08 |  | 14005 CJ USA | 14005 CJ USA : Fuites sur tuyauterie ébonitée
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14006 BETA retard mise à disposiiton colonnes pour BMA.doc | 14006 | SMB | 2014-02-20 | ExRTH |  | BMA | BETA | Supplier Dysfonctionning |  | 1971 | 1971/10.9517 | IEX | Retard mise à disposition colonnes | SYSTEMS | Purchase | Reception at supplier | Material / Matière |  |  | 2014-03-20 | NO |  |  | 2014-05-20 | 2014-04-18 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-04-18 |  | 14006 BMA | 14006 BMA : Retard mise à disposition colonnes
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14007 Vitalus.doc | 14007 | SMB | 2014-02-28 | BBS |  | VITALUS |  | Internal Anomaly |  | NA | AJO-0239 | IEX/NF/OI | Résultats essais non exploitables | R&D | PPD Process |  | Method / Méthode |  |  | 2014-03-11 | YES | BBS |  | 2014-05-28 | 2014-05-21 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-09-09 | Réussite Vilatus2, cde basic design | 14007 VITALUS | 14007 VITALUS : Résultats essais non exploitables
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14008 Nestlé.doc | 14008 | SMB | 2014-03-13 | PBO |  | NESTLE CHILI |  | Claim |  | NA | CV 1211 -0008 | UF | trous en surface couche 150 KD | Cust. Sce | After sales process | PMP Purchase | Material / Matière |  | CTI | 2014-03-28 | NO |  |  | 2014-06-13 | 2014-05-14 | YES |  | 2014-04-22 | [5 empty] | 0 | YES | 2014-05-14 |  | 14008 NESTLE CHILI | 14008 NESTLE CHILI : trous en surface couche 150 KD
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14009 RZBC.doc | 14009 | SMB | 2014-03-17 | CCA |  | RZBC |  | Claim |  | 1967 | 10.9131 | IEX/CA/SSMB | cracks on rubber lining columns | SYSTEMS | I&R process | Reception | Environment / Milieu |  |  | 2014-04-01 | YES | CCA |  | 2014-06-17 | 2014-05-26 | YES |  | 2014-03-26 | [5 empty] | 0 | YES | 2014-09-04 | en sept. 14 (après 3 mois de fonctionnement) | 14009 RZBC | 14009 RZBC : cracks on rubber lining columns
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14010 Zuoyan SDV Resin label.doc | 14010 | SMB | 2014-03-20 | CCA |  | ZUOYAN | SDV | Supplier Dysfonctionning |  | 1968 | 1968/10.9680 | IEX | démarquage résines | SYSTEMS | Purchase | Logistic | Material / Matière |  | SDV | 2014-03-20 | NO |  |  | 2014-06-20 | 2014-06-11 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-09-04 |  | 14010 ZUOYAN | 14010 ZUOYAN : démarquage résines
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14011 EVONIK Fermas.doc | 14011 | SMB | 2014-03-27 | SGU |  | EVONIK FERMAS | CTI | Claim |  | NA | CV-1301-0011 | MF/UF | Flèche et casse mbre Kerasep | Cust. Sce | After sales process | PMP Purchase | Material / Matière |  | CTI | 2014-05-20 | YES | SGU |  | 2014-06-27 | 2014-06-26 | YES |  | 2014-04-08 | [5 empty] | 0 | YES | 2014-11-28 | audit PBO/SGU réalisé 14 au 16/10/14 conseil sur CIP | 14011 EVONIK FERMAS | 14011 EVONIK FERMAS : Flèche et casse mbre Kerasep
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14012 GOS4-ACDN.doc | 14012 | SMB | 2014-03-31 | CVO |  | GOS4 | ACDN | Supplier Dysfonctionning |  | 1965 | 1965/10.9245 | IEX | fourniture de joints non pleine bride | SYSTEMS | Purchase | Reception | Material / Matière |  |  | 2014-05-26 | NO |  |  | 2014-06-30 | 2014-06-20 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-08-28 |  | 14012 GOS4 | 14012 GOS4 : fourniture de joints non pleine bride
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14013 GOS4-CH06.doc | 14013 | SMB | 2014-03-31 | CVO |  | GOS4 |  | Internal Anomaly |  | 1965 | 1965/10.9245 | IEX | erreur de plans ramification | SYSTEMS | I&R process | Meca Design | Manpower / Main d'œuvre |  |  | 2014-01-28 | YES | SOV |  | 2014-06-30 | 2014-05-26 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-05-26 |  | 14013 GOS4 | 14013 GOS4 : erreur de plans ramification
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14014 GOS4-ICP.doc | 14014 | SMB | 2014-03-31 | CVO |  | GOS4/ | ICP | Supplier Dysfonctionning |  | 1965 | 1965/10.9245 | IEX | défaut épaisseur ébonitage /regards | SYSTEMS | Purchase | Reception | Material / Matière |  |  | 2014-02-20 | YES | SOV |  | 2014-06-30 | 2014-05-26 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-05-26 |  | 14014 GOS4/ | 14014 GOS4/ : défaut épaisseur ébonitage /regards
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14015 GOS4- Plastexel.doc | 14015 | SMB | 2014-03-31 | CVO |  | GOS4/ | Plastexel | Supplier Dysfonctionning |  | 1965 | 1965/10.9245 | IEX | Abs. trous fixation regards | SYSTEMS | Purchase | Reception | Material / Matière |  |  | 2014-02-20 | NO |  |  | 2014-06-30 | 2014-05-26 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-05-26 |  | 14015 GOS4/ | 14015 GOS4/ : Abs. trous fixation regards
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14016 Ingredion.doc | 14016 | SMB | 2014-04-15 | LZE |  | Ingredion/ | Cole Parmer | Supplier Dysfonctionning |  | NA | AVO-13-0096 | SSMB | Pompe HS sur pilote SSMB | Cust. Sce | After sales process | NVS INC | Method / Méthode |  |  | 2014-05-22 | YES | LZE |  | 2014-07-15 | 2014-07-09 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-09-15 |  | 14016 Ingredion/ | 14016 Ingredion/ : Pompe HS sur pilote SSMB
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14017 ADM Network design.doc | 14017 | SMB | 2014-04-24 | WWE |  | ADM |  | Internal Anomaly |  | 1951 | 10.8754 | IEX | mixed bed top networks design | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2014-04-14 | YES | SOV |  | 2014-07-24 | 2014-06-23 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2014-10-30 | Au 30/10 : OK pas de nouveau pb, vérification plans par SOV | 14017 ADM | 14017 ADM : mixed bed top networks design
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14018 ASR Qtity and dimensions fasteners.doc | 14018 | SMB | 2014-04-24 | WWE |  | ASR |  | Internal Anomaly |  | 1969 | 10.9470 | IEX | fasteners qtity and dimensions of mixed beds | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2014-04-24 | YES | SOV |  | 2014-07-24 | 2014-07-16 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-08-28 | au 30/10/14 : en cours avec LPR, tableau à finaliser, std à identifier | 14018 ASR | 14018 ASR : fasteners qtity and dimensions of mixed beds
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14019 Zuoyan Strainers tightening.doc | 14019 | SMB | 2014-04-24 | WWE |  | ZUOYAN |  | Internal Anomaly |  | 1968 | 1968/10.9680 | IEX | strainers tightening | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2014-04-24 | YES | SOV |  | 2014-07-24 | 2014-07-16 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-08-28 | au 30/10/14 : en Chine pas de prémontage, la cale est intégrée dans nos plans std, SOV demande à Chine de faire de même. | 14019 ZUOYAN | 14019 ZUOYAN : strainers tightening
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14020 Cevital ébonite crépine NF.doc | 14020 | SMB | 2014-05-21 | NCH |  | CEVITAL |  | Internal Anomaly |  | 1339 | 10.6499 | IEX | dégradation ébonite/casse crépine | Cust. Sce | I&R process | Meca Design | Method / Méthode |  |  | 2014-07-15 | NO |  |  | 2014-08-21 | 2014-07-16 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-09-02 | Afaire en Nov suite MES extension avec nvelle crépine (cylindrique/conique) | 14020 CEVITAL | 14020 CEVITAL : dégradation ébonite/casse crépine
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14021 Olmedo ébonite NF.doc | 14021 | SMB | 2014-05-21 | NCH |  | TEREOS OLMEDO |  | Internal Anomaly |  | 1849 | 10.7690 | IEX | arrachement ébonite interne colonne | Cust. Sce | I&R process | Meca Design | Method / Méthode |  |  | 2014-06-12 | NO |  |  | 2014-08-21 | 2014-07-16 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-09-02 | Vieillissement colonnes | 14021 TEREOS OLMEDO | 14021 TEREOS OLMEDO : arrachement ébonite interne colonne
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14022 Pièces de NF Knappe.doc | 14022 | SMB | 2014-05-21 | NCH |  | CEVITAL | KNAPPE | Supplier Dysfonctionning |  | 1952 | 10.6499 / 10.7690 | NF | déformation collecteur perméat NF / corrosion bague alu des TP | Cust. Sce | I&R process | Meca Design /Purchase | Material / Matière |  | KNAPPE | 2014-06-12 | NO |  |  | 2014-08-21 | 2015-01-07 | NO |  |  |  |  | N/A |  |  | 0 | NO | 2015-09-02 | CAP 15015 | 14022 CEVITAL | 14022 CEVITAL : déformation collecteur perméat NF / corrosion bague alu des TP
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14023 SUNOKO.doc | 14023 | SMB | 2014-06-24 | CCA |  | SUNOKO | Dupont | Claim |  | 1953 | 1953/10.9263 | SSMB | non atteinte de la capacité contractuelle | SYSTEMS | I&R process | Purchase | Material / Matière |  | DuPont | 2014-06-24 | YES | CCA/NPA |  | 2014-09-24 | 2016-01-14 | NO |  | 2014-06-24 | 2015-05-01 | 2016-01-01 | NO |  |  | 0 |  | A faire 10/16 |  | 14023 SUNOKO | 14023 SUNOKO : non atteinte de la capacité contractuelle
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14024 Accdt PWT.doc | 14024 | SMB | 2014-07-15 | CPT |  | Service IT |  | Safety |  | NA | NA | NA | Chute escalier suite malaise | NA | IT |  | Manpower / Main d'œuvre |  |  | 2014-10-27 | YES | CPT |  | 2014-10-15 | 2014-11-26 | NO |  |  |  |  | N/A |  |  | 0 | YES | 2015-06-29 |  | 14024 Service IT | 14024 Service IT : Chute escalier suite malaise
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14025 ADM Lanxess Problèmes livraison inerte.doc | 14025 | SMB | 2014-08-25 | EWI |  | ADM | LANXESS | Supplier Dysfonctionning |  | 1984 | 1984/10.9728 | SSMB | Problèmes livraison inerte | Cust. Sce | After sales process |  | Material / Matière |  | LANXESS | 2014-08-01 | NO |  |  | 2014-11-25 | 2014-10-17 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-09-02 |  | 14025 ADM | 14025 ADM : Problèmes livraison inerte
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14026 Dow Problèmes livraison résines.doc | 14026 | SMB | 2014-08-25 | EWI |  | Conaprole - VRS | DOW | Supplier Dysfonctionning |  | 1980 | 1980/10.9726 | SSMB | Problèmes livraison résines | Cust. Sce | After sales process |  | Material / Matière |  | DOW | 2014-08-05 | NO |  |  | 2014-11-25 | 2014-10-03 | YES |  |  |  |  | N/A |  |  | 0 | NO | 2014-11-28 | voir CAP14038 | 14026 Conaprole - VRS | 14026 Conaprole - VRS : Problèmes livraison résines
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14027 Tanichem - Jinlong.doc | 14027 | SMB | 2014-09-29 | WWE |  | Tanichem | Wuxi Jinlong | Supplier Dysfonctionning | YES | 1976 | 10.8531 | IEX | Erreur dimensions bride de tampon (GB Code / ASME) | SYSTEMS | I&R process | Meca Design | Material / Matière |  |  | 2014-10-25 | YES | SOV |  | 2014-12-29 | 2014-12-22 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-08-28 |  | 14027 Tanichem | 14027 Tanichem : Erreur dimensions bride de tampon (GB Code / ASME)
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14028 CONAPROLE TUYAUTERIE NON FABRIQUEE.doc | 14028 | SMB | 2014-10-09 | LPR |  | Conaprole | STCL | Supplier Dysfonctionning |  | 1980 | 10.9726 | IEX | tuyauteries entrée lavage manquantes | SYSTEMS | I&R process | Meca Design /Purchase | Material / Matière |  |  | 2014-09-30 | YES | SOV |  | 2015-01-09 | 2015-01-06 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-08-28 |  | 14028 Conaprole | 14028 Conaprole : tuyauteries entrée lavage manquantes
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14029 CEVITAL démarrage extension.doc | 14029 | SMB | 2014-10-10 | RTH |  | Cevital |  | Claim |  | 1952 | 1952/10.8259 | IEX | Durée d'arrêt raffinerie - redémarrage | SYSTEMS | I&R process | AEI Design | Method / Méthode |  |  | 2014-11-06 | YES | EWI |  | 2015-01-10 | 2014-11-28 | YES |  | 2014-11-06 | 2014-11-01 | 2014-11-01 | YES |  |  | 0 | YES | 2015-09-02 |  | 14029 Cevital | 14029 Cevital : Durée d'arrêt raffinerie - redémarrage
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14030 GE Absence retard ARCs BLs.doc | 14030 | SMB | 2014-10-21 | EWI |  | GE |  | Supplier Dysfonctionning |  | NA | NA | NF | Absence/retard systématique d'ARCs et B/Ls | Cust. Sce | After sales process | Purchase | Material / Matière |  | GE | 2014-10-20 | NO |  |  | 2015-01-21 | 2014-11-28 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-09-02 |  | 14030 GE | 14030 GE : Absence/retard systématique d'ARCs et B/Ls
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14031 Tableur glucoserie.doc | 14031 | SMB | 2014-10-21 | AME |  | ALMASIRAH |  | Internal Anomaly |  | NA | offre 20.10129 | IEX | Erreur calcul conso électrique glucoserie | SYSTEMS | Order acquirement process | Chiffrage Procédé | Method / Méthode |  |  | 2014-10-17 | NO |  |  | 2015-01-21 | 2015-10-29 | NO |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-09 |  | 14031 ALMASIRAH | 14031 ALMASIRAH : Erreur calcul conso électrique glucoserie
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14032 SUNOKO Spider.doc | 14032 | SMB | 2014-10-31 | NPA |  | SUNOKO | Ziyou | Supplier Dysfonctionning |  | 1953 | 1953/10.9263 | SSMB | Fuite sur tuyauterie de distribution (araignée) | SYSTEMS | IER : concept° Etude Méca | Purchase NVS Asia | Material / Matière |  |  | 2014-10-24 | YES | CCA |  | 2015-01-31 | 2015-01-27 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-08-28 |  | 14032 SUNOKO | 14032 SUNOKO : Fuite sur tuyauterie de distribution (araignée)
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14033 ENSIVAL_MORET.doc | 14033 | SMB | 2014-11-03 | SML |  | CJ US | ENSIVAL MORET | Claim |  | 1953 | 1931/10.8573 | IEX | Ampérage moteurs des pompes excessif | SYSTEMS | I&R process | AEI Design | Material / Matière |  |  | 2014-12-16 | YES | SMR |  | 2015-02-03 | 2015-04-21 | NO |  | 2015-01-09 | 2015-04-01 | 2015-04-01 | YES |  |  | 0 | YES | 2015-10-29 |  | 14033 CJ US | 14033 CJ US : Ampérage moteurs des pompes excessif
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14034 SUNOKO Columns.doc | 14034 | SMB | 2014-11-05 | NPA |  | SUNOKO | Greens | Supplier Dysfonctionning |  | 1953 | 1953/10.9263 | SSMB | Fuite sur tampon trou d'homme d'entrée réseau (colonnes) | SYSTEMS | IER : concept° Etude Méca | Purchase NVS Asia | Material / Matière |  |  | 2014-10-24 | YES | CCA |  | 2015-02-05 | 2015-02-02 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-08-28 |  | 14034 SUNOKO | 14034 SUNOKO : Fuite sur tampon trou d'homme d'entrée réseau (colonnes)
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14035 SUNOKO Grids.doc | 14035 | SMB | 2014-11-06 | NPA |  | SUNOKO |  | Internal Anomaly |  | 1953 | 9263 | SSMB | Déformation grille sur réseau (intérieur colonne) | SYSTEMS | IER : concept° Etude Méca | Purchase NVS Asia | Material / Matière |  |  | 2014-10-24 | YES | CCA |  | 2015-02-06 | 2015-01-13 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-10-29 |  | 14035 SUNOKO | 14035 SUNOKO : Déformation grille sur réseau (intérieur colonne)
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14036 Sanofi Chimie Aramon Carbosep.doc | 14036 | SMB | 2014-11-18 | PBO |  | Sanofi Chimie Aramon |  | Internal Anomaly |  | NA | contrat carbosep | CARBOSEP | erreur stock membranes réservées | Cust. Sce | After sales process | Supply Chain PMP | Method / Méthode |  |  | 2014-11-28 | YES | PBO |  | 2015-02-18 | 2015-02-05 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-09-02 |  | 14036 Sanofi Chimie Aramon | 14036 Sanofi Chimie Aramon : erreur stock membranes réservées
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14037 SENSUS essais PPD.doc | 14037 | SMB | 2014-11-18 | VGA |  | SENSUS |  | Internal Anomaly |  | NA | EN 2894 | SSMB | retard essais PPD | R&D | PPD Process | Pilot | Method / Méthode |  |  | 2014-11-18 | YES | BBS |  | 2015-02-18 | 2015-02-10 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-09-08 |  | 14037 SENSUS | 14037 SENSUS : retard essais PPD
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2014\14038 Armor Protéines Retard livraison résine.doc | 14038 | SMB | 2014-11-28 | EWI |  | Armor Proteines | DOW | Claim |  | NA | CV-1410-0028 | SSMB | Retard de livraison résine | Cust. Sce | After sales process |  | Material / Matière |  | DOW | 2014-11-26 | NO |  |  | 2015-02-28 | 2015-01-13 | YES |  | 2014-12-11 | [5 empty] | 0 | NO | 2015-09-02 | voir CAP15018 | 14038 Armor Proteines | 14038 Armor Proteines : Retard de livraison résine
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15001 Solanic dimensions trou d'homme.doc | 15001 | SMB | 2015-01-12 | CVO | IER | Solanic |  | Claim |  | 1987 | 8023 | IEX | Dimensions trous d'homme cuve back wash | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2014-12-16 | NO |  |  | 2015-04-12 | 2015-03-13 | YES |  |  | 2015-04-01 | 2015-03-01 | YES |  |  | 0 | YES | 2015-08-28 |  | 15001 Solanic | 15001 Solanic : Dimensions trous d'homme cuve back wash
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15002 Solanic - CTI.doc | 15002 | SMB | 2015-01-12 | CVO | IER | Solanic | CTI | Internal Anomaly |  | 1987 | 8023 | IEX | Absence Pression d'air / marquage colonnes | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2015-04-02 | NO |  |  | 2015-04-12 | 2015-04-08 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-08-28 |  | 15002 Solanic | 15002 Solanic : Absence Pression d'air / marquage colonnes
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15003 Solanic - MTCI.doc | 15003 | SMB | 2015-01-12 | CVO | IER | Solanic | MTCI | Internal Anomaly |  | 1987 | 8023 | IEX | Erreur diamètre tuyauterie skids | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2015-01-13 | NO |  |  | 2015-04-12 | 2015-03-13 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-08-28 |  | 15003 Solanic | 15003 Solanic : Erreur diamètre tuyauterie skids
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15004 TUNISIE SUCRE.doc | 15004 | SMB | 2015-01-13 | CVO | IER | Tunisie sucre |  | Internal Anomaly |  | 8101 | 9933 | IEX | Pompe neutralisation endommagée | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2015-04-02 | NO |  |  | 2015-04-13 | 2015-04-08 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-08-28 |  | 15004 Tunisie sucre | 15004 Tunisie sucre : Pompe neutralisation endommagée
| 15005 | SMB | 2015-01-16 | PBO | CS | Jungbunzlauer | CTI | Claim |  | NA | CV-1411-0052 | MF | Défaut longueur d'étanchement mbre Kerasep | Cust. Sce | After sales process | Supply Chain PMP | Material / Matière |  |  | 2015-03-11 | YES | EWI |  | 2015-04-16 | 2015-04-13 | YES |  | 2015-03-11 | [5 empty] | 0 | YES | 2016-11-07 | pas de nvelle cde Kerasep | 15005 Jungbunzlauer | 15005 Jungbunzlauer : Défaut longueur d'étanchement mbre Kerasep
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15006 Tereos - GE joints NF.doc | 15006 | SMB | 2015-02-17 | PBO | CS | TEREOS NESLE | GE | Claim |  | NA | CA 13040375 | NF | Joints plus larges sur 20 éléments | Cust. Sce | After sales process |  | Material / Matière |  | GE | 2015-03-11 | NO |  |  | 2015-05-17 | 2015-04-13 | YES |  | 2015-03-27 | [5 empty] | 0 | YES | 2015-09-02 |  | 15006 TEREOS NESLE | 15006 TEREOS NESLE : Joints plus larges sur 20 éléments
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15007 ADM venting nozzle orientation.doc | 15007 | SMB | 2015-02-18 | WWE | NVSA | ADM | Greens | Internal Anomaly |  | 1984 | 9728 | SSMB | Conflit entre évent et réseau intérieur colonne | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2015-01-19 | YES | SOV |  | 2015-05-18 | 2015-05-11 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-08-28 |  | 15007 ADM | 15007 ADM : Conflit entre évent et réseau intérieur colonne
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15008 Cevital fuite sur colonne de décoloration.doc | 15008 | SMB | 2015-02-23 | EWI | CS | Cevital | Green / SPA | Claim |  | 1952 | 8259 | Decolo | Fuite sur colonne de décoloration | SYSTEMS | I&R process | Purchase NVSA | Material / Matière |  |  | 2015-03-04 | YES | ExFLU/PGA |  | 2015-05-23 | 2016-08-23 | NO |  | 2015-03-04 | 2015-05-01 | 2016-08-23 | NO |  |  | 0 |  | A faire 02/17 | après mise en sce | 15008 Cevital | 15008 Cevital : Fuite sur colonne de décoloration
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15009 ADM DIT length.doc | 15009 | SMB | 2015-02-27 | WWE | NVSA | ADM | Endress Hauser | Internal Anomaly |  | 1984 | 9728 | SSMB | erreur longueur DIT | SYSTEMS | I&R process | AEI Design | Method / Méthode |  |  | 2015-01-12 | YES | SOV |  | 2015-05-27 | 2015-05-11 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2015-08-28 |  | 15009 ADM | 15009 ADM : erreur longueur DIT
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15010 Bioamber columns lining leaks.doc | 15010 | SMB | 2015-03-02 | NPA | IER | Bioamber | KCH | Claim |  | 1973 | 9323 | IEX | hard rubber lining leaks | SYSTEMS | I&R process | Purchase NVSA | Environment / Milieu |  |  | 2015-05-06 | NO |  |  | 2015-06-02 | 2015-12-08 | NO |  | 2015-04-29 | [5 empty] | 0 |  | A faire 12/16 | à l'issue litige juridique | 15010 Bioamber | 15010 Bioamber : hard rubber lining leaks
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15011 Bioamber Backwash tank.doc | 15011 | SMB | 2015-03-02 | NPA | IER | Bioamber |  | Internal Anomaly |  | 1973 | 9323 | IEX | no backwash tank on PID | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2015-05-29 | NO |  |  | 2015-06-02 | 2015-09-10 | NO |  |  |  |  | N/A |  |  | 0 | YES | 2016-06-29 |  | 15011 Bioamber | 15011 Bioamber : no backwash tank on PID
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15012 Central Romana.doc | 15012 | SMB | 2015-03-05 | FBU | STP | Central Romana |  | Internal Anomaly |  | 1945 | 9918 | IEX | Ecart nbre de pompe figurant dans l'offre/fourni | SYSTEMS | Order acquirement process | Chiffrage Procédé | Manpower / Main d'œuvre |  |  | 2015-03-23 | NO |  |  | 2015-06-05 | 2015-05-19 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-09 |  | 15012 Central Romana | 15012 Central Romana : Ecart nbre de pompe figurant dans l'offre/fourni
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15013 GSK Hamilton Etanchement mbre.doc | 15013 | SMB | 2015-03-11 | SGU | CS | GSK Bio Hamilton (NVS Inc) |  | Claim |  | NA | CV-1309-0087 | MF/UF | Tenue étanchement mbre kerasep | Cust. Sce | After sales process | Supply Chain PMP | Material / Matière | [6 empty] | 2015-06-11 | Cancelled | NO | [7 empty] | 0 |  |  |  | 15013 GSK Bio Hamilton (NVS Inc) | 15013 GSK Bio Hamilton (NVS Inc) : Tenue étanchement mbre kerasep
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15014 Arab Sweeteners.doc | 15014 | SMB | 2015-03-17 | CHP | STP | Arab Sweeteners |  | Internal Anomaly |  | NA | 20.105 | CPL | erreur estimatif OPEX | SYSTEMS | Order acquirement process | Chiffrage Procédé | Manpower / Main d'œuvre |  |  | 2015-03-18 | NO |  |  | 2015-06-17 | 2015-06-08 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-09 |  | 15014 Arab Sweeteners | 15014 Arab Sweeteners : erreur estimatif OPEX
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15015 Tunisie Sucre bouchon tubes de pression.doc | 15015 | SMB | 2015-03-23 | NPA | IER | Tunisie sucre | KNAPPE | Internal Anomaly | YES | 8101 | 10.6835 | NF | Déformation bouchon Tube de pression | SYSTEMS | I&R process | Meca Design | Material / Matière |  |  | 2015-05-11 | NO |  |  | 2015-06-23 | 2015-10-22 | NO |  |  |  |  | N/A |  |  | 0 | YES | 2016-06-29 | bouchons inox OK | 15015 Tunisie sucre | 15015 Tunisie sucre : Déformation bouchon Tube de pression
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15016 Sofivo.doc | 15016 | SMB | 2015-04-10 | EWI | CS | Sofivo | MEGA | Claim |  | NA | CV-1502-0077 | ED | Aspect visuel et fonctionnement stacks neufs | Cust. Sce | After sales process |  | Method / Méthode |  |  | 2015-03-24 | NO |  |  | 2015-07-10 | 2015-06-04 | YES |  | 2015-03-24 | [5 empty] | 0 | YES | 2016-11-07 | Nvelle cde à livrer S27 2016 | 15016 Sofivo | 15016 Sofivo : Aspect visuel et fonctionnement stacks neufs
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15017 Sedamyl.doc | 15017 | SMB | 2015-04-28 | EWI | CS | SEDAMYL | GE | Claim |  | NA | cv 1502-0012 | NF | Emballage abimé | Cust. Sce | After sales process |  | Material / Matière |  | GE | 2015-05-27 | YES | EWI |  | 2015-07-28 | 2015-07-27 | YES |  | 2015-05-27 | [5 empty] | 0 | YES | 2016-06-28 |  | 15017 SEDAMYL | 15017 SEDAMYL : Emballage abimé
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15018 Sunpaper.doc | 15018 | SMB | 2015-04-28 | EWI | CS | Sunpaper | DOW | Supplier Dysfonctionning | YES | 1997 | 10390 | CHR | Retard livraison résine | Cust. Sce | After sales process |  | Material / Matière |  | DOW | 2015-04-28 | YES | EWI |  | 2015-07-28 | 2015-07-06 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-06-28 |  | 15018 Sunpaper | 15018 Sunpaper : Retard livraison résine
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15019 Solanic Tuyauterie.doc | 15019 | SMB | 2015-05-05 | CVO | IER | Solanic | MTCI | Supplier Dysfonctionning |  | 1987 | 8023 | IEX | Alignement tuyauterie | SYSTEMS | I&R process | Meca Design | Material / Matière |  |  | 2015-05-06 | YES | SOV |  | 2015-08-05 | 2015-07-16 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-08 |  | 15019 Solanic | 15019 Solanic : Alignement tuyauterie
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15020 Solanic Joint.doc | 15020 | SMB | 2015-05-05 | CVO | IER | Solanic |  | Internal Anomaly |  | 1987 | 8023 | IEX | Joint sur-contraints | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2015-07-06 | YES | SOV |  | 2015-08-05 | 2015-07-07 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-08 |  | 15020 Solanic | 15020 Solanic : Joint sur-contraints
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15021 Solanic Volume mort.doc | 15021 | SMB | 2015-05-05 | CVO | IER | Solanic |  | Internal Anomaly |  | 1987 | 8023 | IEX | Vidangeabilité tuyauterie | SYSTEMS | I&R process | Meca Design | Manpower / Main d'œuvre |  |  | 2015-05-06 | NO |  |  | 2015-08-05 | 2015-07-07 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-08 |  | 15021 Solanic | 15021 Solanic : Vidangeabilité tuyauterie
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15022 Al Masirah Cation column internal support conflict.doc | 15022 | SMB | 2015-06-08 | WWE | NVSA | ALMASIRAH |  | Internal Anomaly |  | 1992 | 10129 | IEX | conflicts between strainer support and sight glass | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2015-06-08 | YES | SOV |  | 2015-09-08 | 2015-08-25 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-08-23 |  | 15022 ALMASIRAH | 15022 ALMASIRAH : conflicts between strainer support and sight glass
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15023 Al Masirah IEX column nozzles plate.doc | 15023 | SMB | 2015-06-08 | WWE | NVSA | ALMASIRAH |  | Internal Anomaly |  | 1992 | 10129 | IEX | noozles arrangement (conflict with head) | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2015-06-08 | YES | SOV |  | 2015-09-08 | 2015-08-25 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-08-23 |  | 15023 ALMASIRAH | 15023 ALMASIRAH : noozles arrangement (conflict with head)
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15024 joints_Maagtechnic.docx | 15024 | SMB | 2015-06-29 | JGO | IER | Shunangqiao5 | MAAGTECHNIC | Supplier Dysfonctionning |  | 1944 | 8410 | SSMB | défaut joints EPDM | SYSTEMS | I&R process | Meca Design | Material / Matière |  | Maagtechnic | 2015-05-28 | NO |  |  | 2015-09-29 | 2015-09-10 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-06-29 | après mise en route installation | 15024 Shunangqiao5 | 15024 Shunangqiao5 : défaut joints EPDM
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15025 CENTRAL ROMANA isometric drawing.doc | 15025 | SMB | 2015-06-29 | LPR | IER | Central Romana | PLASTICON | Supplier Dysfonctionning |  | 1945 | 9918 | IEX | Pb front piping assembly | SYSTEMS | I&R process | Meca Design | Material / Matière |  | Plasticon | 2015-06-04 | NO |  |  | 2015-09-29 | 2015-09-29 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-07-21 | Après montage installation | 15025 Central Romana | 15025 Central Romana : Pb front piping assembly
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15026 Scents EL drawings.doc | 15026 | SMB | 2015-07-02 | JPL | IER | Scents |  | Internal Anomaly |  | 1983 | 9574 | IEX | Wiring and EL drawings updated | SYSTEMS | I&R process | AEI Design | Method / Méthode |  |  | 2015-06-30 | NO |  |  | 2015-10-02 | 2015-09-22 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-09-15 |  | 15026 Scents | 15026 Scents : Wiring and EL drawings updated
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15027 SUNOKO TRISLOT.doc | 15027 | SMB | 2015-07-22 | NPA | IER | Sunoko | TRISLOT | Supplier Dysfonctionning |  | 1953 | 9263 | SSMB | Default slot distribution grids floor | SYSTEMS | I&R process | Site acceptance | Material / Matière |  | Filtr'action | 2015-09-10 | NO |  |  | 2015-10-22 | 2015-10-14 | YES |  |  |  |  | N/A |  |  | 0 |  | A faire 12/16 | attente livraison nvelle colonne | 15027 Sunoko | 15027 Sunoko : Default slot distribution grids floor
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15028 Tetrapack- raccords SMS.doc | 15028 | SMB | 2015-07-22 | LPR | IER | TetraPak | STCL | Internal Anomaly |  | 1990 | 9838 | IEX | SMS diameter fitting | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2015-10-20 | NO |  |  | 2015-10-22 | 2015-10-21 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-07-21 |  | 15028 TetraPak | 15028 TetraPak : SMS diameter fitting
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15029 ASR gasket.doc | 15029 | SMB | 2015-07-28 | LPR | IER | ASR | WUXI JINLONG | Claim |  | 1969 | 10.9470 | IEX | Characteristics gasket column | SYSTEMS | Purchase |  | Material / Matière |  |  | 2015-08-05 | YES | DBA/SMR |  | 2015-10-28 | 2017-01-23 | NO |  | 2015-10-19 | 2016-01-01 | 2017-01-23 | NO |  |  | 0 |  |  |  | 15029 ASR | 15029 ASR : Characteristics gasket column
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15030 Meihua 6.doc | 15030 | SMB | 2015-07-31 | SGU | CS | MEIHUA 6 | CTI | Claim |  | NA | CV-1410-0027/0048 | MF/UF | Abrasion 0,1 µ membrane | Cust. Sce | After sales process | Purchase | Material / Matière |  | CTI | 2015-07-20 | YES | SGU |  | 2015-10-31 | 2016-09-30 | NO |  | 2015-07-17 | [5 empty] | 0 |  | A faire 02/17 |  | 15030 MEIHUA 6 | 15030 MEIHUA 6 : Abrasion 0,1 µ membrane
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15031 Conaprole.doc | 15031 | SMB | 2015-08-25 | PGA | IER | Conaprole |  | Internal Anomaly |  | 1980 | 9726 | IEX | Communication dysfonctionning - Lack of documents transmission | SYSTEMS | I&R process | Meca Design | Manpower / Main d'œuvre |  |  | 2015-09-09 | NO |  |  | 2015-11-25 | 2015-10-09 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-09-15 |  | 15031 Conaprole | 15031 Conaprole : Communication dysfonctionning - Lack of documents transmission
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15032 PT SUJ Sand filter nozzles.doc | 15032 | SMB | 2015-09-17 | TFR | IER | PT SUJ2 | Lianyungang | Supplier Dysfonctionning |  | 1995 | 10268 | NF | Nozzles length/sand filter floor thickness | SYSTEMS | Purchase | NVSA | Material / Matière |  |  | 2015-11-13 | NO |  |  | 2015-12-17 | 2015-12-04 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-08 |  | 15032 PT SUJ2 | 15032 PT SUJ2 : Nozzles length/sand filter floor thickness
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15033 Tetrapack Erreur AU02.doc | 15033 | SMB | 2015-09-22 | SML | IER | TETRAPACK |  | Internal Anomaly |  | 1990 | 9838 | IEX | Erreur dans AU02 | SYSTEMS | I&R process | AEI Design | Manpower / Main d'œuvre |  |  | 2015-11-12 | NO |  |  | 2015-12-22 | 2015-12-09 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-07 |  | 15033 TETRAPACK | 15033 TETRAPACK : Erreur dans AU02
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15034 CONAPROLE Cablage client avec mauvais schémas électriques.doc | 15034 | SMB | 2015-09-22 | SML | IER | Conaprole | BOSSARD | Supplier Dysfonctionning |  | 1980 | 9726 | IEX | Non diffusion dernière révision schéma électrique | SYSTEMS | I&R process | AEI Design | Material / Matière |  | BOSSARD | 2015-12-09 | NO |  |  | 2015-12-22 | 2015-12-09 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-07 |  | 15034 Conaprole | 15034 Conaprole : Non diffusion dernière révision schéma électrique
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15035 Diffusion schémas électriques pour cablage client.doc | 15035 | SMB | 2015-09-22 | SML | IER | Service AEI |  | Prevent / improve |  | NA | NA | NA | Diffusion client révisions schémas électriques | SYSTEMS | I&R process | AEI Design | Method / Méthode |  |  | 2015-12-11 | NO |  |  | 2015-12-22 | 2015-12-18 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-07 |  | 15035 Service AEI | 15035 Service AEI : Diffusion client révisions schémas électriques
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15036 BBCA performance issue.doc | 15036 | SMB | 2015-09-23 | ExLGR | IER | BBCA |  | Claim |  | 1970 | 9364 | SSMB | contractual performance not achieved (CA recovery) | SYSTEMS | I&R process | Reception | Method / Méthode |  |  | 2015-09-23 | YES | LGR/SMR |  | 2015-12-23 | 2018-01-10 | NO |  | 2015-09-16 | 2016-03-01 | 2018-01-10 | NO |  |  | 0 | NA |  | pas de volonté du client de mettre en œuvre plan d'action NVS | 15036 BBCA | 15036 BBCA : contractual performance not achieved (CA recovery)
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15037 NORAM PR réseaux SSMB4.doc | 15037 | SMB | 2015-09-28 | ExSVN | STP | Noram (DFI) |  | Internal Anomaly |  | NA | 20.1135 | SSMB | Erreur dans formule de calcul du Prix de revient des internes | SYSTEMS | Order acquirement process | Chiffrage Procédé | Manpower / Main d'œuvre |  |  | 2015-11-17 | NO |  |  | 2015-12-28 | 2015-12-04 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-09 |  | 15037 Noram (DFI) | 15037 Noram (DFI) : Erreur dans formule de calcul du Prix de revient des internes
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15038 Dow erreur résine.doc | 15038 | SMB | 2015-10-02 | EWI | CS | Friesland Foods | DOW | Supplier Dysfonctionning |  | NA | CV-1504-0043 | IEX | Mauvaise résine livrée dans 2 sacs | Cust. Sce | After sales process | Resins purchase | Material / Matière |  | DOW | 2015-10-02 | NO |  |  | 2016-01-02 | 2015-12-22 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-06-28 |  | 15038 Friesland Foods | 15038 Friesland Foods : Mauvaise résine livrée dans 2 sacs
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15039 Location Pilote.doc | 15039 | SMB | 2015-10-02 | PDU | R&D | CAPUA | ROQUETTE | Internal Anomaly |  | NA | CV-1508-0047 | MF/UF | Location pilote même période à 2 clients | R&D | PPD Process | Pilot rent | Method / Méthode |  |  | 2015-11-09 | YES | BBS |  | 2016-01-02 | 2015-12-09 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-05-09 |  | 15039 CAPUA | 15039 CAPUA : Location pilote même période à 2 clients
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15040 intervention sur sorbonnes R&D.doc | 15040 | SMB | 2015-10-05 | GTI | R&D | Service R&D | VINCI | Supplier Dysfonctionning |  | NA |  | NA | Coupure électrique lors de l'intervention sur sorbonnes labo | R&D | PPD Process | Labs | Material / Matière |  | Vinci | 2015-10-01 | NO |  |  | 2016-01-05 | 2015-12-18 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-05-09 |  | 15040 Service R&D | 15040 Service R&D : Coupure électrique lors de l'intervention sur sorbonnes labo
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15041 Sédamyl - GE.doc | 15041 | SMB | 2015-10-06 | EWI | CS | SEDAMYL | GE | Claim |  | NA | CV-1502-0012 | NF | Baisse performances membranes NF (skid N°2) | Cust. Sce | After sales process |  | Material / Matière |  | GE | 2015-12-08 | YES | PBO |  | 2016-01-06 | 2016-02-23 | NO | [7 empty] | 0 | YES | 2016-11-07 | Mise en route d'un 5eme TP | 15041 SEDAMYL | 15041 SEDAMYL : Baisse performances membranes NF (skid N°2)
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15042 Al Nouran.doc | 15042 | SMB | 2015-10-29 | CCR | STP | Al Nouran |  | Internal Anomaly |  | 2002 | 10510 | Decolo | Surdimensionnement échangeur | SYSTEMS | I&R process | process conception | Manpower / Main d'œuvre |  |  |  | NO |  |  | 2016-01-29 | 2016-01-11 | YES |  |  |  |  | N/A |  |  | 0 |  | A faire 12/16 |  | 15042 Al Nouran | 15042 Al Nouran : Surdimensionnement échangeur
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15043 Incident chariot.doc | 15043 | SMB | 2015-11-23 | CPT | R&D | Unilever |  | Safety |  | NA | EN 2900 | NA | Renversement IBC de KOH | R&D | PPD Process | Pilot | Manpower / Main d'œuvre |  |  | 2015-11-06 | YES | CPT |  | 2016-02-23 | 2016-01-06 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-05-09 |  | 15043 Unilever | 15043 Unilever : Renversement IBC de KOH
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15044 FRIESLAND GOS4.doc | 15044 | SMB | 2015-11-24 | VGA | Sales | Friesland Foods GOS4 |  | Claim |  | 1965 | 9245 | Decolo | Développement biofilm et bactérie | Cust. Sce |  |  | Method / Méthode |  |  |  | YES | DBA |  | 2016-02-24 | 2016-11-09 | NO | [7 empty] | 0 |  | A faire 02/17 |  | 15044 Friesland Foods GOS4 | 15044 Friesland Foods GOS4 : Développement biofilm et bactérie
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15045 AL MASIRAH - puissance moteurs.doc | 15045 | SMB | 2015-11-30 | RBA | IER | Almasirah | PADOVAN | Supplier Dysfonctionning |  | 1992 | 10129 | IEX | Ecart puissance moteur transmis | SYSTEMS | I&R process | Meca Design / Puchase | Material / Matière |  | Padovan | 2016-02-11 | NO |  |  | 2016-02-29 | 2016-02-23 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-15 |  | 15045 Almasirah | 15045 Almasirah : Ecart puissance moteur transmis
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15046 explosion Erlenmeyer Labo.doc | 15046 | SMB | 2015-11-30 | CPT | R&D | Tanichem |  | Safety |  | NA | 2015-026 | NA | Explosion Erlenmeyer | R&D | PPD Process |  | Equipment / Matériel |  |  | 2015-09-30 | YES | CPT |  | 2016-02-29 | 2016-01-26 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-05-09 |  | 15046 Tanichem | 15046 Tanichem : Explosion Erlenmeyer
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2015\15047 Olmedo.doc | 15047 | SMB | 2015-12-21 | EWI | CS | Téréos Olmédo | ICP Beugin | Internal Anomaly | YES | 1876 | 7690 | Decolo | fissure ébonite déformation plancher | Cust. Sce | After sales process |  | Manpower / Main d'œuvre |  |  | 2016-02-04 | YES | RRA |  | 2016-03-21 | 2016-09-23 | NO |  |  |  |  | N/A |  |  | 0 |  | A faire 01/17 |  | 15047 Téréos Olmédo | 15047 Téréos Olmédo : fissure ébonite déformation plancher
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2016\16001 ADM spray nozzle.doc | 16001 | SMB | 2016-01-04 | LPR | IER | ADM |  | Internal Anomaly |  | 1984 | 9728 | SSMB | lack of spray nozzles | SYSTEMS | I&R process | Meca Design | Manpower / Main d'œuvre |  |  | 2015-10-08 | NO |  |  | 2016-04-04 | 2016-03-18 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-09 |  | 16001 ADM | 16001 ADM : lack of spray nozzles
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2016\16002 ADM vacuum breaker.doc | 16002 | SMB | 2016-01-04 | LPR | IER | ADM |  | Internal Anomaly |  | 1984 | 9728 | IEX | vaccum breaker missing | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  | 2015-10-27 | YES | SOV |  | 2016-04-04 | 2016-03-21 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-09 |  | 16002 ADM | 16002 ADM : vaccum breaker missing
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2016\16003 FRIESLANDFOOD GOS4 rupture joints.docx | 16003 | SMB | 2016-01-06 | DBA | CS | Friesland Foods GOS4 |  | Internal Anomaly |  | 1965 | 9245 | Decolo | breaking gasket | Cust. Sce | After sales process | audit | Method / Méthode |  |  | 2016-02-01 | NO |  |  | 2016-04-06 | 2016-03-04 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-10 |  | 16003 Friesland Foods GOS4 | 16003 Friesland Foods GOS4 : breaking gasket
\\srvwork\AQHSE\1-FICHES_CAP\\CAP_EMISES 2016\16004 CSC Sugar.doc | 16004 | SMB | 2016-01-11 | ExSVN | STP | CSC Sugar |  | Internal Anomaly |  | NA | 28.11698 | IEX | process design error liquid sugar | SYSTEMS | Order acquirement process | process design | Manpower / Main d'œuvre |  |  | 2015-12-29 | YES | CHP |  | 2016-04-11 | 2016-03-31 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-11-09 |  | 16004 CSC Sugar | 16004 CSC Sugar : process design error liquid sugar
R:\QA-NVA IB\CAP\16005 MEFSCO IEX deformation.doc | 16005 | NVSA | 2016-01-11 | WWE | IER | MEFSCO | JINLONG | Supplier Dysfonctionning |  | 1974 | 9876 | IEX | floor deformations issue | SYSTEMS | I&R process |  | Material / Matière |  |  | 2016-01-12 | YES | WWE |  | 2016-04-11 | 2016-05-16 | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 16005 MEFSCO | 16005 MEFSCO : floor deformations issue
R:\QA-NVA IB\CAP\16006 ADM Fibersol limit switch issue.doc | 16006 | NVSA | 2016-01-11 | SLI | IER | ADM | Bray | Claim |  | 1984 | 9728 | SSMB/IEX | quality issue of limit switch | SYSTEMS | Purchase |  | Material / Matière |  |  | 2015-12-03 | YES | SLI |  | 2016-04-11 | 2016-03-21 | YES |  | 2015-03-12 | 2016-04-11 | 2016-03-21 | YES |  |  | 0 | YES | 2016-11-16 |  | 16006 ADM | 16006 ADM : quality issue of limit switch
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2016\16007 GOI.doc | 16007 | SMB | 2016-01-28 | DBA | CS | GOI |  | Internal Anomaly |  | 1640 | 10.6760 | IEX | leak and cation rubber lining cracks | Cust. Sce | After sales process | audit | Material / Matière |  |  |  | YES | EWI |  | 2016-04-28 | 2016-04-26 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-03 |  | 16007 GOI | 16007 GOI : leak and cation rubber lining cracks
\\srvwork\AQHSE\1-FICHES_CAP\CAP_EMISES 2016\16008 MEFSCO - AF.doc | 16008 | SMB | 2016-02-09 | XRO | IER | MEFSCO |  | Internal Anomaly |  | 1974 | 9876 | IEX | mistake in functional analysis | SYSTEMS | I&R process | Process Design (AF) | Method / Méthode |  |  |  | YES | CHP |  | 2016-05-09 | 2016-05-09 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-11-20 |  | 16008 MEFSCO | 16008 MEFSCO : mistake in functional analysis
R:\QA-NVA IB\CAP\16009 PT SUJ HCl pump issue.doc | 16009 | NVSA | 2016-02-22 | VCH | IER | PT SUJ | IWAKI | Claim |  | 1995 | 10268 | Decolo | Acid pump issue | SYSTEMS | Purchase |  | Material / Matière |  |  | 2016-01-05 | NO |  |  | 2016-05-22 | 2016-07-04 | NO |  |  | 2016-06-01 | 2016-06-28 | NO |  |  | 0 |  |  |  | 16009 PT SUJ | 16009 PT SUJ : Acid pump issue
R:\QA-NVA IB\CAP\16010 PT SUJ steril filter.doc | 16010 | NVSA | 2016-02-22 | VCH | IER | PT SUJ | Sunshine | Claim |  | 1972 | 9407 | NF | plate deformation of sterile filter | SYSTEMS | Purchase |  | Material / Matière |  |  | 2016-02-18 | NO |  |  | 2016-05-22 | 2016-08-30 | NO |  |  | August-16 | 2016-08-30 | YES |  |  | 0 |  |  |  | 16010 PT SUJ | 16010 PT SUJ : plate deformation of sterile filter
CAP_EMISES 2016\16011 incohérence doc AU02-PR02-PR06.doc | 16011 | SMB | 2016-02-23 | CPV | STP | Shuangqiao5 Fufeng |  | Internal Anomaly |  | 1944 | 8410 |  | inconsistency between AU02-PR02-PR06 | SYSTEMS | I&R process | AEI Design | Method / Méthode |  |  | 2015-12-31 | YES | SOV |  | 2016-05-23 | 2017-04-05 | NO |  |  |  |  | N/A |  |  | 0 |  | A faire 12/17 |  | 16011 Shuangqiao5 Fufeng | 16011 Shuangqiao5 Fufeng : inconsistency between AU02-PR02-PR06
CAP_EMISES 2016\16012 Solanic CTI-ACDN.doc | 16012 | SMB | 2016-02-26 | JMR | IER | Solanic | CTI-ACDN | Claim |  | 8106 | 10.8023 | IEX | cell leak of IEX column | SYSTEMS | I&R process | Meca design | Material / Matière |  |  | 2016-02-24 | YES | SMR |  | 2016-05-26 | 2017-09-05 | NO |  | 2016-04-06 | 2016-09-30 | 2017-09-05 | NO |  |  | 0 |  | A faire 01/18 |  | 16012 Solanic | 16012 Solanic : cell leak of IEX column
R:\QA-NVA IB\CAP\16013 PT JMR & PT DSI CIP tank leaking issue.doc | 16013 | NVSA | 2016-03-01 | SUXI | IER | PT Jawamanis & DUTA | ALLIBERT | Supplier Dysfonctionning |  | 2005&2006 | 10.11070&10.11169 | NF | Leaking between two parts in CIP tank(PP) | SYSTEMS | Purchase |  | Material / Matière |  |  | 2016-02-23 | NO |  |  | 2016-06-01 | 2016-03-17 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2016-09-10 |  | 16013 PT Jawamanis & DUTA | 16013 PT Jawamanis & DUTA : Leaking between two parts in CIP tank(PP)
CAP_EMISES 2016\16014 Glanbia.doc | 16014 | SMB | 2016-03-18 | XRO | IER | Glanbia | Bilfinger | Claim |  | 1981 | 9922 | IEX | bent nozzles and leaking fine mesch resin | SYSTEMS | I&R process |  | Material / Matière |  |  | 2016-03-11 | NO |  |  | 2016-06-18 | 2016-06-09 | YES |  | 2016-03-09 | 2016-06-18 | 2016-06-09 | YES |  |  | 0 | NO | 2016-10-06 | CAP 16039 | 16014 Glanbia | 16014 Glanbia : bent nozzles and leaking fine mesch resin
CAP_EMISES 2016\16015 TESSIER.doc | 16015 | SMB | 2016-04-04 | PBO | CS | TESSIER | Progress | Internal Anomaly |  | NA | NA | MF/UF | keeping of K138 gaskets | Cust. Sce | After sales process |  | Material / Matière |  |  | 2015-12-31 | YES | PBO |  | 2016-07-04 | 2016-06-28 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-03 |  | 16015 TESSIER | 16015 TESSIER : keeping of K138 gaskets
R:\QA-NVA IB\CAP\16016 Meihua 9 Floc & white sediment issue.doc | 16016 | NVSA | 2016-05-05 | EGU | IER | Meihua 9 |  | Internal Anomaly |  | 2004 | 2014/10.11218 | MF | Floc & white sediment issue | SYSTEMS | I&R process | reception | Material / Matière |  |  |  | YES | EGU |  | 2016-08-05 | 2016-11-15 | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 16016 Meihua 9 | 16016 Meihua 9 : Floc & white sediment issue
CAP_EMISES 2016\16017 CLS taggins.doc | 16017 | SMB | 2016-05-18 | XDE | IER | CLS |  | Internal Anomaly |  | 2013 | 11461 |  | late taggings change | SYSTEMS | I&R process | AEI Design (TAG) | Method / Méthode |  |  | 2016-04-29 | YES | CPV/SOV |  | 2016-08-18 | 2016-07-22 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-10 |  | 16017 CLS | 16017 CLS : late taggings change
CAP_EMISES 2016\16018 Central Romana Rubberlining.doc | 16018 | SMB | 2016-05-24 | FCA | IER | Central Romana | SPA | Internal Anomaly |  | 1985 | 9918 | Decolo | Rubberlining damage | SYSTEMS | I&R process | commissioning | Material / Matière |  |  | 2016-02-19 | YES | PGA |  | 2016-08-24 | 2016-12-07 | NO |  |  |  |  | N/A |  |  | 0 |  | A faire 12/17 | intervention MGL/Brandt pour vérifier état de l'ébonitage S48/49 | 16018 Central Romana | 16018 Central Romana : Rubberlining damage
CAP_EMISES 2016\16019 Valio.doc | 16019 | SMB | 2016-06-15 | PBO | CS | VALIO | Supply Chain Pompey | Claim |  | NA | CV-1602-0067 | MF/UF | Air-tightness carbosep modules | Cust. Sce | After sales process |  | Material / Matière |  |  | 2016-06-13 | YES | PBO |  | 2016-09-15 | 2016-09-08 | YES | [7 empty] | 0 | YES | 2016-11-07 |  | 16019 VALIO | 16019 VALIO : Air-tightness carbosep modules
CAP_EMISES 2016\16020 NUTRIBIO.doc | 16020 | SMB | 2016-06-20 | RWA | IER | Boccard/Nutribio | Concept Inox | Supplier Dysfonctionning |  | 2011 | 10282 | NF | Input/output exchanger reverse | SYSTEMS | Purchase | Reception | Material / Matière |  | Concept Inox | 2016-06-30 | NO |  |  | 2016-09-20 | 2016-09-20 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-20 |  | 16020 Boccard/Nutribio | 16020 Boccard/Nutribio : Input/output exchanger reverse
R:\QA-NVA IB\CAP\16021 CLS MB internals mounting issue.doc | 16021 | NVSA | 2016-06-22 | SXI | IER | CLS | Gree | Supplier Dysfonctionning |  | 2013 | 11416 | IEX | Internals design and assembly issue | SYSTEMS | I&R process |  | Material / Matière |  |  | 2016-06-08 | YES | RCH |  | 2016-09-22 | 2016-07-26 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 16021 CLS | 16021 CLS : Internals design and assembly issue
R:\QA-NVA IB\CAP\16022 Agrana IEX column head deformation issue.doc | 16022 | NVSA | 2016-06-22 | WWE | IER | AGRANA | Gree | Supplier Dysfonctionning |  | 2014 | 10416 | IEX | columns head deformation issue | SYSTEMS | I&R process |  | Material / Matière |  |  | 2016-06-02 | YES | RCH/WWE |  | 2016-09-22 | 2016-10-17 | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 16022 AGRANA | 16022 AGRANA : columns head deformation issue
R:\QA-NVA IB\CAP\16023 ADM leakgae risk issue of SSMB strainer.doc | 16023 | NVSA | 2016-06-22 | SLI | IER | ADM | Runyuan | Supplier Dysfonctionning |  | 2022 | 11279 | SSMB | leakage risk issue of SSMB strainers | SYSTEMS | I&R process |  | Material / Matière |  |  | 2016-05-06 | YES | SLI |  | 2016-09-22 | 2016-08-09 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 16023 ADM | 16023 ADM : leakage risk issue of SSMB strainers
CAP_EMISES 2016\16024 AGRANA.doc | 16024 | SMB | 2016-07-13 | ACR | IER | AGRANA |  | Internal Anomaly |  | 2014 | 10416 | IEX | IEX Columns : design pressure & booster pumps | SYSTEMS | I&R process | process design | Manpower / Main d'œuvre |  |  | 2016-06-30 | YES | NGO |  | 2016-10-13 | 2016-10-07 | YES |  |  |  |  | N/A |  |  | 0 |  | A faire 12/17 | à faire qd unités seront au débit nominal fin 17. | 16024 AGRANA | 16024 AGRANA : IEX Columns : design pressure & booster pumps
| 16025 | NVSA | 2016-07-27 | RCH | IER | AGRANA | Plasticon | Supplier Dysfonctionning |  | 2014 | 10416 | IEX | quality issue of PP-FRP front piping | SYSTEMS | I&R process | reception | Material / Matière |  |  | 2016-07-08 | YES | RCH |  | 2016-10-27 | 2016-08-09 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 16025 AGRANA | 16025 AGRANA : quality issue of PP-FRP front piping
CAP_EMISES 2016\16026 Friesland Foods calcul colonnes.doc | 16026 | SMB | 2016-07-27 | EWI | CS | Friesland Foods GOS4 | ACDN-CTI | Claim | YES | 1965 | 9245 | Decolo | Erreur calcul colonnes | Cust. Sce | I&R process | Meca Design | Material / Matière |  | ACDN | 2016-07-08 | YES | SMR |  | 2016-10-27 | 2017-04-07 | NO | [7 empty] | 0 | YES | 2017-10-10 |  | 16026 Friesland Foods GOS4 | 16026 Friesland Foods GOS4 : Erreur calcul colonnes
CAP_EMISES 2016\16027 Boccard Nutribio récupération égouttures.doc | 16027 | SMB | 2016-07-29 | JGO | IER | Boccard/Nutribio |  | Internal Anomaly |  | 2011 | 10282 | NF | Débordements collecte égouttures vannes | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | SOV |  | 2016-10-29 | 2016-10-20 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-19 |  | 16027 Boccard/Nutribio | 16027 Boccard/Nutribio : Débordements collecte égouttures vannes
CAP_EMISES 2016\16028 Incident évapo.doc | 16028 | SMB | 2016-07-29 | MED | R&D | ERAMET |  | Safety |  | EN2988 | 2015-055 | Evapo | désolidarisation colonne évapo | R&D |  |  | Method / Méthode |  |  |  | YES | GTI |  | 2016-10-29 | 2016-10-26 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-11 |  | 16028 ERAMET | 16028 ERAMET : désolidarisation colonne évapo
CAP_EMISES 2016\16029 Eramet Pb As.doc | 16029 | SMB | 2016-07-29 | MED | R&D | ERAMET |  | Safety |  | EN2988 | 2015-055 |  | présence As | R&D |  |  | Material / Matière |  |  |  | YES | CHP |  | 2016-10-29 | 2016-10-26 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-11 |  | 16029 ERAMET | 16029 ERAMET : présence As
R:\QA-NVA IB\CAP\16030 RZBC 2 IEX anion column leg insufficient issue.doc | 16030 | NVSA | 2016-08-18 | WWE | IER | RZBC | Gree | Supplier Dysfonctionning |  | 2015 | 11722 | IEX | IEX Columns : Leg strength | SYSTEMS | I&R process |  | Material / Matière |  |  | 2016-08-18 | YES | WWE |  | 2016-11-18 | 2016-10-17 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 16030 RZBC | 16030 RZBC : IEX Columns : Leg strength
CAP_EMISES 2016\16031 Pilote Polypeptides.doc | 16031 | SMB | 2016-08-26 | SGU | CS | Polypeptide Laboratories | TIA | Claim |  | NA | CV-1601-0076 | NF | corrosion corps de pompe d'alimentation | Cust. Sce | After sales process | Purchase | Material / Matière |  | TIA |  | YES | SGU |  | 2016-11-26 | 2017-03-10 | NO | [7 empty] | 0 | YES | 2017-10-03 |  | 16031 Polypeptide Laboratories | 16031 Polypeptide Laboratories : corrosion corps de pompe d'alimentation
CAP_EMISES 2016\16032 Tuyauteries Al Nouran.doc | 16032 | SMB | 2016-09-06 | XDE | IER | Al Nouran | Allia | Internal Anomaly |  | 2002 | 10510 | Decolo | Revêtement anti-corrosion sur tuyauteries | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | NO |  |  | 2016-12-06 | 2016-10-26 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-10 |  | 16032 Al Nouran | 16032 Al Nouran : Revêtement anti-corrosion sur tuyauteries
CAP_EMISES 2016\16033 Tetrapak.doc | 16033 | SMB | 2016-09-13 | NPA | IER | Tetrapak | Méga | Claim |  | 1990 | 9838 | ED | Rupture tuyau soude sur ED | SYSTEMS | I&R process | commissioning | Material / Matière |  | Mega |  | YES | JMR |  | 2016-12-13 | 2017-05-03 | NO |  | 2016-09-14 | déc.16 | 2017-05-03 | YES |  |  | 0 | YES | 2017-11-20 |  | 16033 Tetrapak | 16033 Tetrapak : Rupture tuyau soude sur ED
CAP_EMISES 2016\16034 Tanichem accessibility.doc | 16034 | SMB | 2016-09-14 | JGO | IER | Tanichem |  | Internal Anomaly |  | 1976 | 8531 | all | Accessibility and ergonomic improvements | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | SOV |  | 2016-12-14 | 2016-11-21 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-19 |  | 16034 Tanichem | 16034 Tanichem : Accessibility and ergonomic improvements
CAP_EMISES 2016\16035 Tanichem design issue.doc | 16035 | SMB | 2016-09-14 | JGO | IER | Tanichem |  | Internal Anomaly |  | 1976 | 8531 | all | Design issues (insulation, rupture discs spec) | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | SOV |  | 2016-12-14 | 2016-11-21 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-19 |  | 16035 Tanichem | 16035 Tanichem : Design issues (insulation, rupture discs spec)
CAP_EMISES 2016\16036 Tanichem welding on hydrogenation reactor.doc | 16036 | SMB | 2016-09-14 | JGO | IER | Tanichem | Gree | Internal Anomaly |  | 1976 | 8531 | all | Welds on reactor after ASME certification | SYSTEMS | I&R process | Meca Design | Material / Matière |  |  |  | YES | SOV |  | 2016-12-14 | 2016-12-13 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-10 |  | 16036 Tanichem | 16036 Tanichem : Welds on reactor after ASME certification
CAP_EMISES 2016\16037 Conaprole Uruguay.doc | 16037 | SMB | 2016-09-30 | PGA | IER | Conaprole |  | Claim |  | 1980 | 9726 | NF | protein content lower than contractual guaranty | SYSTEMS | I&R process | commissioning | Environment / Milieu |  |  |  | YES | PGA |  | 2016-12-30 | 2017-10-20 | NO |  | 2016-10-04 | 2017-02-28 | 2017-10-20 | NO |  |  | 0 |  | A faire 03/18 |  | 16037 Conaprole | 16037 Conaprole : protein content lower than contractual guaranty
CAP_EMISES 2016\16038 CJ Brésil durée de vie membranes BE.doc | 16038 | SMB | 2016-10-03 | EWI | CS | CJ Brésil | CTI | Claim |  | NA | CV-1404-0085 | MF | Kerasep membrane lifetime | Cust. Sce | After sales process | Purchase | Method / Méthode |  |  |  | YES | EWI |  | 2017-01-03 | 2017-01-02 | YES | [7 empty] | 0 | YES | 2017-10-03 |  | 16038 CJ Brésil | 16038 CJ Brésil : Kerasep membrane lifetime
CAP_EMISES 2016\16039 Glanbia.doc | 16039 | SMB | 2016-10-06 | XRO | IER | Glanbia | Bilfinger | Claim |  | 1981 | 9922 | IEX | bent nozzles and leaking fine mesch resin | SYSTEMS | I&R process |  | Method / Méthode |  |  |  | YES | XRO |  | 2017-01-06 | 2017-07-27 | NO |  | 2016-09-19 | 2017-12-31 | 2017-07-01 | YES |  |  | 0 |  | A faire 01/18 |  | 16039 Glanbia | 16039 Glanbia : bent nozzles and leaking fine mesch resin
R:\QA-NVA IB\CAP\16040 KLIM Cambodia column installed with wrong orientation issue.doc | 16040 | NVSA | 2016-10-18 | RCH | IER | KLIM |  | Pdt unconformity |  | 1991 | 10138 | Decolo | column installed with wrong orientation | SYSTEMS | I&R process | Site erection | Method / Méthode |  |  | 2016-09-05 | YES | RCH |  | 2017-01-18 | 2016-11-07 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 16040 KLIM | 16040 KLIM : column installed with wrong orientation
| 16041 | NVSA | 2016-10-19 | SZH | IER | Shuangqiao |  | Pdt unconformity |  | 2016 | 11478 | IEX | internals assembling of IEX column | SYSTEMS | I&R process |  | Method / Méthode |  |  | 2016-09-08 | YES | SZH |  | 2017-01-19 | 2016-11-07 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 16041 Shuangqiao | 16041 Shuangqiao : internals assembling of IEX column
CAP_EMISES 2016\16042 TANICHEM Gestion des arrets urgence.doc | 16042 | SMB | 2016-10-21 | SML | IER | Tanichem |  | Internal Anomaly |  | 1976 | 8531 | all | Non raccordement arrêts d'urgence | SYSTEMS | I&R process | AEI Design | Material / Matière |  |  |  | YES | SML |  | 2017-01-21 | 2017-01-19 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-03 |  | 16042 Tanichem | 16042 Tanichem : Non raccordement arrêts d'urgence
CAP_EMISES 2016\16043 TANICHEM Protection equipements electriques.doc | 16043 | SMB | 2016-10-21 | SML | IER | Tanichem |  | Internal Anomaly |  | 1976 | 8531 | all | Equipements automatisme détériorés | SYSTEMS | I&R process | AEI Design | Environment / Milieu |  |  |  | YES | SML |  | 2017-01-21 | 2017-01-19 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-03 |  | 16043 Tanichem | 16043 Tanichem : Equipements automatisme détériorés
CAP_EMISES 2016\16044TANICHEM Redondance PLC.doc | 16044 | SMB | 2016-10-21 | SML | IER | Tanichem |  | Internal Anomaly |  | 1976 | 8531 | all | Abscence de redondance automate | SYSTEMS | I&R process | AEI Design | Manpower / Main d'œuvre |  |  |  | NO |  |  | 2017-01-21 | 2016-12-13 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-03 |  | 16044 Tanichem | 16044 Tanichem : Abscence de redondance automate
Ouverture CAP 16042,043 | 16045 | SMB | 2016-10-21 | SML | IER | Tanichem |  | Internal Anomaly |  | 1976 | 8531 | all | Tps fermeture/ouverte vannes trop long | SYSTEMS | I&R process | AEI Design | Method / Méthode |  |  |  | NO |  |  | 2017-01-21 | 2016-12-13 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-03 |  | 16045 Tanichem | 16045 Tanichem : Tps fermeture/ouverte vannes trop long
CAP_EMISES 2016\16046TANICHEM Remplacement PT sur filtre charbon.doc | 16046 | SMB | 2016-10-25 | SML | IER | Tanichem | Endress Hauser | Internal Anomaly |  | 1976 | 8531 | filtre charbon | Remplacement PT sur filtre charbon | SYSTEMS | I&R process | AEI Design | Method / Méthode |  |  |  | NO |  |  | 2017-01-25 | 2017-01-19 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-03 |  | 16046 Tanichem | 16046 Tanichem : Remplacement PT sur filtre charbon
CAP_EMISES 2016\16047 Fufeng fuite vannes.doc | 16047 | SMB | 2016-10-25 | DBU | IER | FUFENG | Burkert | Supplier Dysfonctionning |  | 2007 | 11179 | MF | Leakage on control valves | SYSTEMS | I&R process | Meca design | Environment / Milieu |  |  |  | YES | DBU |  | 2017-01-25 | 2017-06-08 | NO |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-03 |  | 16047 FUFENG | 16047 FUFENG : Leakage on control valves
CAP_EMISES 2016\16048 Biospringer.doc | 16048 | SMB | 2016-10-26 | XDE | IER | Biospringer | SUDMO | Internal Anomaly |  | 2026 | 11244 | MF | Commande vannes norme DIN au lieu ISO | SYSTEMS | Purchase | Spec validation | Method / Méthode |  |  |  | NO |  |  | 2017-01-26 | 2017-01-03 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-10 |  | 16048 Biospringer | 16048 Biospringer : Commande vannes norme DIN au lieu ISO
CAP_EMISES 2016\16049 Ouest Import certificat alimentarité.doc | 16049 | SMB | 2016-10-26 | MGL | CS | OUEST IMPORT |  | Internal Anomaly |  | 1885/1886 | 7709/7839 | Decolo | Alimentarité matériaux colonnes de décolo | Cust. Sce | After sales process | Purchase | Method / Méthode |  |  |  | YES | EWI |  | 2017-01-26 | 2017-01-23 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-03 |  | 16049 OUEST IMPORT | 16049 OUEST IMPORT : Alimentarité matériaux colonnes de décolo
CAP_EMISES 2016\16050 Cévital.doc | 16050 | SMB | 2016-11-14 | PGA | IER | Cevital | SPA | Claim | YES | 1952 | 8259 | Decolo | Leakage of resins | SYSTEMS | I&R process | Commissioning | Material / Matière |  |  |  | YES | SMR |  | 2017-02-14 | 2017-04-07 | NO |  | 2016-11-09 | 2017-03-31 | 2017-04-07 | NO |  |  | 0 | YES | 2017-10-10 |  | 16050 Cevital | 16050 Cevital : Leakage of resins
R:\QA-NVA IB\CAP\16051 Fufeng floor fall down issue.doc | 16051 | NVSA | 2016-11-15 | WWE | IER | FUFENG |  | Claim |  | 1988 | 10132 | SSMB | Floor fall down | SYSTEMS | After sales process |  | Material / Matière |  |  |  | YES | WWE |  | 2017-02-15 | 2017-10-10 | NO |  | 2016-11-07 | 2017-06-01 | 2017-10-10 | NO |  |  | 0 |  |  |  | 16051 FUFENG | 16051 FUFENG : Floor fall down
R:\QA-NVA IB\CAP\16052 Plasticon FRP pipe chamfer issue.doc | 16052 | NVSA | 2016-11-16 | WWE | IER | FUFENG | Plasticon | Supplier Dysfonctionning |  | 2025/2027 | 11291/11432 | SSMB | FRP piping chamfer | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | WWE |  | 2017-02-16 | 2017-01-25 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 16052 FUFENG | 16052 FUFENG : FRP piping chamfer
CAP_EMISES 2016\16053 Yi'an Tagging.doc | 16053 | SMB | 2016-11-17 | CPV | STP | Yi'an |  | Internal Anomaly |  | 2033 | 12449 | Decolo | Error PID Tags | SYSTEMS | I&R process | Process design | Method / Méthode |  |  |  | NO |  |  | 2017-02-17 | 2017-02-07 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-11-20 |  | 16053 Yi'an | 16053 Yi'an : Error PID Tags
R:\QA-NVA IB\CAP\16054 Fufeng resin leakage issue.doc | 16054 | NVSA | 2016-12-02 | EGU | IER | Fufeng |  | Claim |  | 2025 | 11291 | SSMB | resin leakage issue | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | EGU |  | 2017-03-02 | 2017-02-20 | YES |  | 2016-12-01 | 2017-03-02 | 2017-02-20 | YES |  |  | 0 |  |  |  | 16054 Fufeng | 16054 Fufeng : resin leakage issue
CAP_EMISES 2016\16055 Al Nouran Fûts Resine Manquants.doc | 16055 | SMB | 2016-12-05 | XRO | IER | Al Nouran | Bollore | Supplier Dysfonctionning |  | 2002 | 10510 | Decolo | Fûts résine manquants | SYSTEMS | Purchase | Logistic | Material / Matière |  |  |  | YES | JNJ |  | 2017-03-05 | 2017-02-22 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-10 |  | 16055 Al Nouran | 16055 Al Nouran : Fûts résine manquants
R:\QA-NVA IB\CAP\16056 Agrana piping re-assembly issue on site.doc | 16056 | NVSA | 2016-12-07 | SLI | IER | AGRANA | Ziyou | Supplier Dysfonctionning |  | 2014 | 10416 | all | piping re-assembly issue on site | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | WWE |  | 2017-03-07 | 2017-01-25 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 16056 AGRANA | 16056 AGRANA : piping re-assembly issue on site
CAP_EMISES 2016\16057 pilote SSMB ADM.doc | 16057 | SMB | 2016-12-13 | ADP | R&D | ADM |  | Internal Anomaly |  |  | AJO-0310 | SSMB | SSMB Pilot design | R&D | PPD Process | Pilot design | Method / Méthode |  |  |  | YES | ABS |  | 2017-03-13 | 2017-03-10 | YES |  |  |  |  | N/A |  |  | 0 | YES | 2017-10-11 |  | 16057 ADM | 16057 ADM : SSMB Pilot design
R:\QA-NVA IB\CAP\16058 Shuangqiao wrong pressure calculation issue.doc | 16058 | NVSA | 2016-12-14 | JHU | IER | ShuangQiao |  | Pdt unconformity |  | 1944/1946 | 8410/9122 | IEX | wrong pressure calculation issue | SYSTEMS | I&R process |  | Method / Méthode |  |  |  | YES | JHU |  | 2017-03-14 | 2017-03-13 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 16058 ShuangQiao | 16058 ShuangQiao : wrong pressure calculation issue
CAP_EMISES 2016\16059 Tereos Nesle.doc | 16059 | SMB | 2016-12-19 | PBO | CS | TEREOS NESLE | GE | Claim |  |  | CV-1602-0049 | NF | High DP2 rate at start-up of NF unit | Cust. Sce | After sales process | Purchase | Material / Matière |  | GE |  | YES | EWI |  | 2017-03-19 | 2017-07-25 | NO |  | 2017-01-06 | [5 empty] | 0 |  | A faire 01/18 |  | 16059 TEREOS NESLE | 16059 TEREOS NESLE : High DP2 rate at start-up of NF unit
#REF! | 17001 | SMB | 2017-01-05 | NPA | IER | Yi'an |  | Internal Anomaly |  | 2033 | 12449 | Decolo | Delay delivery resins | SYSTEMS | After sales process | Logistic | Method / Méthode |  |  |  | YES | EWI | 2017-02-02 | 2017-04-05 | 2017-03-28 | YES |  |  |  |  | N/A | 830 | 0 | 830 | YES | 2017-10-03 |  | 17001 Yi'an | 17001 Yi'an : Delay delivery resins
#REF! | 17002 | SMB | 2017-01-10 | NPA | IER | SBC |  | Internal Anomaly |  | 2008 | 11482 | UF | Error reference Kerasep membranes | SYSTEMS | I&R process | process design | Method / Méthode |  |  |  | YES | NPA | 2017-01-16 | 2017-04-10 | 2017-03-24 | YES |  |  |  |  | N/A | 830 | 0 | 830 | YES | 2017-11-20 |  | 17002 SBC | 17002 SBC : Error reference Kerasep membranes
#REF! | 17003 | SMB | 2017-01-25 | SMR | IER | TAT Omnia |  | Claim |  | 2018 | 11600 | Decolo | cation working, bad smell syrup, quality final product | SYSTEMS | I&R process | commissioning | Method / Méthode |  |  |  | YES | SMR | 2017-01-30 | 2017-04-25 | 2017-12-14 | NO |  | 2017-02-02 | 2017-08-01 | 2017-12-14 | NO | 3467 | 1280 | 4747 | YES | 2018-11-08 |  | 17003 TAT Omnia | 17003 TAT Omnia : cation working, bad smell syrup, quality final product
#REF! | 17004 | SMB | 2017-01-31 | RBA | IER | Yi'an | Bossard | Supplier Dysfonctionning |  | 2033 | 12449 | Decolo | PLC cards undersized | SYSTEMS | I&R process | AEI Design | Material / Matière |  |  |  | NO |  | 2017-01-31 | 2017-04-30 | 2017-04-12 | YES |  |  |  |  | N/A | 394 | 702 | 1096 | YES | 2017-10-10 |  | 17004 Yi'an | 17004 Yi'an : PLC cards undersized
#REF! | 17005 | SMB | 2017-02-01 | DBU | IER | Cargill |  | Internal Anomaly | PID | 2031 | 10376 | IEX | Error functionnal analysis (PR60) | SYSTEMS | I&R process | process design | Manpower / Main d'œuvre |  |  |  | YES | CHP/RMU | 2017-02-09 | 2017-05-01 | 2017-04-10 | YES |  |  |  |  | N/A | 830 | 0 | 830 | YES | 2017-11-20 |  | 17005 Cargill | 17005 Cargill : Error functionnal analysis (PR60)
#REF! | 17006 | SMB | 2017-02-08 | ECR | IER | Agrana | Althammer | Supplier Dysfonctionning |  | 2014 | 10416 | IEX | Error nozzle diameter soft water tank | SYSTEMS | I&R process | commissioning | Material / Matière |  |  |  | NO |  | 2017-02-08 | 2017-05-08 | 2017-03-24 | YES |  |  |  |  | N/A | 664 | 0 | 664 |  | A faire 12/19 | en fin de projet | 17006 Agrana | 17006 Agrana : Error nozzle diameter soft water tank
#REF! | 17007 | SMB | 2017-02-08 | ECR | IER | Agrana | Gree | Supplier Dysfonctionning |  | 2014 | 10416 | IEX | C615 ID plate support damaged | SYSTEMS | I&R process | Asia purchase | Material / Matière |  |  |  | YES | FBA | 2017-02-24 | 2017-05-08 | 2018-10-31 | NO |  |  |  |  | N/A | 0 | 0 | 0 |  | NA |  | 17007 Agrana | 17007 Agrana : C615 ID plate support damaged
#REF! | 17008 | SMB | 2017-02-08 | ECR | IER | Agrana | Gree | Supplier Dysfonctionning |  | 2014 | 10416 | IEX | C625 ID plate support damaged | SYSTEMS | I&R process | Asia purchase | Material / Matière |  |  |  | YES | FBA | 2017-02-24 | 2017-05-08 | 2018-10-31 | NO |  |  |  |  | N/A | 0 | 0 | 0 |  | NA |  | 17008 Agrana | 17008 Agrana : C625 ID plate support damaged
#REF! | 17009 | SMB | 2017-02-08 | ECR | IER | Agrana | Gree | Supplier Dysfonctionning |  | 2014 | 10416 | IEX | C635 ID plate support damaged | SYSTEMS | I&R process | Asia purchase | Material / Matière |  |  |  | YES | FBA | 2017-02-24 | 2017-05-08 | 2018-10-31 | NO |  |  |  |  | N/A | 0 | 0 | 0 |  | NA |  | 17009 Agrana | 17009 Agrana : C635 ID plate support damaged
#REF! | 17010 | SMB | 2017-02-08 | ECR | IER | Agrana | Gree | Supplier Dysfonctionning |  | 2014 | 10416 | IEX | cationic/anionic columns showing coating damages | SYSTEMS | I&R process | Asia purchase | Material / Matière |  |  |  | YES | ABN | 2017-02-24 | 2017-05-08 | 2019-05-21 | NO |  |  |  |  | N/A | 276 | 4063.3 | 4339.3 |  | A faire 12/19 | en fin de projet | 17010 Agrana | 17010 Agrana : cationic/anionic columns showing coating damages
#REF! | 17011 | SMB | 2017-02-08 | ECR | IER | Agrana | Plasticon | Supplier Dysfonctionning |  | 2014 | 10416 | IEX | internal diameter PP piping too small | SYSTEMS | I&R process | Asia purchase | Material / Matière |  |  |  | YES | ABN | 2017-02-24 | 2017-05-08 | 2017-05-02 | YES |  |  |  |  | N/A | 3320 | 0 | 3320 |  | A faire 12/19 | en fin de projet | 17011 Agrana | 17011 Agrana : internal diameter PP piping too small
#REF! | 17012 | SMB | 2017-02-08 | ECR | IER | Agrana | Ziyou | Supplier Dysfonctionning |  | 2014 | 10416 | IEX | missing studs on all flanges of vessels | SYSTEMS | I&R process | Asia purchase | Material / Matière |  |  |  | YES | ABN/ACR | 2017-03-06 | 2017-05-08 | 2017-04-19 | YES |  |  |  |  | N/A | 6640 | 130 | 6770 |  | A faire 12/19 | en fin de projet | 17012 Agrana | 17012 Agrana : missing studs on all flanges of vessels
#REF! | 17013 | NVSA | 2017-03-06 | WWE | IER | Agrana | KCH | Supplier Dysfonctionning |  | 2014 | 10416 | IEX | painting colour for IEX columns of Phase I is wrong | SYSTEMS | I&R process |  | Manpower / Main d'œuvre |  | KCH |  | YES | WWE | 2017-03-08 | 2017-06-06 | 2017-05-31 | YES |  |  |  |  | N/A | 123.6958 | 0 | 123.6958 |  |  |  | 17013 Agrana | 17013 Agrana : painting colour for IEX columns of Phase I is wrong
#REF! | 17014 | SMB | 2017-03-06 | PBO | CS | Agrana |  | Claim |  |  | CV-1611-0025 | MF | outside kerasep membrane storage | Cust. Sce | After sales process | Logistic | Method / Méthode |  |  |  | YES | PBO | 2017-03-09 | 2017-06-06 | 2017-06-02 | YES |  | 2017-02-28 |  |  |  | 4623 | 27804 | 32427 | YES | 2017-10-03 |  | 17014 Agrana | 17014 Agrana : outside kerasep membrane storage
#REF! | 17015 | SMB | 2017-03-13 | EWI | CS | Beneo Orafti | DOW | Supplier Dysfonctionning |  |  | CV-1612-0038 | IEX | resin delivery delay | Cust. Sce | After sales process | resin purchase | Material / Matière |  | DOW |  | NO |  |  | 2017-06-13 | 2017-05-12 | YES |  |  |  |  | N/A | 166 | 0 | 166 | NO | 2017-11-02 | CAP17054 | 17015 Beneo Orafti | 17015 Beneo Orafti : resin delivery delay
#REF! | 17016 | SMB | 2017-03-17 | RWA | IER | Mérial | Valorel | Claim |  | 2010 | 11326 | UF | trace of rust on UF52 module | SYSTEMS | I&R process | commissioning | Material / Matière |  | Valorel |  | YES | JGO | 2017-03-22 | 2017-06-17 | 2017-06-08 | YES |  | 2017-03-28 | 2017-06-01 | 2017-06-08 | NO | 4980 | 2274 | 7254 | YES | 2017-10-20 |  | 17016 Mérial | 17016 Mérial : trace of rust on UF52 module
#REF! | 17017 | SMB | 2017-03-23 | XDE | IER | TAT |  | Supplier Dysfonctionning |  | 2021 | 10617 | SSMB | conical filter on piping deformed | SYSTEMS | I&R process | commissioning | Material / Matière |  |  |  | YES | SOV | 2017-04-12 | 2017-06-23 | 2017-06-07 | YES |  |  |  |  | N/A | 6276 | 2617.08 | 8893.08 | YES | 2017-10-10 |  | 17017 TAT | 17017 TAT : conical filter on piping deformed
#REF! | 17018 | SMB | 2017-03-23 | EWI | CS | VITALUS | Purolite | Supplier Dysfonctionning |  | 2024 | 10065 | IEX | resin doesn't in accordance with FDA requirements | Cust. Sce | After sales process | resin purchase | Material / Matière |  | Purolite |  | NO |  |  | 2017-06-23 | 2017-07-24 | NO |  |  |  |  | N/A | 13015 | 2000 | 15015 | NO | 2017-11-06 | CAP 17055 | 17018 VITALUS | 17018 VITALUS : resin doesn't in accordance with FDA requirements
#REF! | 17019 | SMB | 2017-03-28 | JMR | Achat | CLS | Alfa Laval | Supplier Dysfonctionning |  | 2013 | 11461 | Evapo | Project management, quality equipment | SYSTEMS | I&R process | site mounting | Material / Matière |  | Alfa laval |  | YES | JMR | 2017-04-12 | 2017-06-28 | 2017-06-27 | YES |  |  |  |  | N/A | 7055 | 0 | 7055 | YES | 2019-11-04 |  | 17019 CLS | 17019 CLS : Project management, quality equipment
#REF! | 17020 | NVSA | 2017-04-01 | SXI | IER | Wuhan Friendship |  | Claim |  | CJ1324 | 10095 | SSMB | The gravel purchased by client himself was not qualified | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | SXI | 2017-04-05 | 2017-07-01 | 2017-05-16 | YES |  | 2017-04-05 | 2017-07-01 | 2017-05-16 | YES | 0 | 0 | 0 |  |  |  | 17020 Wuhan Friendship | 17020 Wuhan Friendship : The gravel purchased by client himself was not qualified
#REF! | 17021 | SMB | 2017-04-05 | SML | IER | Tanichem | Endress hauser | Internal Anomaly |  | 1976 | 8531 | IEX | Flowmeter technology no adapted | SYSTEMS | I&R process | Process design | Manpower / Main d'œuvre |  |  |  | NO |  |  | 2017-07-05 | 2017-06-07 | YES |  |  |  |  | N/A | 332 | 2886 | 3218 | YES | 2018-11-07 | en fin de projet | 17021 Tanichem | 17021 Tanichem : Flowmeter technology no adapted
#REF! | 17022 | SMB | 2017-04-14 | XDE | IER | Biospringer | Ziyou | Claim |  | 2026 | 11244 | MF | piping pb, mounting impossibility | SYSTEMS | I&R process | site mounting | Material / Matière |  |  |  | YES | SMR | 2017-04-19 | 2017-07-14 | 2017-06-15 | YES |  | 2017-04-18 | 2017-07-01 | 2017-06-15 | YES | 19805 | 43730 | 63535 | YES | 2018-11-08 |  | 17022 Biospringer | 17022 Biospringer : piping pb, mounting impossibility
#REF! | 17023 | SMB | 2017-04-20 | DBA | CS | Armor Protéine | CTI-ACDN | Claim |  | 1925 | 7985 | SSMB | leakage welding SSMB cells | Cust. Sce | After sales process | Purchase | Material / Matière |  | CTI |  | YES | EWI/SMR | 2017-04-19 | 2017-07-20 | 2017-12-22 | NO |  | 2017-04-18 |  |  |  | 40915 | 91798 | 132713 | YES | 2018-11-09 |  | 17023 Armor Protéine | 17023 Armor Protéine : leakage welding SSMB cells
#REF! | 17024 | SMB | 2017-04-21 | FCA | IER | MEFSCO | SPA | Internal Anomaly |  | 1974 | 9876 | IEX | defect of piping assembly | SYSTEMS | I&R process | site mounting | Material / Matière |  |  |  | NO |  |  | 2017-07-21 | 2017-07-07 | YES |  |  |  |  | N/A | 2905 | 0 | 2905 | YES | 2018-11-07 |  | 17024 MEFSCO | 17024 MEFSCO : defect of piping assembly
#REF! | 17025 | SMB | 2017-05-02 | EWI | CS | Tetra Pak |  | Claim |  |  | CV-1609-0011 | UF | convex tightening plate of K99 modules | Cust. Sce | After sales process | Supply Chain PMP | Method / Méthode |  |  |  | YES | EWI | 2017-05-04 | 2017-08-02 | 2017-07-24 | YES |  | 2017-05-02 |  |  |  | 5950 | 4100 | 10050 | YES | 2018-11-09 |  | 17025 Tetra Pak | 17025 Tetra Pak : convex tightening plate of K99 modules
#REF! | 17026 | SMB | 2017-05-10 | MGL | IER | Sunoko | Gree | Supplier Dysfonctionning |  | 1953 | 9263 | SSMB | resin leakage on network plates | SYSTEMS | I&R process | commissioning | Material / Matière |  |  |  | NO |  |  | 2017-08-10 | 2017-07-11 | YES |  |  |  |  | N/A | 9350 | 3700 | 13050 |  | A faire 07/18 | reporté à l'issue du litige | 17026 Sunoko | 17026 Sunoko : resin leakage on network plates
#REF! | 17027 | SMB | 2017-05-22 | XRO | IER | ADM US |  | Internal Anomaly |  | 2022 | 11279 | SSMB | TU01 error : reversed Extract/Raffinate collectors | SYSTEMS | I&R process | Meca Design | Manpower / Main d'œuvre |  |  |  | YES | SOV | 2017-06-08 | 2017-08-22 | 2017-07-13 | YES |  |  |  |  | N/A | 1530 | 0 | 1530 | YES | 2018-11-07 |  | 17027 ADM US | 17027 ADM US : TU01 error : reversed Extract/Raffinate collectors
#REF! | 17028 | SMB | 2017-05-22 | XRO | IER | MEFSCO |  | Claim | PID | 1974 | 9876 | IEX | piping material error (CS instead of SS) | SYSTEMS | I&R process | Meca Design | Manpower / Main d'œuvre |  |  |  | YES | XRO | 2017-06-01 | 2017-08-22 | 2018-01-18 | NO |  | 2017-04-06 | 2018-01-31 | 2018-01-18 | YES | 850 | 0 | 850 | YES | 2018-11-07 |  | 17028 MEFSCO | 17028 MEFSCO : piping material error (CS instead of SS)
#REF! | 17029 | SMB | 2017-05-22 | GTI | R&D | ERAMET |  | Safety |  | EN3068 |  |  | acid solution projection | R&D | PPD Process |  | Manpower / Main d'œuvre |  |  |  | YES | CPT | 2017-05-22 | 2017-08-22 | 2018-01-19 | NO |  |  |  |  | N/A | 340 | 0 | 340 | YES | 2018-11-07 |  | 17029 ERAMET | 17029 ERAMET : acid solution projection
#REF! | 17030 | SMB | 2017-05-31 | ACR | IER | Agrana | Gree | Internal Anomaly |  | 2014 | 10416 | IEX | collision betweenplatform & manholes of columns | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | SOV | 2017-06-15 | 2017-08-31 | 2017-07-21 | YES |  |  |  |  | N/A | 340 | 0 | 340 | YES | 2018-11-07 |  | 17030 Agrana | 17030 Agrana : collision betweenplatform & manholes of columns
#REF! | 17031 | SMB | 2017-06-19 | CPV | STP | Tanichem |  | Internal Anomaly |  | 1976 | 8531 | all | Mismanagement of AF updates during commissioning | SYSTEMS | I&R process | commissioning | Method / Méthode |  |  |  | YES | CPV | 2017-06-28 | 2017-09-19 | 2018-07-23 | NO |  |  |  |  | N/A | 4083 | 0 | 4083 |  | A faire 01/19 | reporté à la clôture projet | 17031 Tanichem | 17031 Tanichem : Mismanagement of AF updates during commissioning
#REF! | 17032 | SMB | 2017-06-19 | JPL | IER | AGRANA |  | Internal Anomaly |  | 2014 | 10416 | all | Valve wiring problem with 2 limit switches | SYSTEMS | I&R process | AEI Design | Manpower / Main d'œuvre |  |  |  | YES | JPL | 2017-06-22 | 2017-09-19 | 2017-08-30 | YES |  |  |  |  | N/A | 340 | 1000 | 1340 |  | A faire 12/19 | en fin de projet | 17032 AGRANA | 17032 AGRANA : Valve wiring problem with 2 limit switches
#REF! | 17033 | NVSA | 2017-06-27 | VXI | IER | FUFENG |  | Claim |  | 2007 | 11179 | MF | MF membranes abrasion | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | VXI | 2017-06-28 | 2017-09-27 | 2019-12-19 | NO |  | 2017-06-28 | 2018-01-31 | 2019-12-19 | NO | 2626 | 192923 | 195549 |  |  |  | 17033 FUFENG | 17033 FUFENG : MF membranes abrasion
#REF! | 17034 | NVSA | 2017-07-05 | SXI | IER | RZBC | COMPOSITES VEC | Supplier Dysfonctionning |  | 2015 | 11722 | IEX | Nozzles are not qualified | SYSTEMS | I&R process | site mounting | Material / Matière |  |  |  | YES | SXI | 2017-07-05 | 2017-10-05 | 2017-09-14 | YES |  |  |  |  | N/A | 1014.4263 | 457.2235 | 1471.6498 |  |  |  | 17034 RZBC | 17034 RZBC : Nozzles are not qualified
#REF! | 17035 | SMB | 2017-07-07 | RBA | IER | MEFSCO | SABE | Supplier Dysfonctionning |  | 1974 | 9876 | IEX | Supplier's error on the electrical characteristics of the motors | SYSTEMS | I&R process | AEI Design | Material / Matière |  | Sabe |  | YES | JNJ | 2017-07-19 | 2017-10-07 | 2017-09-18 | YES |  |  |  |  | N/A | 1020 | 0 | 1020 | YES | 2018-11-07 |  | 17035 MEFSCO | 17035 MEFSCO : Supplier's error on the electrical characteristics of the motors
#REF! | 17036 | SMB | 2017-07-07 | RBA | IER | ADM Turquie |  | Internal Anomaly |  | 2039 | 11996 | SSMB | AEI budget underestimated | SYSTEMS | System order acquisition | Offer quotation | Manpower / Main d'œuvre |  |  |  | YES | SPB | 2017-07-19 | 2017-10-07 | 2017-09-27 | YES |  |  |  |  | N/A | 765 | 0 | 765 | YES | 2018-11-07 |  | 17036 ADM Turquie | 17036 ADM Turquie : AEI budget underestimated
#REF! | 17037 | SMB | 2017-07-07 | SML | IER | KLIM Cambodge |  | Internal Anomaly |  | 1991 | 10138 | all | Chinese translation of supervision views | SYSTEMS | I&R process | AEI Design | Material / Matière |  |  |  | YES | SML | 2017-07-07 | 2017-10-07 | 2017-09-18 | YES |  |  |  |  | N/A | 1485.7692 | 5005.1282 | 6490.8974 | YES | 2018-11-07 |  | 17037 KLIM Cambodge | 17037 KLIM Cambodge : Chinese translation of supervision views
#REF! | 17038 | SMB | 2017-07-17 | ACR | IER | Boccard/Nutribio | Méga | Claim |  | 2011 | 10282 | ED | Dysfonction ED unit | SYSTEMS | I&R process | commissioning | Material / Matière |  |  |  | YES | ACR/SMR | 2017-07-20 | 2017-10-17 | 2017-09-27 | YES |  | 2017-07-20 | 2017-10-31 | 2017-09-27 | YES | 3825 | 337 | 4162 | YES | 2018-11-08 |  | 17038 Boccard/Nutribio | 17038 Boccard/Nutribio : Dysfonction ED unit
#REF! | 17039 | SMB | 2017-07-17 | SGU | CS | Tetra Pak/ Glycom | CTI | Claim |  |  | CV-1609-0011 | UF | Breakage of BE Kerasep membranes | Cust. Sce | After sales process | Purchase | Material / Matière |  |  |  | YES | EWI/PBO | 2017-07-17 | 2017-10-17 | 2019-04-09 | NO |  | 2017-07-18 | 2017-10-31 | 2019-04-09 | NO | 13205 | 16350 | 29555 | YES | 2019-11-05 |  | 17039 Tetra Pak/ Glycom | 17039 Tetra Pak/ Glycom : Breakage of BE Kerasep membranes
#REF! | 17040 | NVSA | 2017-08-04 | SXI | IER | SBC | ZIYOU | Supplier Dysfonctionning |  | 2008 | 11482 | all | goods packing issue | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | SXI | 2017-07-31 | 2017-11-04 | 2017-11-01 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 17040 SBC | 17040 SBC : goods packing issue
#REF! | 17041 | NVSA | 2017-08-10 | WWE | IER | HUATANG | ZIYOU | Supplier Dysfonctionning |  | 1996 | 8759 | Decolo/MF | piping issue | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | WWE | 2017-08-10 | 2017-11-10 | 2017-11-08 | YES |  |  |  |  | N/A | 328.2051 | 33.3333 | 361.5385 |  |  |  | 17041 HUATANG | 17041 HUATANG : piping issue
#REF! | 17042 | NVSA | 2017-08-10 | WWE | IER | HUATANG | ZIYOU | Supplier Dysfonctionning |  | 1996 | 8759 | Decolo/MF | IEX position and backwashing nozzle issues | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | WWE | 2017-08-10 | 2017-11-10 | 2017-11-08 | YES |  |  |  |  | N/A | 492.3077 | 0 | 492.3077 |  |  |  | 17042 HUATANG | 17042 HUATANG : IEX position and backwashing nozzle issues
#REF! | 17043 | NVSA | 2017-08-15 | EGU | IER | HUATANG | JINLONG | Pdt unconformity |  | 1996 | 8759 | Decolo/MF | MB manhole height issue | SYSTEMS | I&R process |  | Manpower / Main d'œuvre |  |  |  | YES | EGU | 2017-08-15 | 2017-11-15 | 2017-11-08 | YES |  |  |  |  | N/A | 1148.7179 | 986.1538 | 2134.8718 |  |  |  | 17043 HUATANG | 17043 HUATANG : MB manhole height issue
#REF! | 17044 | SMB | 2017-08-29 | MGL | CS | ARIAS | CTI | Claim |  |  | CV-1507-0069 | UF | proteins loss higher than our guarantees | Cust. Sce | After sales process | Purchase | Material / Matière |  |  |  | YES | MGL | 2017-09-04 | 2017-11-29 | 2018-02-13 | NO |  | 2017-06-02 | 2017-11-30 | 2018-02-13 | NO | 10642 | 2600 | 13242 | YES | 2018-11-07 |  | 17044 ARIAS | 17044 ARIAS : proteins loss higher than our guarantees
#REF! | 17045 | SMB | 2017-09-06 | CPT | STP | AGRANA |  | Safety |  | 2014 | 10416 | NA | discomfort on customer site | STP | I&R process |  | Manpower / Main d'œuvre |  |  |  | YES | CHP | 2017-10-18 | 2017-12-06 | 2019-07-25 | NO |  |  |  |  | N/A | 595 | 0 | 595 | NA | NA |  | 17045 AGRANA | 17045 AGRANA : discomfort on customer site
#REF! | 17046 | SMB | 2017-09-07 | SMR | IER | Biospringer | CTI | Claim |  | 2026 | 11244 | MF | Breakage of Kerasep membranes | SYSTEMS | I&R process | commissioning | Material / Matière |  | CTI |  | YES | EWI | 2017-09-11 | 2017-12-07 | 2017-12-22 | NO |  | 2017-09-11 | 2017-12-31 | 2017-12-22 | YES | 21590 | 96313 | 117903 | NO | 2018-03-05 | CAP 18008 | 17046 Biospringer | 17046 Biospringer : Breakage of Kerasep membranes
#REF! | 17047 | SMB | 2017-09-07 | SMR | IER | Biospringer |  | Internal Anomaly |  | 2026 | 11244 | MF | CIP Filter damaged by tartar | SYSTEMS | I&R process | commissioning | Environment / Milieu |  |  |  | NO |  |  | 2017-12-07 | 2017-11-17 | YES |  |  |  |  | N/A | 850 | 585 | 1435 | YES | 2018-11-08 |  | 17047 Biospringer | 17047 Biospringer : CIP Filter damaged by tartar
#REF! | 17048 | NVSA | 2017-09-05 | JZH | IER | YIXING | NOVASEP SMB | Pdt unconformity |  | CJ1077 | 7838 | SSMB | strainer material is wrong | SYSTEMS | After sales process |  | Material / Matière |  |  |  | YES | JZH | 2017-09-05 | 2017-12-05 | 2018-02-09 | NO |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 17048 YIXING | 17048 YIXING : strainer material is wrong
#REF! | 17049 | NVSA | 2017-09-14 | SXI | IER | RZBC2 | SPIE | Supplier Dysfonctionning |  | 2015 | 11722 | IEX | The program is not completed | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | SML | 2017-09-14 | 2017-12-14 | 2017-11-17 | YES |  |  |  |  | N/A | 1641.0256 | 512.8205 | 2153.8462 |  |  |  | 17049 RZBC2 | 17049 RZBC2 : The program is not completed
#REF! | 17050 | SMB | 2017-10-02 | DBU | IER | Cargill Manchester | Bollore | Internal Anomaly |  | 2032 | 12519 | IEX | Management of gravel supply | SYSTEMS | I&R process | Logistic | Method / Méthode |  |  |  | NO |  |  | 2018-01-02 | 2017-12-14 | YES |  |  |  |  | N/A | 255 | 0 | 255 | NO | 2019-03-06 | CAP19015 | 17050 Cargill Manchester | 17050 Cargill Manchester : Management of gravel supply
#REF! | 17051 | NVSA | 2017-10-09 | JLI | IER | Fufeng |  | Safety |  | 2027 | 11432 | SSMB | Hose broken, Jeff burn by hot water and resin | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | JLI | 2017-10-15 | 2018-01-09 | 2018-01-18 | NO |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 17051 Fufeng | 17051 Fufeng : Hose broken, Jeff burn by hot water and resin
#REF! | 17052 | NVSA | 2017-10-19 | WWE | IER | YINMORE | Heibei KNT FRP | Pdt unconformity |  | 2029 | 9801 | Decolo/MF | The nozzle plate was not oriented at the right angle | SYSTEMS | I&R process |  | Method / Méthode |  |  |  | YES | WWE | 2017-11-17 | 2018-01-19 | 2018-01-05 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 17052 YINMORE | 17052 YINMORE : The nozzle plate was not oriented at the right angle
#REF! | 17053 | NVSA | 2017-10-31 | JHU | IER | FUFENG | HAIYI | Pdt unconformity |  | 2046 | 13011 | MF & SSMB | The name plate of HE is wrong | SYSTEMS | I&R process |  | Manpower / Main d'œuvre |  |  |  | YES | JHU | 2017-11-15 | 2018-01-31 | 2017-11-30 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 17053 FUFENG | 17053 FUFENG : The name plate of HE is wrong
#REF! | 17054 | SMB | 2017-11-02 | EWI | CS | TAT Nisasta | DOW-Bolloré | Supplier Dysfonctionning | YES | 2044 | 13042 | SSMB | resin delivery delay | Cust. Sce | After sales process | resin purchase | Material / Matière |  | DOW, Bolloré |  | NO |  |  | 2018-02-02 | 2018-04-24 | NO |  |  |  |  | N/A | 7712 | 7014 | 14726 | YES | 2018-11-09 |  | 17054 TAT Nisasta | 17054 TAT Nisasta : resin delivery delay
#REF! | 17055 | SMB | 2017-11-06 | MED | R&D | VITALUS | DOW | Supplier Dysfonctionning | YES | 2024 | 10065 | SSMB | resin doesn't in accordance with FDA requirements | Cust. Sce | After sales process | resin purchase | Material / Matière |  | DOW |  | NO |  |  | 2018-02-06 | 2018-03-26 | NO |  |  |  |  | N/A | 28634 | 29419 | 58053 | YES | 2018-11-07 |  | 17055 VITALUS | 17055 VITALUS : resin doesn't in accordance with FDA requirements
#REF! | 17056 | NVSA | 2017-11-30 | EGU | IER | FUFENG | BRAY | Claim |  | 2025 | 11291 | SSMB | Valve malfunction and recovery rate low | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | VXI | 2017-11-15 | 2018-02-28 | 2018-02-02 | YES |  | 2017-11-07 | 2018-02-28 | 2018-02-02 | YES | 1230.7692 | 769.2308 | 2000 |  |  |  | 17056 FUFENG | 17056 FUFENG : Valve malfunction and recovery rate low
#REF! | 17057 | SMB | 2017-12-01 | DBR | IER | NA | Novatrade | Internal Anomaly |  | NA | NA | NA | Difficulty in making the down payment | SYSTEMS | Purchase |  | Method / Méthode |  |  |  | YES | JMR | 2017-12-14 | 2018-03-01 | 2018-02-26 | YES |  |  |  |  | N/A | 431 | 0 | 431 | YES | 2019-11-04 |  | 17057 NA | 17057 NA : Difficulty in making the down payment
CAP_EMISES 2018\18001 Tereos Nesle.docm | 18001 | SMB | 2018-01-12 | PBO | CS | TEREOS NESLE | GE | Claim |  |  | CV-1611-0050 | NF | breaking gaskets NF membrane | Cust. Sce | After sales process | Purchase | Material / Matière |  | GE |  | YES | PBO | 2017-01-16 | 2018-04-12 | 2018-03-13 | YES |  | 2018-01-12 | 2018-04-30 | 2018-03-13 | YES | 572 | 0 | 572 | YES | 2018-11-07 |  | 18001 TEREOS NESLE | 18001 TEREOS NESLE : breaking gaskets NF membrane
CAP_EMISES 2018\18002 Mefsco - reges cation & anion.docm | 18002 | SMB | 2018-01-19 | FCA | IER | MEFSCO |  | Internal Anomaly | PID | 1974 | 9876 | IEX | Hydraulic issues during cation/anion regeneration | SYSTEMS | I&R process | commissioning | Method / Méthode |  |  |  | YES | SPB/SOV | 2017-01-31 | 2018-04-19 | 2018-04-06 | YES |  |  |  |  | N/A | 17600 | 0 | 17600 | YES | 2018-11-07 |  | 18002 MEFSCO | 18002 MEFSCO : Hydraulic issues during cation/anion regeneration
CAP_EMISES 2018\18003 Hilmar Cheese.docm | 18003 | SMB | 2018-01-29 | EWI | CS | Hilmar Cheese | Andritz | Internal Anomaly |  |  | CV-1708-0057 |  | Supplier purchase order oversight | Cust. Sce | After sales process | Purchase | Manpower / Main d'œuvre |  |  |  | YES | EWI | 2017-02-07 | 2018-04-29 | 2018-03-16 | YES |  |  |  |  | N/A | 632 | 0 | 632 | YES | 2018-11-09 |  | 18003 Hilmar Cheese | 18003 Hilmar Cheese : Supplier purchase order oversight
R:\QA-NVA IB\CAP\18004 Canlac abbott base issue.docm | 18004 | NVSA | 2018-02-02 | WWE | IER | Canlac Abbott | JINLONG | Prevent / improve |  | 2034 | 11864 | SSMB | The anchoring bolts too close to insulation hinder couter drilling on concrete | SYSTEMS | I&R process | Meca design | Manpower / Main d'œuvre |  |  |  | YES | WWE | 2017-09-16 | 2018-05-02 | 2018-03-16 | YES |  |  |  |  | N/A | 2424 | 9814 | 12238 |  |  |  | 18004 Canlac Abbott | 18004 Canlac Abbott : The anchoring bolts too close to insulation hinder couter drilling on concrete
R:\QA-NVA IB\CAP\18005 Cargill IEX top manhole FEA issue.docm | 18005 | NVSA | 2018-02-02 | WWE | IER | Cargill | GREETH | Pdt unconformity |  | 2032 | 12519 | Anionic column | The top manhole on anionic IEX column FEA calculation can't pass | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | NO |  |  | 2018-05-02 | 2018-03-16 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 18005 Cargill | 18005 Cargill : The top manhole on anionic IEX column FEA calculation can't pass
CAP_EMISES 2018\18006 surpresseur-refroisseur Atlas.docm | 18006 | SMB | 2018-02-02 | ABN | IER | Pfeifer and Langen | Atlas Copco | Internal Anomaly |  | 2053 | 13174 |  | Supplier quotation not updated in PkPv | SYSTEMS | System order acquisition | Offer quotation | Manpower / Main d'œuvre |  |  |  | NO |  |  | 2018-05-02 | 2018-03-22 | YES |  |  |  |  | N/A | 176 | 4000 | 4176 | YES | 2019-11-12 |  | 18006 Pfeifer and Langen | 18006 Pfeifer and Langen : Supplier quotation not updated in PkPv
CAP_EMISES 2018\18007 CEVA.docm | 18007 | SMB | 2018-02-27 | DBU | IER | CEVA | NVS PMP | Internal Anomaly |  | 2049 | 13198 | UF | Carbosep modules mounting issues | SYSTEMS | I&R process | Supply Chain PMP | Method / Méthode |  |  |  | YES | DBU | 2018-03-08 | 2018-05-27 | 2018-09-18 | NO |  |  |  |  | N/A | 6688 | 1895 | 8583 | YES | 2019-01-31 |  | 18007 CEVA | 18007 CEVA : Carbosep modules mounting issues
CAP_EMISES 2018\18008 CJ MALAISIE - CASSE MEMBRANE.docm | 18008 | SMB | 2018-03-05 | NPA | IER | CJ Malaisie | CTI | Claim | YES | 2040 | 12585 | UF | Breakage of BE Kerasep membranes | SYSTEMS | I&R process | Purchase | Material / Matière |  | CTI |  | YES | NPA/EWI | 2018-03-12 | 2018-06-05 | 2018-07-26 | NO |  | 2018-03-08 | 2018-08-31 | 2018-07-26 | YES | 7964.25 | 10547.5 | 18511.75 | YES | 2019-11-05 |  | 18008 CJ Malaisie | 18008 CJ Malaisie : Breakage of BE Kerasep membranes
CAP_EMISES 2018\18009 Accdt FMG.docm | 18009 | SMB | 2018-03-07 | FMG | STP | NA |  | Safety |  | NA | NA | NA | Fall of an employee outside staircase | STP | NA | NA | Manpower / Main d'œuvre |  |  |  | YES | CPT | 2018-03-07 | 2018-06-07 | 2018-05-02 | YES |  |  |  |  | N/A | 352 | 0 | 352 | YES | 2018-11-07 |  | 18009 NA | 18009 NA : Fall of an employee outside staircase
R:\QA-NVA IB\CAP\18010 Fufeng membranes issue.docm | 18010 | NVSA | 2018-03-13 | SXI | IER | FUFENG 7 | DANAI | Prevent / improve |  | 2045 | 13010 | MF | The membranes were damaged by SS scraps in manifolds | SYSTEMS | I&R process | commissioning | Material / Matière |  |  |  | YES | SXI | 2018-06-11 | 2018-06-13 | 2018-06-12 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 18010 FUFENG 7 | 18010 FUFENG 7 : The membranes were damaged by SS scraps in manifolds
CAP_EMISES 2018\18011 Friesland Moonraker.docm | 18011 | SMB | 2018-03-28 | DBU | IER | Friesland Campina | STCL Bossard Concept inox | Claim |  | 2038 | 12573 | MF | delay in units delivery, welding quality issue | SYSTEMS | I&R process |  | Method / Méthode |  |  |  | YES | DBU | 2018-03-28 | 2018-06-28 | 2018-09-28 | NO |  | 2018-04-04 | 2018-08-31 | 2018-09-28 | NO | 15400 | 28875 | 44275 | YES | 2019-09-18 |  | 18011 Friesland Campina | 18011 Friesland Campina : delay in units delivery, welding quality issue
R:\QA-NVA IB\CAP\18012 Xiangyu TRP Column bottom and top board deformation issue.docx | 18012 | NVSA | 2018-04-26 | EGU | IER | Xiangyu |  | Internal Anomaly |  | 2055 | 12578 | SSMB | Column bottom and top board deformation | SYSTEMS | I&R process |  | Method / Méthode |  |  |  | YES | EGU | 2018-04-26 | 2018-07-26 | 2018-07-02 | YES |  |  |  |  | N/A | 1230.7692 | 4641.0256 | 5871.7949 |  |  |  | 18012 Xiangyu | 18012 Xiangyu : Column bottom and top board deformation
CAP_EMISES 2018\18013 STCL.docm | 18013 | SMB | 2018-05-02 | JNJ | Achat | Friesland Campina | STCL | Supplier Dysfonctionning |  | 2038 | 12573 | MF | Welding quality issue MF skid | SYSTEMS | I&R process | Purchase/meca design | Material / Matière |  | STCL |  | YES | SOV/JNJ | 2018-05-02 | 2018-08-02 | 2018-07-11 | YES |  |  |  |  | N/A | 8272 | 13639 | 21911 | NO | 2019-02-18 | CAP19003 | 18013 Friesland Campina | 18013 Friesland Campina : Welding quality issue MF skid
14 | 18014 | SMB | 2018-05-03 | EWI | CS | GOI | Bollore | Claim |  |  | CV-1708-0012 | IEX | Resins tagging error | Cust. Sce | After sales process | Logistic | Method / Méthode |  |  |  | YES | EWI | 2018-05-14 | 2018-08-03 | 2018-07-23 | YES |  | 2018-05-15 | 2018-08-31 | 2018-07-23 | YES | 7744 | 4100 | 11844 | YES | 2019-02-14 |  | 18014 GOI | 18014 GOI : Resins tagging error
CAP_EMISES 2018\18015 YCSR Yemen Buses K1.docm | 18015 | SMB | 2018-05-07 | EWI | CS | YCSR | Composites Vec | Supplier Dysfonctionning |  |  | CV-1801-0018 | IEX | Defective nozzles | Cust. Sce | After sales process | Purchase | Material / Matière |  | CompositesVec |  | NO |  |  | 2018-08-07 | 2018-06-22 | YES |  |  |  |  | N/A | 440 | 300 | 740 | YES | 2018-11-09 |  | 18015 YCSR | 18015 YCSR : Defective nozzles
R:\QA-NVA IB\CAP\18016 Archer Zhang site accident - broken foot - PFA.docm | 18016 | NVSA | 2018-05-08 | PFA | IER | WANBANG |  | Safety |  | PN2997 |  |  | Archer Zhang site accident - broken foot | Equipement |  |  | Method / Méthode |  |  |  | YES | PFA | 2018-05-30 | 2018-08-08 | 2019-04-29 | NO |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 18016 WANBANG | 18016 WANBANG : Archer Zhang site accident - broken foot
CAP_EMISES 2018\18017 Vale Inco.docm | 18017 | SMB | 2018-05-14 | DBA | CS | Vale Inco | Composites Vec | Internal Anomaly |  |  | CV-1804-0001 |  | Error of purchased nozzle references | Cust. Sce | After sales process | Purchase | Manpower / Main d'œuvre |  |  |  | NO |  | 2018-05-14 | 2018-08-14 | 2018-07-06 | YES |  |  |  |  | N/A | 528 | 9055 | 9583 | YES | 2019-11-05 |  | 18017 Vale Inco | 18017 Vale Inco : Error of purchased nozzle references
CAP_EMISES 2018\18018 Friesland retard livraison skids UF RO.docm | 18018 | SMB | 2018-05-25 | DBU | IER | Friesland Campina | Concept Inox Bossard | Internal Anomaly |  | 2038 | 12573 | UF RO | Delay UF RO skids delivery | SYSTEMS | I&R process | project management | Method / Méthode |  |  |  | YES | DBU | 2018-05-23 | 2018-08-25 | 2018-08-21 | YES |  |  |  |  | N/A | 2552 | 0 | 2552 | YES | 2019-09-18 |  | 18018 Friesland Campina | 18018 Friesland Campina : Delay UF RO skids delivery
CAP_EMISES 2018\18019 ADM US-Borniers dans armoire.docm | 18019 | SMB | 2018-06-08 | JPL | IER | ADM US | SPIE | Supplier Dysfonctionning |  | 2048 | 12194 |  | Error in the choice of electrical terminal blocks | SYSTEMS | I&R process | AEI design | Material / Matière |  |  |  | NO |  |  | 2018-09-08 | 2018-08-22 | YES |  |  |  |  | N/A | 616 | 0 | 616 | YES | 2019-11-04 |  | 18019 ADM US | 18019 ADM US : Error in the choice of electrical terminal blocks
CAP_EMISES 2018\18020 Beneo.docm | 18020 | SMB | 2018-06-15 | ADP | R&D | BENEO Chili |  | Internal Anomaly |  |  | 2018-009 | cIEX | Regeneration protocol pb and not adapted pilot | R&D | PPD Process | R&D piloting | Equipment / Matériel |  |  |  | YES | ADP | 2018-07-03 | 2018-09-15 | 2018-09-11 | YES |  |  |  |  | N/A | 12936 | 1930 | 14866 | YES | 2019-10-30 |  | 18020 BENEO Chili | 18020 BENEO Chili : Regeneration protocol pb and not adapted pilot
CAP_EMISES 2018\18021 Biospringer fuite module K99 G3.docm | 18021 | SMB | 2018-06-27 | SMR | IER | Biospringer | CMN | Supplier Dysfonctionning |  | 2026 | 11244 | MF | K99 module leakage | SYSTEMS | Purchase | Supply Chain PMP | Material / Matière |  |  |  | NO |  |  | 2018-09-27 | 2018-09-14 | YES |  |  |  |  | N/A | 2728 | 0 | 2728 | YES | 2019-01-30 |  | 18021 Biospringer | 18021 Biospringer : K99 module leakage
R:\QA-NVA IB\CAP\18022 CJ internals fabrication issue.docm | 18022 | NVSA | 2018-07-05 | WWE | IER | CJ GMP1 | Composite vec | Internal Anomaly |  | 2062 | 13678 | CIEX | The mismatch on internals parts | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | RCH/SOV | 2018-07-03 | 2018-10-05 | 2018-07-26 | YES |  |  |  |  | N/A | 164.1026 | 145.3846 | 309.4872 |  |  |  | 18022 CJ GMP1 | 18022 CJ GMP1 : The mismatch on internals parts
R:\QA-NVA IB\CAP\18023-Yinmore Nozzles issue.docm | 18023 | NVSA | 2018-07-05 | WWE | IER | Yinmore-Haisum |  | Internal Anomaly |  | 2029 | 9801 | IEX | The nozzle under internal backwashing flange can't be mounted | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | RCH | 2018-07-13 | 2018-10-05 | 2018-07-26 | YES |  |  |  |  | N/A | 164.1026 | 46.1538 | 210.2564 |  |  |  | 18023 Yinmore-Haisum | 18023 Yinmore-Haisum : The nozzle under internal backwashing flange can't be mounted
CAP_EMISES 2018\18024 Soin LLR.docm | 18024 | SMB | 2018-07-17 | LLR | R&D | Sucden |  | Safety |  |  | 2018-001 |  | Rotavapor balloon breakage | R&D | PPD Process | Laboratory tests | Method / Méthode |  |  |  | YES | CPT | 2018-07-17 | 2018-10-17 | 2018-10-05 | YES |  |  |  |  | N/A | 176 | 418 | 594 | YES | 2019-10-30 |  | 18024 Sucden | 18024 Sucden : Rotavapor balloon breakage
R:\QA-NVA IB\CAP\18025-ADM 2 FT issue.docm | 18025 | NVSA | 2018-07-31 | ALI | IER | ADM | E+H | Prevent / improve |  | 1984 | 9728 | SSMB+MB | The electromagnetic flowmeter doesn't work properly | SYSTEMS | I&R process | AEI design | Method / Méthode |  |  |  | YES | ALI | 2018-07-31 | 2018-10-31 | 2018-10-30 | YES |  |  |  |  | N/A | 1518.2051 | 25641.0256 | 27159.2308 |  |  |  | 18025 ADM | 18025 ADM : The electromagnetic flowmeter doesn't work properly
CAP_EMISES 2018\18026 Téréos Chevrières.docm | 18026 | SMB | 2018-08-21 | DBA | CS | Téréos Chevrières | DOW | Pdt unconformity |  |  | CV-1710-0020 | IEX | Amine taste of liquid sugar | Cust. Sce | After sales process |  | Method / Méthode |  |  |  | YES | DBA | 2018-08-21 | 2018-11-21 | 2019-02-11 | NO |  |  |  |  | N/A | 1408 | 100 | 1508 | YES | 2019-11-12 |  | 18026 Téréos Chevrières | 18026 Téréos Chevrières : Amine taste of liquid sugar
CAP_EMISES 2018\18027 Mérial St-Priest.docm | 18027 | SMB | 2018-08-22 | PBO | CS | Mérial | Progress | Claim |  |  | CV-1807-0027 | UF | Leakage and broken Carbosep mbres | Cust. Sce | After sales process |  | Material / Matière |  |  |  | YES | PBO | 2018-08-27 | 2018-11-22 | 2019-01-25 | NO |  | 2018-08-13 | 2019-01-31 | 2019-01-25 | YES | 616 | 0 | 616 | YES | 2019-11-04 |  | 18027 Mérial | 18027 Mérial : Leakage and broken Carbosep mbres
CAP_EMISES 2018\18028 QNS.docm | 18028 | SMB | 2018-09-03 | CPV | STP | QNS |  | Internal Anomaly | X | 2070 | 13599 | Decolo/NF | PID Tags coding error | SYSTEMS | I&R process | Meca design | Manpower / Main d'œuvre |  |  |  | YES | CPV/SOV | 2018-09-25 | 2018-12-03 | 2019-01-23 | NO |  |  |  |  | N/A | 1533 | 0 | 1533 | YES | 2019-11-04 |  | 18028 QNS | 18028 QNS : PID Tags coding error
CAP_EMISES 2018\18029 CEVA Chine Module S52 1709-02.docm | 18029 | SMB | 2018-09-21 | ExMPT | IER | CEVA | Valorel | Supplier Dysfonctionning |  | 2050 | 13191 | UF | flatness defect on permeate output module S52 | SYSTEMS | I&R process | Supply Chain PMP | Material / Matière |  |  |  | NO |  |  | 2018-12-21 | 2018-10-23 | YES |  |  |  |  | N/A | 0 | 0 | 0 | YES | 2019-01-31 |  | 18029 CEVA | 18029 CEVA : flatness defect on permeate output module S52
CAP_EMISES 2018\18030 BDU_KLIM3-Bolloré.docm | 18030 | SMB | 2018-09-28 | JMR | Achat | KLIM 3 | Bollore | Internal Anomaly |  | 2051 | 10154 | NF | Shipment of material subject to export license without license | SYSTEMS | Purchase | Logistic | Method / Méthode |  |  |  | YES | JMR | 2018-09-12 | 2018-12-28 | 2018-12-06 | YES |  |  |  |  | N/A | 704 | 0 | 704 | YES | 2019-10-30 |  | 18030 KLIM 3 | 18030 KLIM 3 : Shipment of material subject to export license without license
CAP_EMISES 2018\18031 Friesland Moonraker pompe OI.docm | 18031 | SMB | 2018-10-10 | AKO | IER | Friesland Campina | Alfa Laval | Internal Anomaly |  | 2038 | 12573 | OI | Broken booster pump | SYSTEMS | I&R process | Commissioning | Method / Méthode | 8D-KT |  |  | YES | JGO | 2018-10-05 | 2019-01-10 | 2019-01-09 | YES |  |  |  |  | N/A | 5720 | 1999.47 | 7719.47 | YES | 2019-09-18 |  | 18031 Friesland Campina | 18031 Friesland Campina : Broken booster pump
CAP_EMISES 2018\18032 CARGILL SPAIN.docm | 18032 | SMB | 2018-10-10 | HPI | IER | Cargill Spain | Gree KCH | Claim |  | 1961 | 9310 | IEX | Leak on cationic column | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | HPI | 2018-10-17 | 2019-01-10 | 2019-01-30 | NO |  | 2018-10-11 | 2019-01-31 | 2019-01-30 | YES | 1496 | 0 | 1496 | YES | 2019-11-04 |  | 18032 Cargill Spain | 18032 Cargill Spain : Leak on cationic column
CAP_EMISES 2018\18033 Cargill Sight glass.docm | 18033 | SMB | 2018-10-22 | ExMPT | IER | Cargill Manchester | Gree KCH Huaming | Claim |  | 2031 | 10376 | IEX | Resin leakage on sight glass column | SYSTEMS | I&R process |  | Method / Méthode |  |  |  | YES | ExMPT | 2018-10-23 | 2019-01-22 | 2019-03-29 | NO |  | 2018-09-14 | 2019-03-31 | 2019-03-29 | YES | 6792 | 1000 | 7792 | YES | 2019-11-13 |  | 18033 Cargill Manchester | 18033 Cargill Manchester : Resin leakage on sight glass column
CAP_EMISES 2018\18034 Agrana-fuite résine.docm | 18034 | SMB | 2018-10-26 | SOV | IER | AGRANA |  | Internal Anomaly |  | 2014 | 10416 | SSMB | Resin leakage on SSMB column | SYSTEMS | I&R process | Commissioning | Method / Méthode | 8D-KT |  |  | YES | SOV | 2018-10-26 | 2019-01-26 | 2019-01-22 | YES |  |  |  |  | N/A | 27896 | 38680 | 66576 |  | A faire 12/20 | reporté à la clôture projet, intervention SOV fin 2020 | 18034 AGRANA | 18034 AGRANA : Resin leakage on SSMB column
| 18035 | SMB | 2018-11-05 | JNJ | Achat | Friesland Campina | Bollore | Internal Anomaly |  | 2038 | 12573 | OI | Missing organic membranes | SYSTEMS | Purchase | Shipment | Method / Méthode |  |  |  | YES | JNJ | 2018-11-08 | 2019-02-05 | 2019-02-01 | YES |  |  |  |  | N/A | 528 | 2026 | 2554 | YES | 2019-11-04 |  | 18035 Friesland Campina | 18035 Friesland Campina : Missing organic membranes
R:\QA-NVA IB\CAP\18036 Fufeng Lysine gasket leakage issue.docm | 18036 | NVSA | 2018-12-19 | ALI | IER | FUFENG | HUAMING/ZY | Prevent / improve |  | 2060 | 13653 | IEX | Gaskets of front piping leakage | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | ALI | 2018-12-31 | 2019-03-19 | 2019-01-07 | YES |  |  |  |  | N/A | 0 | 350 | 350 |  |  |  | 18036 FUFENG | 18036 FUFENG : Gaskets of front piping leakage
CAP_EMISES 2018\18037 GOI livraison silex.docm | 18037 | SMB | 2018-12-21 | EWI | CS | GOI | Bollore | Claim |  |  | CV-1803-0017 | IEX | Damaged gravels bags/pallets | Cust. Sce | After sales process | Shipment | Material / Matière |  |  |  | YES | EWI | 2019-01-08 | 2019-03-21 | 2019-02-14 | YES |  | 2018-12-08 | 2019-03-31 | 2019-02-14 | YES | 352 | 1200 | 1552 |  | A faire 12/20 | cde en cours | 18037 GOI | 18037 GOI : Damaged gravels bags/pallets
CAP_EMISES 2019\19001 Bac BW Agrana.docm | 19001 | SMB | 2019-01-16 | FBI | STP | Agrana |  | Internal Anomaly |  | 2014 | 10416 | IEX | Back wash tank design | SYSTEMS | I&R process | Process design | Method / Méthode |  |  |  | YES | FBI | 2019-01-24 | 2019-04-16 | 2019-04-15 | YES |  |  |  |  | N/A | 1256 | 5000 | 6256 | YES | 2020-11-25 |  | 19001 Agrana | 19001 Agrana : Back wash tank design
R:\QA-NVA IB\CAP\19002 QNS 300# gaskest material mistake issue.docm | 19002 | NVSA | 2019-01-28 | WWE | IER | QNS | HUAMING | Internal Anomaly |  | 2070 | 13599 | Decolo/MF | Material of 300# gasket should be PTFE instead of EPDM, wrong chosed in spec | SYSTEMS | I&R process | Commissioning | Manpower / Main d'œuvre |  |  |  | YES | RCH | 2019-03-15 | 2019-04-28 | 2019-03-18 | YES |  |  |  |  | N/A | 213.3333 | 62.1733 | 275.5067 |  |  |  | 19002 QNS | 19002 QNS : Material of 300# gasket should be PTFE instead of EPDM, wrong chosed in spec
CAP_EMISES 2019\19003 Friesland GOS75_Labbe\19003 GOS75_LABBE.docm | 19003 | SMB | 2019-02-06 | JMR | Achat | Friesland Campina | LABBE | Supplier Dysfonctionning | X | 2047 | 13149 | SSMB | Welding quality issue chromato columns | SYSTEMS | Purchase |  | Method / Méthode | 8D-KT |  |  | YES | JMR | 2019-02-18 | 2019-05-06 | 2019-09-13 | NO |  |  |  |  | N/A | 23092 | 78494 | 101586 |  | A faire 01/21 | pas nouveau projet, à décaler 2021 | 19003 Friesland Campina | 19003 Friesland Campina : Welding quality issue chromato columns
CAP_EMISES 2019\19004 Sunar\19004 SUNAR.docm | 19004 | SMB | 2019-02-13 | LRD | R&D | Sunar |  | Prevent / improve |  |  | RD2018-048 | SSMB | Insufficient URS at the begining of the project | R&D | PPD Process | Process design | Method / Méthode |  |  |  | NO |  |  | 2019-05-13 | 2019-05-06 | YES |  |  |  |  | N/A | 1293.6 | 0 | 1293.6 | YES | 2020-11-16 |  | 19004 Sunar | 19004 Sunar : Insufficient URS at the begining of the project
CAP_EMISES 2019\19005 GOI conditionnement résine\19005 GOI conditionnement résines.docm | 19005 | SMB | 2019-02-19 | CDL | CS | GOI | DOW | Supplier Dysfonctionning |  |  | CV-1803-0017 | IEX | Poor packaging of resins | Cust. Sce | After sales process | packaging | Material / Matière |  |  |  | NO |  |  | 2019-05-19 | 2019-05-09 | YES |  |  |  |  | N/A | 2992 | 0 | 2992 | NO | 2019-12-17 | CAP19052 | 19005 GOI | 19005 GOI : Poor packaging of resins
CAP_EMISES 2019\19006 PARAG Bolloré\19006 PARAG.docm | 19006 | SMB | 2019-03-05 | CDL | CS | Parag | Bollore | Supplier Dysfonctionning | X |  | CV-1809-0017 | IEX | Bad resine reference sent to customer | Cust. Sce | After sales process | Logistic | Material / Matière |  | Bolloré |  | YES | EWI | 2019-04-03 | 2019-06-05 | 2019-05-07 | YES |  |  |  |  | N/A | 1564 | 2000 | 3564 | YES | 2020-11-18 |  | 19006 Parag | 19006 Parag : Bad resine reference sent to customer
CAP_EMISES 2019\19007 Olon Filtres\19007 OLON filtres auto-nettoyants.docm | 19007 | SMB | 2019-03-05 | RDA | IER | OLON |  | Internal Anomaly |  | 2073 | 13929 | MF | Important budget difference between offer and order of self-cleaning filters | SYSTEMS | I&R process | Process design | Method / Méthode |  |  |  | YES | RDA | 2019-03-07 | 2019-06-05 | 2019-05-22 | YES |  |  |  |  | N/A | 0 | 47500 | 47500 | YES | 2020-11-18 |  | 19007 OLON | 19007 OLON : Important budget difference between offer and order of self-cleaning filters
CAP_EMISES 2019\19008 Alkem Mauvais cablage\19008 Alkem Mauvais cablage.docm | 19008 | SMB | 2019-03-15 | SML | IER | ALKEM | SPIE | Internal Anomaly |  | 2052 | 12322 | SSMB | Bad wiring done by customer from electrical diagrams provided | SYSTEMS | I&R process | AEI design | Method / Méthode |  |  |  | NO |  |  | 2019-06-15 | 2019-06-12 | YES |  |  |  |  | N/A | 2484 | 0 | 2484 | YES | 2020-11-17 |  | 19008 ALKEM | 19008 ALKEM : Bad wiring done by customer from electrical diagrams provided
CAP_EMISES 2019\19009 BBCA\19009 BBCA.docm | 19009 | SMB | 2019-03-19 | EWI | SC | BBCA | NVS PMP | Internal Anomaly |  |  | CV-1902-0012 | MF | Delay to place purchase order | Cust. Sce | After sales process | Supply Chain PMP | Method / Méthode |  |  |  | YES | EWI | 2019-04-01 | 2019-06-19 | 2019-06-17 | YES |  |  |  |  | N/A | 736 | 0 | 736 | YES | 2020-11-18 |  | 19009 BBCA | 19009 BBCA : Delay to place purchase order
CAP_EMISES 2019\19010 Danone Nutricia\19010 Nutricia Danone.docm | 19010 | SMB | 2019-03-21 | TEB | R&D | Danone |  | Internal Anomaly |  |  | EN-3168 |  | Hydrolysis of a customer sample stored at room temperature | R&D | PPD Process | sample reception | Manpower / Main d'œuvre |  |  |  | NO |  |  | 2019-06-21 | 2019-06-19 | YES |  |  |  |  | N/A | 276 | 0 | 276 | YES | 2020-11-18 |  | 19010 Danone | 19010 Danone : Hydrolysis of a customer sample stored at room temperature
R:\QA-NVA IB\CAP\19011 CJ GMP3 LSH-LSL height mistake.docm | 19011 | NVSA | 2019-04-01 | WWE | IER | CJ Liaocheng | JINLONG | Internal Anomaly |  | 2077 | 13825 | SSMB | The height of LSH/LSL is wrong | SYSTEMS | I&R process | Meca design | Method / Méthode |  |  |  | YES | RCH | 2019-04-22 | 2019-07-01 | 2019-06-13 | YES |  |  |  |  | N/A | 426.6667 | 566.6667 | 993.3333 |  |  |  | 19011 CJ Liaocheng | 19011 CJ Liaocheng : The height of LSH/LSL is wrong
R:\QA-NVA IB\CAP\19012 CJ Jombang CIEX resin package issue.docm | 19012 | NVSA | 2019-04-01 | EGU | IER | CJ Jombang Indonesia | Mitsubishi | Internal Anomaly |  | 2069 | 13883 | IEX | The resin package should be blank. | Cust. Sce | After sales process | Resin marking | Manpower / Main d'œuvre |  |  |  | YES | EGU | 2019-04-06 | 2019-07-01 | 2019-04-30 | YES |  |  |  |  | N/A | 757.3333 | 2917.3333 | 3674.6667 |  |  |  | 19012 CJ Jombang Indonesia | 19012 CJ Jombang Indonesia : The resin package should be blank.
CAP_EMISES 2019\19013 QNS - blower\19013 Blower QNS.docm | 19013 | SMB | 2019-04-02 | RDA | IER | QNS | AERZEN | Internal Anomaly |  | 2070 | 13599 | IEX | Blower not purchased on time | SYSTEMS | Purchase | Meca design | Manpower / Main d'œuvre |  |  |  | YES | RDA | 2019-04-03 | 2019-07-02 | 2019-07-01 | YES |  |  |  |  | N/A | 460 | 2260 | 2720 | YES | 2020-11-18 |  | 19013 QNS | 19013 QNS : Blower not purchased on time
CAP_EMISES 2019\19014 Ingredion - Bray\19014 Ingredion -Bray.docm | 19014 | SMB | 2019-04-09 | CCR | IER | Ingredion | Bray | Internal Anomaly |  | 2067 | 11925 | SSMB | Material of butterfly valves | SYSTEMS | Purchase | Meca Design | Manpower / Main d'œuvre |  |  |  | YES | SMR | 2019-04-16 | 2019-07-09 | 2019-07-05 | YES |  |  |  |  | N/A | 1472 | 25547 | 27019 | YES | 2020-11-13 |  | 19014 Ingredion | 19014 Ingredion : Material of butterfly valves
CAP_EMISES 2019\19015 Alkem - silex\19015 Alkem- silex.docm | 19015 | SMB | 2019-04-11 | JMR | IER | Alkem | Bollore | Internal Anomaly |  | 2052 | 12322 | SSMB | Gravel not delivered to customer site | SYSTEMS | Purchase | After sales | Method / Méthode |  |  |  | YES | JMR | 2019-03-06 | 2019-07-11 | 2019-06-17 | YES |  |  |  |  | N/A | 920 | 1290 | 2210 | YES | 2020-11-26 |  | 19015 Alkem | 19015 Alkem : Gravel not delivered to customer site
R:\QA-NVA IB\CAP\19016 CJ Brazil Sulzer motor issue.docm | 19016 | NVSA | 2019-04-26 | SUXI | IER | CJ Brazil | SULZER | Supplier Dysfonctionning |  | 2072 | 14268 | MF | The Sulzer motor missed delivery | SYSTEMS | I&R process |  | Method / Méthode |  |  |  | NO |  |  | 2019-07-26 | 2019-04-30 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 19016 CJ Brazil | 19016 CJ Brazil : The Sulzer motor missed delivery
R:\QA-NVA IB\CAP\19017 CJ Brazil Ebro delivery mistake issue.docm | 19017 | NVSA | 2019-04-26 | SUXI | IER | CJ Brazil | Ebro | Supplier Dysfonctionning |  | 2072 | 14268 | MF | The Ebro valves delivery mistake | SYSTEMS | I&R process |  | Method / Méthode |  |  |  | NO |  |  | 2019-07-26 | 2019-04-30 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 19017 CJ Brazil | 19017 CJ Brazil : The Ebro valves delivery mistake
R:\QA-NVA IB\CAP\19018 HuaQiao Ebro valves indicator wrong position issue.docm | 19018 | NVSA | 2019-04-26 | GYO | IER | HUAQIAO | Ebro | Supplier Dysfonctionning |  | 2056 | 12996 | Decolo/MF | Butterfly valve disc position indicators are wrongly mounted | SYSTEMS | I&R process |  | Manpower / Main d'œuvre |  |  |  | YES | RCH | 2019-04-18 | 2019-07-26 | 2019-07-16 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 19018 HUAQIAO | 19018 HUAQIAO : Butterfly valve disc position indicators are wrongly mounted
R:\QA-NVA IB\CAP\19019 Klim 3 (Ethiopia) import resin packing list issue.docm | 19019 | NVSA | 2019-05-08 | ALI | IER | KLIM | NOVASEP SMB | Internal Anomaly |  | 2051 | 10154 | Decolo | Resin packing list information wrong | SYSTEMS | I&R process |  | Manpower / Main d'œuvre |  |  |  | NO |  |  | 2019-08-08 | 2019-06-13 | YES |  |  |  |  | N/A | 0 | 333.3333 | 333.3333 |  |  |  | 19019 KLIM | 19019 KLIM : Resin packing list information wrong
CAP_EMISES 2019\19020 Olon EV\19020 OLON Electrovannes VAC - VDC.docm | 19020 | SMB | 2019-05-15 | RDA | IER | OLON |  | Internal Anomaly |  | 2073 | 13929 | MF | MF solenoid valves specifications error | SYSTEMS | I&R process | AEI design | Manpower / Main d'œuvre |  |  |  | YES | RDA | 2019-05-20 | 2019-08-15 | 2019-07-12 | YES |  |  |  |  | N/A | 0 | 2287.5 | 2287.5 | YES | 2020-11-18 |  | 19020 OLON | 19020 OLON : MF solenoid valves specifications error
R:\QA-NVA IB\CAP\19021 CJ Brazil Sulzer coupling issue.docm | 19021 | NVSA | 2019-05-24 | SUXI | IER | CJ Brazil | SULZER | Supplier Dysfonctionning |  | 2072 | 14268 | MF | Sulzer circulation pump GA2242 coupling rubber tire(Martin) was broken | SYSTEMS | Purchase |  | Method / Méthode |  |  |  | NO |  |  | 2019-08-24 | 2019-07-05 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 19021 CJ Brazil | 19021 CJ Brazil : Sulzer circulation pump GA2242 coupling rubber tire(Martin) was broken
CAP_EMISES 2019\19022 Pfeifer and langen\19022 Pfeifer and langen - positionnement pied des colones.docm | 19022 | SMB | 2019-06-18 | ABN | IER | Pfeifer and Langen |  | Claim |  | 2053 | 13174 | IEX | Misposition column feet | SYSTEMS | I&R process | Meca design | Method / Méthode |  |  |  | NO |  |  | 2019-09-18 | 2019-09-05 | YES |  | 2019-05-13 | 2019-09-30 | 2019-09-05 | YES | 92 | 1513 | 1605 | YES | 2020-11-13 |  | 19022 Pfeifer and Langen | 19022 Pfeifer and Langen : Misposition column feet
CAP_EMISES 2019\19023 MAG\19023 MAG.docm | 19023 | SMB | 2019-06-25 | CPV | STP | MAG | SPIE | Internal Anomaly |  | 2074 | 14035 | IEX | Untested exchange table on customer site | SYSTEMS | I&R process | commissioning | Method / Méthode |  |  |  | YES | CPV | 2019-06-26 | 2019-09-25 | 2019-09-06 | YES |  |  |  |  | N/A | 5888 | 1040 | 6928 |  | A faire 01/21 | pas nouveau projet, à décaler 2021 | 19023 MAG | 19023 MAG : Untested exchange table on customer site
CAP_EMISES 2019\19024 TEREOS Chevrières\19024 TEREOS CHEVRIERES RESINES.docm | 19024 | SMB | 2019-06-26 | CDL | CS | Tereos Chevrières | DOW | Supplier Dysfonctionning |  |  | CV-1903-0027 | IEX | Lack of resins delivery information | Cust. Sce | After sales process | Logistic | Material / Matière |  | DOW |  | NO |  |  | 2019-09-26 | 2019-09-12 | YES |  |  |  |  | N/A | 368 | 0 | 368 | YES | 2020-11-18 |  | 19024 Tereos Chevrières | 19024 Tereos Chevrières : Lack of resins delivery information
R:\QA-NVA IB\CAP\19025 Fufeng 10 flashing tank flange mistake.docm | 19025 | NVSA | 2019-07-04 | SUXI | IER | FUFENG | ZY | Internal Anomaly |  | 2076 | 14478 | SSMB | Flange DN150 on degassing tank F160 is too small | SYSTEMS | I&R process | Meca Design | Manpower / Main d'œuvre |  |  |  | YES | RCH | 2019-07-29 | 2019-10-04 | 2019-07-29 | YES |  |  |  |  | N/A | 88.33 | 0 | 88.33 |  |  |  | 19025 FUFENG | 19025 FUFENG : Flange DN150 on degassing tank F160 is too small
CAP_EMISES 2019\19026 MAG reglage parametres\19026 MAG.docm | 19026 | SMB | 2019-07-08 | CPV | STP | MAG | SPIE | Internal Anomaly |  | 2074 | 14035 | IEX | Default settings and screenshot | SYSTEMS | I&R process | commissioning | Manpower / Main d'œuvre |  |  |  | YES | HPI | 2019-07-18 | 2019-10-08 | 2019-10-03 | YES |  |  |  |  | N/A | 828 | 0 | 828 |  | A faire 01/21 | pas nouveau projet, à décaler 2021 | 19026 MAG | 19026 MAG : Default settings and screenshot
CAP_EMISES 2019\19027 OLON- montage sondes\19027 OLON montage sondes.docm | 19027 | SMB | 2019-07-17 | XDE | IER | OLON |  | Internal Anomaly |  | 2073 | 13929 | MF | Mounting problem pH and conductivity probes | SYSTEMS | I&R process | Meca Design | Manpower / Main d'œuvre |  |  |  | YES | SOV | 2019-07-19 | 2019-10-17 | 2019-10-11 | YES |  |  |  |  | N/A | 184 | 2500 | 2684 | YES | 2020-11-23 |  | 19027 OLON | 19027 OLON : Mounting problem pH and conductivity probes
CAP_EMISES 2019\19028 QNS- refroidisseur\19028 QNS -Air cooler.docm | 19028 | SMB | 2019-07-18 | RDA | IER | QNS |  | Internal Anomaly |  | 2070 | 13599 | Decolo | Air cooler order not generated despite of its specification | SYSTEMS | Purchase | Meca design | Method / Méthode |  |  |  | YES | SOV | 2019-07-24 | 2019-10-18 | 2019-10-15 | YES |  |  |  |  | N/A | 330 | 278 | 608 | YES | 2020-11-18 |  | 19028 QNS | 19028 QNS : Air cooler order not generated despite of its specification
R:\QA-NVA IB\CAP\19029 CJ Liaocheng Bolts length issue.docm | 19029 | NVSA | 2019-07-23 | ALI | IER | CJ LIAOCHENG |  | Internal Anomaly |  | 2077 | 13825 | CIEX | Bolts length is not long enough | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | RCH | 2019-07-23 | 2019-10-23 | 2019-10-23 | YES |  |  |  |  | N/A | 128 | 4116.1333 | 4244.1333 |  |  |  | 19029 CJ LIAOCHENG | 19029 CJ LIAOCHENG : Bolts length is not long enough
R:\QA-NVA IB\CAP\19030 CJ Liaocheng fasterner drawing updating issue.docm | 19030 | NVSA | 2019-07-23 | ALI | IER | CJ LIAOCHENG | Runyuan | Internal Anomaly |  | 2077 | 13825 | CIEX | Drawing updating and following should be continuously tracking | SYSTEMS | I&R process | Meca design | Method / Méthode |  |  |  | YES | RCH | 2019-07-30 | 2019-10-23 | 2019-08-01 | YES |  |  |  |  | N/A | 128 | 0 | 128 |  |  |  | 19030 CJ LIAOCHENG | 19030 CJ LIAOCHENG : Drawing updating and following should be continuously tracking
CAP_EMISES 2019\19031 ADM- Bolloré\19031 ADM - Bolloré.docm | 19031 | SMB | 2019-07-25 | CJA | CS | ADM | Bollore | Supplier Dysfonctionning |  |  | CV-1905-0071 |  | Package sent by mistake to a customer | Cust. Sce | After sales process | Logistic | Material / Matière |  | Bolloré |  | NO |  |  | 2019-10-25 | 2019-10-21 | YES |  |  |  |  | N/A | 220 | 6256.1333 | 6476.1333 | YES | 2020-11-13 |  | 19031 ADM | 19031 ADM : Package sent by mistake to a customer
CAP_EMISES 2019\19031 ADM- Bolloré\19031 ADM - Bolloré.docm | 19032 | SMB | 2019-08-09 | SML | IER | OLON | Endress hauser | Supplier Dysfonctionning |  | 2073 | 13929 | UF | Connection issue pH and conductivity probes on tank (NA Connect) | SYSTEMS | I&R process | AEI Design | Method / Méthode |  |  |  | NO |  |  | 2019-11-09 | 2019-10-25 | YES |  |  |  |  | N/A | 1196 | 40 | 1236 | YES | 2020-11-17 |  | 19032 OLON | 19032 OLON : Connection issue pH and conductivity probes on tank (NA Connect)
CAP_EMISES 2019\19033 Pfeifer & Langen moteur ventilateur\19033 Pfeifer & Langen moteru ventilo.docm | 19033 | SMB | 2019-08-27 | MGL | IER | Pfeifer and Langen |  | Internal Anomaly |  | 2053 | 13174 | IEX | Fan blower forgotten for electrical study | SYSTEMS | I&R process | AEI Design | Method / Méthode |  |  |  | YES | HPI | 2019-08-27 | 2019-11-27 | 2019-11-05 | YES |  |  |  |  | N/A | 1840 | 2178 | 4018 | YES | 2020-11-23 |  | 19033 Pfeifer and Langen | 19033 Pfeifer and Langen : Fan blower forgotten for electrical study
CAP_EMISES 2019\19034 Chengxin Bolloré\19034 Chengxin Bolloré.docm | 19034 | SMB | 2019-08-27 | XRO | IER | CHENGXIN | Bollore | Supplier Dysfonctionning |  | 2078 | 12769 | SSMB | Issue with Re-Labelling of XA Resins by our Logistic Supplier | SYSTEMS | Purchase | Logistic | Material / Matière |  | Bolloré |  | YES | JMR | 2019-09-20 | 2019-11-27 | 2019-11-22 | YES |  |  |  |  | N/A | 703.3333 | 0 | 703.3333 | YES | 2020-11-26 |  | 19034 CHENGXIN | 19034 CHENGXIN : Issue with Re-Labelling of XA Resins by our Logistic Supplier
CAP_EMISES 2019\19035 OLON MTCI\19035 OLON_MTCI drain MF.docm | 19035 | SMB | 2019-09-04 | XDE | IER | OLON | MTCI | Supplier Dysfonctionning |  | 2073 | 13929 | MF | Manufacturing and mounting failure of MF drain piping | SYSTEMS | Purchase |  | Material / Matière |  | MTCI |  | NO |  |  | 2019-12-04 | 2019-11-27 | YES |  |  |  |  | N/A | 184 | 2000 | 2184 | YES | 2020-11-23 |  | 19035 OLON | 19035 OLON : Manufacturing and mounting failure of MF drain piping
CAP_EMISES 2019\19036 Etude labo\19036 Etuve labo.docm | 19036 | SMB | 2019-09-09 | TEB | R&D | Service R&D |  | Safety |  | NA | NA | NA | Overheating of a R&D oven | R&D | PPD Process |  | Equipment / Matériel |  |  |  | NO |  |  | 2019-12-09 | 2020-01-06 | NO |  |  |  |  | N/A | 92 | 200 | 292 | YES | 2020-11-18 |  | 19036 Service R&D | 19036 Service R&D : Overheating of a R&D oven
CAP_EMISES 2019\19037 définition DP\19037 P&L DP.docm | 19037 | SMB | 2019-09-10 | ABN | IER | Pfeifer and Langen |  | Prevent / improve |  | 2053 | 13174 | IEX | DP definition | SYSTEMS | I&R process | Process design | Method / Méthode |  |  |  | NO |  |  | 2019-12-10 | 2019-12-02 | YES |  |  |  |  | N/A | 552 | 0 | 552 | YES | 2020-11-13 |  | 19037 Pfeifer and Langen | 19037 Pfeifer and Langen : DP definition
CAP_EMISES 2019\19038 Dédouanement produit R&D\19038 Tate & Lyle_dédouanement produit R&D.docm | 19038 | SMB | 2019-09-13 | AGI | R&D | Tate & Lyle | Bollore | Internal Anomaly |  |  | 2019-044 |  | Customer sample received late at NVS SMB | R&D | PPD Process |  | Method / Méthode | 8D-KT |  |  | YES | AGI | 2019-10-02 | 2019-12-13 | 2019-12-04 | YES |  |  |  |  | N/A | 1567.8333 | 0 | 1567.8333 |  | A faire 01/21 |  | 19038 Tate & Lyle | 19038 Tate & Lyle : Customer sample received late at NVS SMB
CAP_EMISES 2019\19039 Ingredion\19039 Ingredion.docm | 19039 | SMB | 2019-09-16 | SMR | IER | Ingredion |  | Internal Anomaly |  | 2067 | 11925 | SSMB | Forgotten item from Novasep scope | SYSTEMS | I&R process | AEI Design | Manpower / Main d'œuvre | 8D-KT |  |  | YES | SMR | 2019-09-26 | 2019-12-16 | 2019-11-26 | YES |  |  |  |  | N/A | 460 | 0 | 460 | YES | 2020-11-13 |  | 19039 Ingredion | 19039 Ingredion : Forgotten item from Novasep scope
CAP_EMISES 2019\19040 Rousselot\19040 Rousselot membranes trop courtes.docm | 19040 | SMB | 2019-09-17 | EWI | CS | Rousselot | CTI | Claim |  |  | CV-1904-0060 | MF | Kerasep membrane length problem | Cust. Sce | After sales process | Purchase | Material / Matière |  | CTI |  | YES | EWI | 2019-09-19 | 2019-12-17 | 2019-11-26 | YES |  | 2019-09-17 | 2019-12-31 | 2019-11-26 | YES | 276 | 100 | 376 | YES | 2020-11-18 |  | 19040 Rousselot | 19040 Rousselot : Kerasep membrane length problem
CAP_EMISES 2019\19041 Parry Sugar livraison mbres NF\19041 Parry Sugar-livraison mbres NF.docm | 19041 | SMB | 2019-09-30 | YVI | CS | Parry Sugar | Bollore | Internal Anomaly |  |  | CV-1810-0047 | NF | NF membranes quantity delivery error | Cust. Sce | After sales process | Logistic | Method / Méthode |  |  |  | YES | EWI | 2019-10-14 | 2019-12-30 | 2020-02-25 | NO |  |  |  |  | N/A | 644 | 0 | 644 | YES | 2020-11-18 |  | 19041 Parry Sugar | 19041 Parry Sugar : NF membranes quantity delivery error
CAP_EMISES 2019\19042 Beneo Orafti-retards livraisons résines\19042 BENEO Orafti-retards livraisons résines.docx | 19042 | SMB | 2019-10-03 | EWI | CS | Beneo Orafti | Lanxess | Claim |  |  | CV-1808-0002 | IEX | Resins delivery delay | Cust. Sce | After sales process | Purchase | Material / Matière |  | Lanxess |  | YES | EWI | 2019-10-17 | 2020-01-03 | 2019-12-11 | YES |  | 2019-10-03 | 2020-01-03 | 2019-12-11 | YES | 644 | 0 | 644 |  | A faire 12/2020 | réunion Direction S48 | 19042 Beneo Orafti | 19042 Beneo Orafti : Resins delivery delay
CAP_EMISES 2019\19043 LAICA-étiquettage résine erroné | 19043 | SMB | 2019-10-07 | MGL | CS | LAICA |  | Internal Anomaly | X |  | CV-1812-0025 |  | Resins labeling error | Cust. Sce | After sales process | Labelling | Manpower / Main d'œuvre | 8D-KT |  |  | YES | EWI | 2019-10-10 | 2020-01-07 | 2020-01-02 | YES |  |  |  |  | N/A | 552 |  | 552 | NO | 2020-10-05 | CAP20020 | 19043 LAICA | 19043 LAICA : Resins labeling error
R:\QA-NVA IB\CAP\19044 CJ Liaocheng Bray butterfly valves quality issue.docx | 19044 | NVSA | 2019-10-14 | SXI | IER | CJ LIAOCHENG | BRAY | Claim |  | 2062 | 13678 | CIEX | Bray butterfly valves quality problem | SYSTEMS | I&R process | project closed | Method / Méthode |  |  |  | YES | CSU | 2019-11-04 | 2020-01-14 | 2020-01-10 | YES |  |  | 2020-01-10 | 2020-01-10 | YES | 0 | 0 | 0 |  |  |  | 19044 CJ LIAOCHENG | 19044 CJ LIAOCHENG : Bray butterfly valves quality problem
R:\QA-NVA IB\CAP\19045 Chengxin resin leakage issue.docx | 19045 | NVSA | 2019-11-19 | EGU | IER | CHENGXIN | Runyuan/Finex | Claim |  | 2078 | 12769 | SSMB | Resin leakage is found from strainers during resin loading phase | SYSTEMS | I&R process | Start up | Equipment / Matériel |  |  |  | YES | EGU | 2019-11-19 | 2020-02-19 | 2021-03-11 | NO |  |  | 2020-03-31 | 2021-03-11 | NO |  |  | 0 |  |  |  | 19045 CHENGXIN | 19045 CHENGXIN : Resin leakage is found from strainers during resin loading phase
CAP_EMISES 2019\19046 Ennolys\19046 ENNOLYS .docx | 19046 | SMB | 2019-11-19 | SLO | CS | Ennolys | CTI | Claim |  |  | CV-1910-0082 | UF | Order confirmation and delay too long | Cust. Sce | After sales process | Purchase | Material / Matière |  | CTI |  | YES | EWI | 2019-11-19 | 2020-02-19 | 2020-02-07 | YES |  | 2019-11-20 | 2020-02-29 | 2020-02-07 | YES | 920 | 0 | 920 | YES | 2020-11-18 |  | 19046 Ennolys | 19046 Ennolys : Order confirmation and delay too long
CAP_EMISES 2019\19047 CKD\19047 CKD.docx | 19047 | SMB | 2019-11-21 | SLO | CS | CKD | CTI | Claim | X |  | CV-1909-0031 | MF | Successive postponements of the delivery date | Cust. Sce | After sales process | Purchase | Material / Matière |  | CTI |  | YES | EWI | 2019-11-22 | 2020-02-21 | 2020-02-19 | YES |  | 2019-11-21 | 2020-02-29 | 2020-02-19 | YES | 920 | 0 | 920 | YES | 2020-11-18 |  | 19047 CKD | 19047 CKD : Successive postponements of the delivery date
CAP_EMISES 2019\19048 Puratos\19048 PURATOS.docx | 19048 | SMB | 2019-11-21 | SLO | CS | Puratos | CTI | Claim | X |  | CV-1910-0053 | MF | Order confirmation and delay too long | Cust. Sce | After sales process | Purchase | Method / Méthode |  | CTI |  | YES | EWI | 2019-11-22 | 2020-02-21 | 2020-02-07 | YES |  | 2019-11-22 | 2020-02-29 | 2020-02-07 | YES | 552 | 0 | 552 | YES | 2020-11-18 |  | 19048 Puratos | 19048 Puratos : Order confirmation and delay too long
CAP_EMISES 2019\19049 pilote Evapo\19049 pilote Evapo R&D-séparateur.docx | 19049 | SMB | 2019-11-26 | GTI | R&D | Service R&D | Concept inox | Internal Anomaly |  | NA | NA | Evapo | Connection of the new separator evaporation pilot incorrectly positioned | R&D | PPD Process | Piloting | Method / Méthode |  |  |  | YES | GTI | 2019-12-03 | 2020-02-26 | 2020-02-18 | YES |  |  |  |  | N/A | 2576 | 300 | 2876 |  | A faire 01/21 | après déplacement des évapo | 19049 Service R&D | 19049 Service R&D : Connection of the new separator evaporation pilot incorrectly positioned
CAP_EMISES 2019\19050 Ingredion - DP C201\19050 Ingredion - pressure drops on lower network cell C201.docm | 19050 | SMB | 2019-11-28 | SMR | IER | Ingredion |  | Internal Anomaly |  | 2067 | 11925 | SSMB | Excessive pressure drop on lower network cell C201 | SYSTEMS | I&R process | commissioning | Manpower / Main d'œuvre |  |  |  | YES | SMR | 2019-11-13 | 2020-02-28 | 2020-01-13 | YES |  |  |  |  | N/A | 7620 | 0 | 7620 | YES | 2020-11-13 |  | 19050 Ingredion | 19050 Ingredion : Excessive pressure drop on lower network cell C201
R:\QA-NVA IB\CAP\19051 CJ P6 columns delay issue.docx | 19051 | NVSA | 2019-12-09 | SXI | IER | CJ P6 | GUANGXIN | Supplier Dysfonctionning |  | 2084 | 14930 | SSMB | Columns delay ,can't catch the schedule | SYSTEMS | Purchase | CQ | Management |  |  |  | YES | SXI | 2019-12-13 | 2020-03-09 | 2020-02-27 | YES |  |  |  |  | N/A | 2725 | 1867 | 4592 |  |  |  | 19051 CJ P6 | 19051 CJ P6 : Columns delay ,can't catch the schedule
CAP_EMISES 2019\19052 Galactic\19052 Galactic.docx | 19052 | SMB | 2019-12-12 | EWI | CS | Galactic | Dupont | Claim | X |  | CV-1908-0031 |  | Delivery without customer agreement and packaging error | Cust. Sce | After sales process | Packaging | Manpower / Main d'œuvre |  | DuPont |  | YES | EWI | 2019-12-17 | 2020-03-12 | 2020-03-26 | NO |  | 2019-12-12 | 2020-03-31 | 2020-03-26 | YES | 644 | 1550 | 2194 | YES | 2020-11-18 |  | 19052 Galactic | 19052 Galactic : Delivery without customer agreement and packaging error
CAP_EMISES 2019\19053 Etihad - Licence\19053 Etihad - licence d'exportation.docx | 19053 | SMB | 2019-12-13 | YVI | CS | Etihad | Bollore | Internal Anomaly | X |  | CV-1907-0015 | NF | Shipment of NF membranes subject to export license without license | Cust. Sce | After sales process | Logistic | Method / Méthode | 8D-KT | Bolloré |  | YES | EWI | 2019-12-18 | 2020-03-13 | 2020-03-10 | YES |  |  |  |  | N/A | 368 | 0 | 368 | YES | 2020-11-18 |  | 19053 Etihad | 19053 Etihad : Shipment of NF membranes subject to export license without license
R:\QA-NVA IB\CAP\19054 CJ Liaocheng Bray butterfly valves issue.docm | 19054 | NVSA | 2019-12-23 | ALI | IER | CJ liaocheng | Bray | Pdt unconformity |  | 2077 | 13825 | IEX | The spring in the pneumatic butterfly actuator cannot close the valve completely | SYSTEMS | Purchase |  | Material / Matière |  |  |  | YES | CSU | 2019-12-23 | 2020-03-23 | 2020-01-07 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 19054 CJ liaocheng | 19054 CJ liaocheng : The spring in the pneumatic butterfly actuator cannot close the valve completely
CAP_EMISES 2020\20001 Evapo verre\20001 Casse Evapo verre.docm | 20001 | SMB | 2020-01-17 | AGI | R&D | UPM C6 |  | Safety |  |  | 2019-055 | Evapo | Brocken glass separator of the evapo pilot | R&D | PPD Process | Piloting | Equipment / Matériel | 8D-KT |  |  | YES | AGI | 2020-01-21 | 2020-04-17 | 2020-07-28 | NO |  |  |  |  | N/A | 368 | 2774.48 | 3142.48 |  | A faire 12/21 | après déplacement des évapo | 20001 UPM C6 | 20001 UPM C6 : Brocken glass separator of the evapo pilot
CAP_EMISES 2020\20002 ADM US\20002 ADM.docx | 20002 | SMB | 2020-01-30 | EWI | CS | ADM |  | Claim |  | 2022 | 11279 | SSMB | Incorrect gravel loading at start-up / Unsuccessful customer service intervention | Cust. Sce | After sales process |  | Management |  |  |  | YES | EWI | 2020-01-31 | 2020-04-30 | 2020-04-28 | YES |  | 2020-01-31 | 2020-04-30 | 2020-04-28 | YES | 1615 | 0 | 1615 | YES | 2020-11-18 |  | 20002 ADM | 20002 ADM : Incorrect gravel loading at start-up / Unsuccessful customer service intervention
CAP_EMISES 2020\20003 Cargill Butterfly\20003 CARGILL BUTTERFLY - FT DEM.docx | 20003 | SMB | 2020-02-19 | SML | IER | Cargill Butterfly |  | Internal Anomaly |  | 2083 | 13900 | IEX | Wrong choice of flowmeter technology | SYSTEMS | I&R process | Process design | Method / Méthode |  |  |  | YES | SML | 2020-02-21 | 2020-05-19 | 2020-06-22 | NO |  |  |  |  | N/A | 944 | 990 | 1934 | YES | 2020-11-17 |  | 20003 Cargill Butterfly | 20003 Cargill Butterfly : Wrong choice of flowmeter technology
CAP_EMISES 2020\20004 Cargill Butterfly-pompes KSB\20004 Cargill Butterfly-Sheet-Pump quotation.docx | 20004 | SMB | 2020-02-27 | CDV | IER | Cargill Butterfly |  | Internal Anomaly |  | 2083 | 13900 | IEX | Sheet pump quotation vs customer URS | SYSTEMS | Order acquirement process | Quotation | Management |  |  |  | YES | CDV | 2020-03-17 | 2020-05-27 | 2020-05-26 | YES |  |  |  |  | N/A | 2208 | 30655 | 32863 |  | A faire 12/21 |  | 20004 Cargill Butterfly | 20004 Cargill Butterfly : Sheet pump quotation vs customer URS
CAP_EMISES 2020\20005 Tereos Nesle\20005 TEREOS NESLE.docx | 20005 | SMB | 2020-02-28 | PBO | CS | TEREOS NESLE | SUEZ | Claim |  |  | CA-1811-0239 | NF | default NF membrane | Cust. Sce | After sales process | Purchase | Material / Matière |  | SUEZ |  | YES | MGL | 2020-03-09 | 2020-05-28 | 2020-04-10 | YES |  | 2020-02-28 | 2020-05-31 | 2020-04-10 | YES | 190 | 0 | 190 | YES | 2020-11-13 |  | 20005 TEREOS NESLE | 20005 TEREOS NESLE : default NF membrane
R:\QA-NVA IB\CAP\20006 CJ P6 stud welded rod fall off from internal box issue.docm | 20006 | NVSA | 2020-03-09 | WWE | IER | CJ P6 | Guanxing | Supplier Dysfonctionning |  | 2084 | 14930 | SSMB | Stud welded rod fall off from internal box | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | WWE | 2020-03-10 | 2020-06-09 | 2020-05-21 | YES |  |  |  |  | N/A | 3057 | 160 | 3217 |  |  |  | 20006 CJ P6 | 20006 CJ P6 : Stud welded rod fall off from internal box
CAP_EMISES 2020\20007 SOFIVO\20007 SOFIVO- MEGA.docx | 20007 | SMB | 2020-03-16 | DBA | CS | Sofivo | Mega | Supplier Dysfonctionning |  |  | CV1910-0033 | ED | Ground welded bolt missing on ED stack | Cust. Sce | After sales process | Purchase | Material / Matière |  | MEGA |  | NO |  |  | 2020-06-16 | 2020-06-02 | YES |  |  |  |  | N/A | 570 | 0 | 570 |  | A faire 12/21 |  | 20007 Sofivo | 20007 Sofivo : Ground welded bolt missing on ED stack
R:\QA-NVA IB\CAP\20008 CJ P6 S parts welding issue.docm | 20008 | NVSA | 2020-03-23 | SUXI | IER | CJ P6 | USACO | Supplier Dysfonctionning |  | 2084 | 14930 | SSMB | Spare parts welding crack | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | SUXI | 2020-03-18 | 2020-06-23 | 2020-05-22 | YES |  |  |  |  | N/A | 2327 | 0 | 2327 |  |  |  | 20008 CJ P6 | 20008 CJ P6 : Spare parts welding crack
R:\QA-NVA IB\CAP\20009 Shuangqiao10 membrane type issue.docx | 20009 | NVSA | 2020-04-15 | EGU | IER | Shuangqiao | CTI | Internal Anomaly |  | 2082 | 14552 | SSMB | Membrane quantity and type | Cust. Sce | Purchase | Quotation | Method / Méthode |  |  |  | YES | EGU | 2020-03-20 | 2020-07-15 | 2020-04-27 | YES |  |  |  |  | N/A | 2163 | 107150 | 109313 |  |  |  | 20009 Shuangqiao | 20009 Shuangqiao : Membrane quantity and type
R:\QA-NVA IB\CAP\20010 Fufeng10 gravel quality issue.docm | 20010 | NVSA | 2020-04-27 | SUXI | IER | Fufeng | Kebao | Supplier Dysfonctionning |  | 2076 | 14478 | SSMB | Gravel quality issue | SYSTEMS | I&R process | Purchase | Material / Matière |  |  |  | YES | SUXI | 2020-04-26 | 2020-07-27 | 2020-06-03 | YES |  |  |  |  | N/A | 2237 | 2174 | 4411 |  |  |  | 20010 Fufeng | 20010 Fufeng : Gravel quality issue
R:\QA-NVA IB\CAP\20011 front piping budget for small columns issue.docm | 20011 | NVSA | 2020-04-30 | SUXI | IER | CITIC |  | Internal Anomaly |  | 2088 | 14363 | SSMB | Front piping budget for small column is not enough | SYSTEMS | I&R process | Quotation | Method / Méthode |  |  |  | NO |  |  | 2020-07-30 | 2020-06-02 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 20011 CITIC | 20011 CITIC : Front piping budget for small column is not enough
R:\QA-NVA IB\CAP\20012 Fufeng10 complain for gravel issue.docm | 20012 | NVSA | 2020-05-08 | SUXI | IER | Fufeng | Kebao | Claim |  | 2076 | 14478 | SSMB | Gravel quality issue need be solved | SYSTEMS | I&R process | Start up | Method / Méthode |  |  |  | NO |  |  | 2020-08-08 | 2020-06-03 | YES |  | 2020-05-08 | 2020-06-30 | 2020-06-03 | YES | 0 | 0 | 0 |  |  |  | 20012 Fufeng | 20012 Fufeng : Gravel quality issue need be solved
R:\QA-NVA IB\CAP\20013 Cargill Zest PP fixation plate machining dimensions issue.docm | 20013 | NVSA | 2020-05-19 | WWE | IER | Cargill Zest | WUXI RUNJIA | Supplier Dysfonctionning |  | 2087 | 13086 | IEX | PP fixation plate machining dimensions is wrong | SYSTEMS | I&R process |  | Material / Matière |  |  |  | NO |  |  | 2020-08-19 | 2020-06-05 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 20013 Cargill Zest | 20013 Cargill Zest : PP fixation plate machining dimensions is wrong
CAP_EMISES 2020\20014 CKD Module K01\20014 CKD module K01.docx | 20014 | SMB | 2020-05-28 | CPI | CS | CKD | Grayel | Claim |  |  | CV-1910-0104 | UF | Wrong sizes of K01 module | Cust. Sce | After sales process | Purchase | Material / Matière |  | Grayel |  | YES | CPI | 2020-06-02 | 2020-08-28 | 2020-07-08 | YES |  | 2020-06-02 | 2020-08-31 | 2020-07-08 | YES | 3126 | 0 | 3126 | YES | 2020-11-13 |  | 20014 CKD | 20014 CKD : Wrong sizes of K01 module
R:\QA-NVA IB\CAP\20015 Huakang 2 PP Support issue.docx | 20015 | NVSA | 2020-06-16 | EGU | IER | Huakang | Runjia | Internal Anomaly |  | 2085 | 15333 | SSMB | Wrong size of PP support | SYSTEMS | I&R process | Meca Design | Manpower / Main d'œuvre |  |  |  | YES | EGU | 2020-06-16 | 2020-09-16 | 2020-09-10 | YES |  |  |  |  | N/A | 292 | 555 | 847 |  |  |  | 20015 Huakang | 20015 Huakang : Wrong size of PP support
R:\QA-NVA IB\CAP\20016 CJ GMP3 PP-FRP pipe broken issue.docm | 20016 | NVSA | 2020-06-17 | SUXI | IER | CJ Liaocheng GMP3 | Plasticon | Supplier Dysfonctionning |  | 2077 | 13825 | SSMB | PP-FRP pipe is broken issue | SYSTEMS | I&R process |  | Material / Matière |  |  |  | YES | SUXI | 2020-06-17 | 2020-09-17 | 2020-11-16 | NO |  |  |  |  | N/A | 973 | 0 | 973 |  |  |  | 20016 CJ Liaocheng GMP3 | 20016 CJ Liaocheng GMP3 : PP-FRP pipe is broken issue
CAP_EMISES 2020\20017 Prolactal\20017 Prolactal.docx | 20017 | SMB | 2020-06-26 | MAB | Sales | Prolactal | Masoneilan | Claim |  |  | CV-2002-0031 |  | Delivered valves damaged | Cust. Sce | After sales process | Purchase | Material / Matière |  |  |  | YES | DBA | 2020-06-29 | 2020-09-26 | 2020-09-11 | YES | 2020-06-25 | 2020-06-26 | 2020-09-30 | 2020-09-11 | YES | 380 | 0 | 380 |  | A faire 12/21 |  | 20017 Prolactal | 20017 Prolactal : Delivered valves damaged
CAP_EMISES 2020\20018 Cargill\20018 Cargill Boz.docx | 20018 | SMB | 2020-07-17 | ENA | CS | Cargill Boz | CompositeVec | Internal Anomaly |  |  | CS3197 |  | Baskets mixed up during pre-mounting | Cust. Sce | After sales process | Pre-Mouting | Management | 8D-KT |  |  | YES | ENA | 2020-07-23 | 2020-10-17 | 2020-10-07 | YES |  |  |  |  | N/A | 276 | 3325 | 3601 |  | A faire 12/21 |  | 20018 Cargill Boz | 20018 Cargill Boz : Baskets mixed up during pre-mounting
\\srvshafs01\shares\Public\Quality\archieve\QA-NVA IB\CAP\Closed CAP\20019 Mipeng NF housing leakage issue-20210325-close.docm | 20019 | NVSA | 2020-08-03 | SUXI | IER | MIPENG | ROPV | Claim |  | 2059 | 13052 | NF | NF housing leakage | SYSTEMS | I&R process | Start up | Material / Matière |  |  |  | YES | DWA | 2020-08-31 | 2020-11-03 | 2021-03-25 | NO | 2020-07-13 |  | 2020-11-30 | 2021-03-25 | NO | 2336 | 1067 | 3403 |  | A faire 04/21 |  | 20019 MIPENG | 20019 MIPENG : NF housing leakage
CAP_EMISES 2020\20020 BENEO Oreye\20020 BENEO Oreye.docx | 20020 | SMB | 2020-10-05 | CJA | CS | BENEO Oreye |  | Internal Anomaly | X |  | CV-1912-0072 | IEX | Resins labeling error | Cust. Sce | After sales process | Labelling | Manpower / Main d'œuvre | 8D-KT |  |  | YES | EWI | 2020-10-07 | 2021-01-05 | 2020-12-16 | YES |  |  |  |  | YES | 236 | 0 | 236 |  | A faire 12/21 |  | 20020 BENEO Oreye | 20020 BENEO Oreye : Resins labeling error
CAP_EMISES 2020\20021 PT SUJ dédouanement\20021 PT SUJ dédouanement.docx | 20021 | SMB | 2020-10-05 | MGL | CS | PT SUJ |  | Internal Anomaly |  | CS3243 | 16420 |  | Incorrect customs values on invoices | Cust. Sce | After sales process | Shipment | Method / Méthode | 8D-KT |  |  | YES | MGL | 2020-10-07 | 2021-01-05 | 2020-12-22 | YES |  |  |  |  | N/A | 567 | 0 | 567 |  | A faire 12/21 |  | 20021 PT SUJ | 20021 PT SUJ : Incorrect customs values on invoices
CAP_EMISES 2020\20022 Pilotage Laredo-Colonne IEX\20022 pilotage Laredo - Colonne IEX.docx | 20022 | SMB | 2020-10-07 | LRD | R&D | Manuelita Laredo pilotage |  | Safety |  | EN3241 |  | IEX | Resin projection IEX pilot | R&D | PPD Process | Piloting | Method / Méthode | 8D-KT |  |  | YES | HOS | 2020-10-13 | 2021-01-07 | 2020-12-16 | YES |  |  |  |  | N/A | 567 | 0 | 567 |  | A faire 12/21 |  | 20022 Manuelita Laredo pilotage | 20022 Manuelita Laredo pilotage : Resin projection IEX pilot
R:\archieve\QA-NVA IB\CAP\Closed CAP\21001 NF housing leakage issue CLOSE 210514.docx | 21001 | NVSA | 2021-01-07 | EGU | IER | Huaqiao |  | Prevent / improve |  | 2056 | 12996 | NF | NF housing leakage | SYSTEMS | I&R process | Start up | Equipment / Matériel |  | First Line |  | YES | EGU | 2020-12-20 | 2021-04-07 | 2021-05-14 | NO | 2021-02-06 | 2021-02-06 | 2021-04-30 | 2021-05-12 | N/A | 3971.94 |  | 3971.94 |  | A faire 12/21 |  | 21001 Huaqiao | 21001 Huaqiao : NF housing leakage
CAP_EMISES 2021\21002 CAPUA sortie effluents\21002 CAPUA sortie effluent.docx | 21002 | SMB | 2021-01-11 | ABN | IER | CAPUA |  | Prevent / improve |  | CS3233 | 16162 | MF | Effluent to be connected to customer sewers | SYSTEMS | I&R process | Commissioning | Method / Méthode |  |  |  | YES | SOV | 2021-01-14 | 2021-04-11 | 2021-03-26 | YES |  |  |  |  | N/A | 279 |  | 279 | YES | 2021-10-26 |  | 21002 CAPUA | 21002 CAPUA : Effluent to be connected to customer sewers
CAP_EMISES 2021\21003 GOI étiquetage résine\21003 GOI Erreur étiquetage.docx | 21003 | SMB | 2021-01-15 | CJA | CS | GOI | Bollore | Claim | X |  | CV-2005-0051 | IEX | Resins labeling error | Cust. Sce | After sales process | Logistic | Material / Matière |  | Bolloré |  | YES | NPA | 2021-01-19 | 2021-04-15 | 2021-04-29 | NO | 2021-01-13 | 2021-01-18 | 2021-05-30 | 2021-04-29 | YES | 1018 | 1540 | 2558 | NO | 2021-08-26 | 21022 | 21003 GOI | 21003 GOI : Resins labeling error
CAP_EMISES 2021\21004 BENEO Oreye\21004 BENO OREYE.docx | 21004 | SMB | 2021-02-01 | CJA | CS | BENEO Oreye | Bollore | Supplier Dysfonctionning |  |  | CV-1912-0072 | IEX | Forgotten pallett, not delivered | Cust. Sce | After sales process | Logistic | Material / Matière |  | Bolloré |  | NO |  |  | 2021-05-01 | 2021-04-22 | YES |  |  |  |  | N/A | 95 | 0 | 95 | YES | 2022-10-26 |  | 21004 BENEO Oreye | 21004 BENEO Oreye : Forgotten pallett, not delivered
CAP_EMISES 2021\21005 Beneo KSB\21005 Bénéo-KSB retard livraison .docx | 21005 | SMB | 2021-02-08 | JNJ | IER | BENEO Chili | KSB | Supplier Dysfonctionning |  | 2066 | 13829 | CPL | Late delivery of the centrifugal pumps order | SYSTEMS | Purchase | Delivery | Material / Matière |  | KSB |  | NO |  |  | 2021-05-08 | 2021-04-19 | YES |  |  |  |  | N/A | 1318 | 0 | 1318 |  | NA | Black listé pas de nvelle cde | 21005 BENEO Chili | 21005 BENEO Chili : Late delivery of the centrifugal pumps order
\\srvshafs01\shares\Public\Quality\archieve\QA-NVA IB\CAP\Closed CAP\21006 Cargill Mounting issue of internal box.docm | 21006 | NVSA | 2021-02-09 | KYU | QC | Cargill | Gree | Supplier Dysfonctionning |  | CS3253 | 15842 | IEX | Mounting issue of internal box | SYSTEMS | I&R process | Pre-Mouting | Material / Matière |  | GREE |  | YES | KYU | 2021-02-09 | 2021-05-09 | 2021-04-27 | YES |  |  |  |  | N/A | 980 |  | 980 |  | A faire 09/21 |  | 21006 Cargill | 21006 Cargill : Mounting issue of internal box
CAP_EMISES 2021\21007 HSN-Tetrapak\21007 HSN-Tetrapak.docx | 21007 | SMB | 2021-02-11 | ENA | CS | HSN-Tetrapak |  | Internal Anomaly |  |  | CV-2101-0037 | ED | Order delivery error | Cust. Sce | After sales process | Logistic | Manpower / Main d'œuvre |  |  |  | YES | CJA | 2021-02-23 | 2021-05-11 | 2021-03-23 | YES |  |  |  |  | N/A | 285 | 80 | 365 | YES | 2022-10-26 |  | 21007 HSN-Tetrapak | 21007 HSN-Tetrapak : Order delivery error
CAP_EMISES 2021\21008 Polypeptide US\21008 pb création projet comptable US sur ISIS.docx | 21008 | SMB | 2021-03-02 | SGU | CS | Polypeptides US |  | Internal Anomaly |  | AJO-0386 | 16977 |  | Creation of US accounting project on ISIS | Cust. Sce | After sales process | Pilot | Method / Méthode |  |  |  | YES | SGU | 2021-03-05 | 2021-06-02 | 2021-04-29 | YES |  |  |  |  | N/A | 570 | 0 | 570 | YES | 2022-11-09 |  | 21008 Polypeptides US | 21008 Polypeptides US : Creation of US accounting project on ISIS
CAP_EMISES 2021\21009 Tereos -sight glass\21009 Tereos_Sight glass.docx | 21009 | SMB | 2021-03-02 | CDV | IER | Tereos Connantres | Gree / SPA | Supplier Dysfonctionning |  | CS3219 | 15771 | IEX | Spare sightglass missing and bad quality for sightglass gaskets | Cust. Sce | After sales process | Revamping | Material / Matière |  |  |  | YES | SOV | 2021-03-02 | 2021-06-02 | 2021-05-19 | YES |  |  |  |  | N/A | 380 | 1232 | 1612 | YES | 2022-10-26 |  | 21009 Tereos Connantres | 21009 Tereos Connantres : Spare sightglass missing and bad quality for sightglass gaskets
CAP_EMISES 2021\21010 Tereos -perte de charge\21010 TEREOS_perte de charge DK.docx | 21010 | SMB | 2021-03-02 | SGU | CS | Tereos Connantres |  | Internal Anomaly |  | CS3219 | 15771 | IEX | High pressure drop in production | Cust. Sce | After sales process | Revamping | Material / Matière |  |  |  | YES | DBA | 2021-01-06 | 2021-06-02 | 2021-05-27 | YES |  |  |  |  | N/A | 5225 | 30765 | 35990 | YES | 2022-11-14 | après nvelle campagne | 21010 Tereos Connantres | 21010 Tereos Connantres : High pressure drop in production
CAP_EMISES 2021\21011 Praj-fuite module NF\21011 Praj-fuite module NF.docx | 21011 | SMB | 2021-03-15 | PDU | R&D | PRAJ |  | Safety |  | EN3274 | 2020-030 | NF | Product leakage, high pressure | R&D | PPD Process | Piloting | Equipment / Matériel | 8D-KT |  |  | YES | HOS | 2021-03-19 | 2021-06-15 | 2021-08-30 | NO |  |  |  |  | N/A | 950 | 140 | 1090 |  | A faire 12/23 |  | 21011 PRAJ | 21011 PRAJ : Product leakage, high pressure
CAP_EMISES 2021\21012 Açucareira Quatá - CUF\21012 Açucareira Quatá-CUF.docx | 21012 | SMB | 2021-04-23 | AAM | CS | Açucareira Quatá |  | Internal Anomaly |  |  | CV-2101-0014 | MF | Exportation certificate unsend to the client on time | Cust. Sce | After sales process | Offer quotation | Method / Méthode |  |  |  | YES | NPA | 2021-04-28 | 2021-07-23 | 2021-07-06 | YES |  |  |  |  | N/A | 570 | 0 | 570 | YES | 2022-11-08 |  | 21012 Açucareira Quatá | 21012 Açucareira Quatá : Exportation certificate unsend to the client on time
CAP_EMISES 2021\21013 Cevital- licence exportation\21013 Cevital - licence exportation.docx | 21013 | SMB | 2021-05-05 | SSI | ADV | Cevital |  | Internal Anomaly |  |  | CV-2011-0059 | NF | Export licence not request | Cust. Sce | After sales process | Expedition | Management | 8D-KT |  |  | YES | NPA | 2021-05-20 | 2021-08-05 | 2021-07-20 | YES |  |  |  |  | N/A | 190 | 0 | 190 | YES | 2022-11-08 |  | 21013 Cevital | 21013 Cevital : Export licence not request
CAP_EMISES 2021\21014 Savola-Purolite\21014 Savola-Résine Purolite.docx | 21014 | SMB | 2021-05-07 | CJA | CS | Savola | Purolite | Supplier Dysfonctionning |  | 2105 | 15099 |  | Resin delivery in non neutral Big Bag | Cust. Sce | After sales process | Labelling | Material / Matière |  |  |  | NO |  |  | 2021-08-07 | 2021-07-27 | YES |  |  |  |  | N/A | 48 | 0 | 48 | YES | 2022-10-26 |  | 21014 Savola | 21014 Savola : Resin delivery in non neutral Big Bag
CAP_EMISES 2021\21015 Nutribio-Suez\21015 NUTRIBIO-Suez.docx | 21015 | SMB | 2021-05-07 | CJA | CS | Nutribio | Suez | Supplier Dysfonctionning |  |  | CV-2101-0062 | NF | Late delivery NF membranes | Cust. Sce | After sales process | Purchase | Material / Matière |  |  |  | NO |  |  | 2021-08-07 | 2021-07-12 | YES |  |  |  |  | N/A | 0 | 700 | 700 | YES | 2022-10-26 |  | 21015 Nutribio | 21015 Nutribio : Late delivery NF membranes
CAP_EMISES 2021\21016 Cargill-SPA\21016 Cargill SPA column rust.docx | 21016 | SMB | 2021-06-02 | ABN | IER | Cargill Butterfly | SPA | Supplier Dysfonctionning |  | 2083 | 13900 | IEX | Rust on IEX columns | SYSTEMS | I&R process | Commissioning | Material / Matière |  |  |  | YES | ABN/KYU | 2021-06-25 | 2021-09-02 | 2021-09-02 | YES |  |  |  |  | N/A | 465 | 0 | 465 |  | A faire 12/23 | à la fin des projets Cargill | 21016 Cargill Butterfly | 21016 Cargill Butterfly : Rust on IEX columns
CAP_EMISES 2021\21017 Tereos Nesle- mbre NF\21017 TEREOS Nesle - mbre NF.docx | 21017 | SMB | 2021-06-04 | MGL | CS | TEREOS NESLE | SUEZ | Claim | X |  | CV-2012-0009 | NF | NF mbre performance out of specification at start up | Cust. Sce | After sales process | Start up | Material / Matière |  | SUEZ |  | YES | MGL | 2021-06-07 | 2021-09-04 | 2021-10-28 | NO | 2021-05-31 | 2021-06-04 | 2021-10-31 | 2021-10-28 | YES | 282 | 0 | 282 | NO | 2022-01-19 | CAP22001 | 21017 TEREOS NESLE | 21017 TEREOS NESLE : NF mbre performance out of specification at start up
CAP_EMISES 2021\21018 Sucro - DOW resin order\21018 Sucro-resin order.docx | 21018 | SMB | 2021-06-07 | ABN | IER | Sucro | DOW US | Supplier Dysfonctionning |  | 2113 | 16807 | IEX | Resin order not received by Dow | SYSTEMS | Purchase | Acknowledgment of receipt | Method / Méthode |  |  |  | YES | ABN | 2021-06-09 | 2021-09-07 | 2021-09-02 | YES |  |  |  |  | N/A | 282 | 0 | 282 | YES | 2022-11-09 |  | 21018 Sucro | 21018 Sucro : Resin order not received by Dow
R:\archieve\QA-NVA IB\CAP\Closed CAP\21019 Jindan wrong internal diameter of PPH+FRP pipe.docx | 21019 | NVSA | 2021-06-15 | MYA | IER | Jindan | Tecofi/Plasticon | Supplier Dysfonctionning |  | 2108 | 16789 | IEX | wrong internal chord length of valve disc | SYSTEMS | I&R process | Pre-Mouting | Material / Matière |  |  |  | YES | SZH | 2021-06-13 | 2021-09-15 | 2021-06-15 | YES |  |  |  |  | N/A | 182.5 | 0 | 182.5 |  |  |  | 21019 Jindan | 21019 Jindan : wrong internal chord length of valve disc
R:\archieve\QA-NVA IB\CAP\21020 Cargill MicroBA transportation & packing issue.docx | 21020 | NVSA | 2021-07-12 | KYU | IER | Cargill MicroBA | Ziyou | Claim |  | 2101 | 16382 | IEX | packing & saddles and lifting issue | SYSTEMS | I&R process | Logistic | Method / Méthode |  |  |  | YES | KYU | 2021-07-11 | 2021-10-12 | 2021-09-27 | YES | 2021-06-28 | 2021-06-29 | 2021-12-31 | 2021-09-27 | YES | 365 |  | 365 |  |  |  | 21020 Cargill MicroBA | 21020 Cargill MicroBA : packing & saddles and lifting issue
CAP_EMISES 2021\21021 Cargill Haubourdin\21021 Cargill Haubourdin joints EPDM-ébonite.docx | 21021 | SMB | 2021-08-24 | MGL | CS | Cargill Haubourdin | Gree SPA | Claim |  | CS3253 | 15842 | IEX | Resin leakage : EPDM gasket pb, rubber lining pb | Cust. Sce | After sales process | Start up | Material / Matière |  |  |  | YES | NPA | 2021-08-25 | 2021-11-24 | 2023-12-08 | NO | 2021-08-20 | 2021-08-26 | 2022-06-30 | 2023-12-08 | NO | 53279 | 99041 | 152320 |  |  |  | 21021 Cargill Haubourdin | 21021 Cargill Haubourdin : Resin leakage : EPDM gasket pb, rubber lining pb
CAP_EMISES 2021\21022 Hochdorf Swiss Nutrition AG\21022 Hochdorf Swiss Nutrition-démarquage résine.docx | 21022 | SMB | 2021-08-25 | MGL | CS | Hochdorf Swiss Nutrition AG | Bollore | Supplier Dysfonctionning | X |  | CVS-2105-0023 | IEX | No resins relabelling by our Logistic Supplier | Cust. Sce | After sales process | Logistic | Material / Matière |  | Bolloré |  | NO |  |  | 2021-11-25 | 2021-11-02 | YES |  |  |  |  | N/A | 190 | 0 | 190 | YES | 2022-10-26 |  | 21022 Hochdorf Swiss Nutrition AG | 21022 Hochdorf Swiss Nutrition AG : No resins relabelling by our Logistic Supplier
| 21023 | NVSA | 2021-09-06 | MSU | IER | Fufeng Zhalantun |  | Internal Anomaly |  | 2007 | 11179 | MF | Financial unbalance caused by closed project purchase | SYSTEMS | purchase |  | Management |  |  |  | NO | MSU |  | 2021-12-06 | CANCELLED | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 21023 Fufeng Zhalantun | 21023 Fufeng Zhalantun : Financial unbalance caused by closed project purchase
CAP_EMISES 2021\21024 Fufneg Longjiang\21024-Fufeng Longjiang Membrane breakage issue CPT MSU.docx | 21024 | NVSA | 2021-09-22 | MYU | ADV | Fufeng Longjiang | CTI | Claim |  | 75 | 2253 | MF | membrane breakage issue | Cust. Sce | After sales process | Start up | Material / Matière |  | CTI |  | YES | MYU | 2021-09-20 | 2021-12-22 | 2021-12-30 | NO | 2021-09-18 |  | 30/03/2022 | 2021-12-30 | YES | 2008 | 32250 | 34258 |  |  |  | 21024 Fufeng Longjiang | 21024 Fufeng Longjiang : membrane breakage issue
CAP_EMISES 2021\21025 CEVITAL\21025 CEVITAL origine résines EUR1.docx | 21025 | SMB | 2021-09-27 | NPA | CS | Cevital | Purolite | Internal Anomaly |  |  | CV-2011-0059 | Decolo | European origin goods | Cust. Sce | After sales process | Purchase | Manpower / Main d'œuvre |  |  |  | NO |  |  | 2021-12-27 | 2022-12-07 | NO |  |  |  |  | N/A | 1425 | 16388 | 17813 | YES | 2023-11-06 |  | 21025 Cevital | 21025 Cevital : European origin goods
CAP_EMISES 2021\21026 21027 Bonumose\21026 Bonumose-Heating system unit.docx | 21026 | SMB | 2021-09-28 | RDA | IER | Bonumose |  | Internal Anomaly |  | 2116 | 16253 | CPL | Extra cost for heating system | SYSTEMS | I&R process | CPL quotation | Method / Méthode |  |  |  | YES | RDA | 2021-10-05 | 2021-12-28 | 2021-12-03 | YES |  |  |  |  | N/A | 0 | 200261.5 | 200261.5 | YES | 2023-11-10 |  | 21026 Bonumose | 21026 Bonumose : Extra cost for heating system
CAP_EMISES 2021\21026 21027 Bonumose\21027 Bonumose-Ultrafiltration unit.docx | 21027 | SMB | 2021-09-28 | RDA | IER | Bonumose |  | Internal Anomaly |  | 2116 | 16253 | CPL | Extra cost for UF unit | SYSTEMS | I&R process | CPL quotation | Method / Méthode |  |  |  | NO |  |  | 2021-12-28 | 2021-12-03 | YES |  |  |  |  | N/A | 1900 | 40000 | 41900 | YES | 2023-11-10 |  | 21027 Bonumose | 21027 Bonumose : Extra cost for UF unit
CAP_EMISES 2021\21028 Savola\21028 Savola skid NF - tank level.docx | 21028 | SMB | 2021-09-30 | RDA | IER | Savola |  | Internal Anomaly |  | 2105 | 15099 | Decolo | NF Skid level in tank and counterpressure | SYSTEMS | I&R process | Process design | Method / Méthode |  |  |  | YES | ASJ | 2021-10-06 | 2021-12-30 | 2021-12-16 | YES |  |  |  |  | N/A | 1045 | 4050 | 5095 | YES | 2022-11-09 |  | 21028 Savola | 21028 Savola : NF Skid level in tank and counterpressure
CAP_EMISES 2021\21029 Rousselot\21029 Rousselot.docx | 21029 | SMB | 2021-10-04 | CDV | IER | Rousselot | ChaudriConcept | Internal Anomaly |  | CS3286 | 15457 | IEX | SS strainers mounting issue | Cust. Sce | I&R process | Meca design | Method / Méthode |  |  |  | YES | SOV | 2021-10-12 | 2022-01-04 | 2021-12-02 | YES |  |  |  |  | N/A | 285 |  | 285 | YES | 2022-10-26 | voir si new projet rentré | 21029 Rousselot | 21029 Rousselot : SS strainers mounting issue
CAP_EMISES 2021\21030 Inopor\21030 Inopor- Mbres abimées-ébréchées en périphérie.docx | 21030 | SMB | 2021-10-05 | SGU | CS | KIE | INOPOR | Supplier Dysfonctionning |  |  | CAS-2105-0050 | MF | Quality issue on membranes delivery | Cust. Sce | After sales process | Purchase | Material / Matière |  | Inopor |  | YES | SGU | 2021-10-05 | 2022-01-05 | 2021-12-09 | YES |  |  |  |  | N/A | 950 | 500 | 1450 | YES | 2022-11-09 |  | 21030 KIE | 21030 KIE : Quality issue on membranes delivery
CAP_EMISES 2021\21031 Rousselot -anneaux de renfort\21031 Rousselot-position anneaux de renfort.docx | 21031 | SMB | 2021-10-27 | MGL | CS | Rousselot | ChaudriConcept | Supplier Dysfonctionning |  | CS3286 | 15457 | IEX | Bad positioning of reinfortement ring | Cust. Sce | After sales process | FAT | Material / Matière |  | Chaudriconcept |  | YES | SOV | 2021-10-28 | 2022-01-27 | 2022-01-10 | YES |  |  |  |  | N/A | 190 | 0 | 190 | YES | 2022-10-26 | si nouveau projet rousselot | 21031 Rousselot | 21031 Rousselot : Bad positioning of reinfortement ring
CAP_EMISES 2021\21032 Rousselot - raccord entrée-sortie\21032 Rousselot-raccords DIN-SMS.docx | 21032 | SMB | 2021-10-27 | MGL | CS | Rousselot | ChaudriConcept | Claim |  | CS3286 | 15457 | IEX | DIN connection supply instead of SMS | Cust. Sce | After sales process | FAT | Material / Matière |  | Chaudriconcept |  | YES | SOV | 2021-10-28 | 2022-01-27 | 2022-01-10 | YES | 2021-10-21 | 2021-10-21 | 2022-01-31 | 2022-01-10 | YES | 285 | 0 | 285 | YES | 2022-10-26 | si nouveau projet rousselot | 21032 Rousselot | 21032 Rousselot : DIN connection supply instead of SMS
CAP_EMISES 2021\21033 SQ- Silex Sibelco\21033 SQ - Silex Sibelco.docx | 21033 | SMB | 2021-11-24 | CJA | CS | SQ-NVS trading | Sibelco | Supplier Dysfonctionning |  |  | CV-2103-0075 |  | Issue of size range gravel | Cust. Sce | After sales process | Purchase | Material / Matière |  | Sibelco |  | NO |  |  | 2022-02-24 | 2022-02-09 | YES |  |  |  |  | N/A | 95 | 12000 | 12095 | YES | 2022-10-26 |  | 21033 SQ-NVS trading | 21033 SQ-NVS trading : Issue of size range gravel
CAP_EMISES 2021\21034 Cargill MicroBA\21034 Cargill MicroBA - Tag plates inversion.docx | 21034 | SMB | 2021-11-25 | LPR | IER | Cargill MicroBA | Gree/SPA | Supplier Dysfonctionning |  | 2101 | 16382 | IEX | Inversion of the columns tags plates | Cust. Sce | I&R process | FAT | Material / Matière |  |  |  | YES | KYU | 2021-11-30 | 2022-02-25 | 2022-01-17 | YES |  |  |  |  | N/A | 984 | 2075 | 3059 |  | A faire 12/23 |  | 21034 Cargill MicroBA | 21034 Cargill MicroBA : Inversion of the columns tags plates
CAP_EMISES 2021\21035 Etihad-Aqua Com\21035 Etihad-TP Aqua Com.docx | 21035 | SMB | 2021-12-06 | MGL | CS | Etihad | Aqua Com | Supplier Dysfonctionning |  |  | CV-1907-0015 | NF | Leakage, pressure vessels coating quality problem | Cust. Sce | After sales process | Process design | Material / Matière |  | Aqua Com |  | YES | NPA | 2021-12-08 | 2022-03-06 | 2022-03-15 | NO |  |  |  |  | N/A | 579 | 3637.39 | 4216.39 |  | A faire 12/23 |  | 21035 Etihad | 21035 Etihad : Leakage, pressure vessels coating quality problem
CAP_EMISES 2021\21036 Cargill MicroBA-ABB\21036 Cargill MicroBA_ABB.docx | 21036 | SMB | 2021-12-07 | SML | IER | Cargill MicroBA | ABB | Supplier Dysfonctionning |  | 2101 | 16382 | IEX | Reference error of the supplied pressure sensors | SYSTEMS | Purchase | commissioning | Material / Matière |  | ABB |  | NO |  |  | 2022-03-07 | 2022-03-03 | YES |  |  |  |  | N/A | 1045 | 0 | 1045 | YES | 2022-11-08 |  | 21036 Cargill MicroBA | 21036 Cargill MicroBA : Reference error of the supplied pressure sensors
R:\archieve\QA-NVA IB\CAP\21037-Dysfunction of supplier Guanxing.docx | 21037 | NVSA | 2021-12-09 | EWA | IER | Lvyuan | Guanxing | Supplier Dysfonctionning |  | 10 | 16017 | SSMB | Dysfunction of supplier Guanxing | Cust. Sce | I&R process | commissioning | Material / Matière |  | Guanxing |  | YES | EWA | 2021-12-09 | 2022-03-09 | 2022-03-08 | YES |  |  |  |  | N/A | 500 | 0 | 500 |  |  |  | 21037 Lvyuan | 21037 Lvyuan : Dysfunction of supplier Guanxing
CAP_EMISES 2021\21038 Gambro- CTI erreur impression cut off membrane\21038 Gambro - CTI erreur impression cut off membrane KERASEP.docx | 21038 | SMB | 2021-12-23 | SGU | CS | Gambro | CTI | Supplier Dysfonctionning |  |  | CVS-2109-0013 | UF | Cut off labeling error on Kerasep mbre | Cust. Sce | After sales process | Purchase | Material / Matière |  | CTI |  | NO |  |  | 2022-03-23 | 2022-02-10 | YES |  |  |  |  | N/A | 285 | 0 | 285 | YES | 2022-11-09 |  | 21038 Gambro | 21038 Gambro : Cut off labeling error on Kerasep mbre
CAP_EMISES 2022\22001 Teréos - Suez\22001 TEREOS Nesle - mbre NF.docx | 22001 | SMB | 2022-01-17 | MGL | CS | TEREOS NESLE | SUEZ | Claim | X |  | CV-2012-0011 | NF | NF mbre performance out of specification at start up | Cust. Sce | After sales process | Start up | Material / Matière |  | SUEZ |  | YES | MGL | 2022-01-19 | 2022-04-17 | 2022-03-25 | YES | 2022-01-13 | 2022-01-14 | 2022-04-30 | 2022-03-25 | YES | 190 | 0 | 190 | YES | 2022-10-26 |  | 22001 TEREOS NESLE | 22001 TEREOS NESLE : NF mbre performance out of specification at start up
CAP_EMISES 2022\22002 SQ - Polarimeter\22002 SQ 10 - polarimeter.docx | 22002 | SMB | 2022-01-19 | CPR | Innov | SQ10 |  | Internal Anomaly |  | 2082 | 14552 | SSMB | Lost polarimeter | SYSTEMS | I&R process | Shipment | Method / Méthode |  |  |  | YES | GSU | 2022-01-21 | 2022-04-19 | 2022-04-19 | YES |  |  |  |  | N/A | 2874 | 20437 | 23311 |  | A faire 12/23 |  | 22002 SQ10 | 22002 SQ10 : Lost polarimeter
S:\archieve\QA-NVA IB\CAP\Closed CAP | 22003 | NVSA | 2022-01-24 | KYU | IER | SQ13 | SPA | Supplier Dysfonctionning |  | 2097 | 16108 | SSMB | Name plates misplaced | SYSTEMS | I&R process | commissioning | Material / Matière |  | SPA |  | YES | KYU | 2022-01-17 | 2022-04-24 | 2022-04-22 | YES | 2021-12-23 |  |  |  | N/A | 1250 | 243 | 1493 |  |  |  | 22003 SQ13 | 22003 SQ13 : Name plates misplaced
S:\archieve\QA-NVA IB\CAP\Closed CAP | 22004 | NVSA | 2022-01-24 | KYU | IER | SQ12 | Guanxing | Supplier Dysfonctionning |  | 2092 | 15490/16979 | SSMB/IEX | Column rods broken or missing | SYSTEMS | I&R process | Pre-Mouting | Material / Matière |  | Guanxing & FDS |  | YES | KYU | 2022-01-03 | 2022-04-24 | 2022-04-22 | YES | 2021-12-26 |  |  |  | N/A | 1250 | 243 | 1493 |  |  |  | 22004 SQ12 | 22004 SQ12 : Column rods broken or missing
CAP_EMISES 2022\22005 Ram Sucre- Composites Vec\22005 RAM SUCRE - buses décolo.docx | 22005 | SMB | 2022-01-25 | MGL | CS | RAM Sucre | Composites Vec | Claim |  |  | CV-1903-0048 | Decolo | Issue of nozzle rod length | Cust. Sce | After sales process | Client's maintenance | Equipment / Matériel |  | Composites Vec |  | YES | MGL | 2022-01-27 | 2022-04-25 | 2022-03-16 | YES | 2022-01-18 | 2022-01-18 | 2022-04-30 | 2022-03-16 | YES | 285 | 40 | 325 | YES | 2022-10-26 |  | 22005 RAM Sucre | 22005 RAM Sucre : Issue of nozzle rod length
CAP_EMISES 2022\22006 Sucro-Bossard\22006 SUCRO-CPU sizing.docx | 22006 | SMB | 2022-02-01 | SML | IER | SUCRO | Bossard | Supplier Dysfonctionning |  | 2113 | 16809 | Decolo | CPU size too small | SYSTEMS | I&R process | AEI design | Material / Matière |  | Bossard |  | NO |  |  | 2022-05-01 | 2022-04-13 | YES |  |  |  |  | N/A | 1143.69 | 0 | 1143.69 |  | A faire 12/23 | voir projet Wuyang | 22006 SUCRO | 22006 SUCRO : CPU size too small
CAP_EMISES 2022\22007 Cristal Union\22007 Cristal Union-FACADE.docx | 22007 | SMB | 2022-02-02 | JNJ | Achat | Cristal Union | STCL | Internal Anomaly |  | 2115 | 16573 | DK NRS | Front piping budget underestimated | SYSTEMS | Order intake | Budget Quotation | Method / Méthode | X |  |  | YES | APS | 2022-02-03 | 2022-05-02 | 2022-04-29 | YES |  |  |  |  | N/A | 1568 | 111540 | 113108 | YES | 2023-11-09 |  | 22007 Cristal Union | 22007 Cristal Union : Front piping budget underestimated
CAP_EMISES 2022\22008 Tessier-casse mbre à réception\22008 Tessier_Membrane cassée à réception.docx | 22008 | SMB | 2022-02-07 | SGU | CS | Tessier | DHL | Claim |  |  | CVS-2111-0007 |  | Broken membranes upon client receipt | Cust. Sce | After sales process | Shipment | Material / Matière |  |  |  | YES | SGU | 2022-02-09 | 2022-05-07 | 2022-05-06 | YES | 2022-01-21 | 2022-01-21 | 2022-05-31 | 2022-05-06 | YES | 784 | 1100 | 1884 | YES | 2022-11-09 |  | 22008 Tessier | 22008 Tessier : Broken membranes upon client receipt
S:\archieve\QA-NVA IB\CAP\Closed CAP | 22009 | NVSA | 2022-02-11 | MYU | CS | DYG | Inopor | Supplier Dysfonctionning |  |  | 75.2269 | MF | Ends of alpha mbre worn out after 3 months usage | Cust. Sce | After sales process | Purchase | Material / Matière |  |  |  | YES | MYU | 2021-12-31 | 2022-05-11 | 2022-05-10 | YES |  |  |  |  | N/A | 1500 | 694 | 2194 |  |  |  | 22009 DYG | 22009 DYG : Ends of alpha mbre worn out after 3 months usage
CAP_EMISES 2022\22010 Fuite appareil Kjeldahl\22010 Fuite appareil Kjedahl.docx | 22010 | SMB | 2022-02-15 | ADP | R&D | Abbott |  | Safety |  | AJO-0409 |  |  | Water leak | R&D | PPD Process | Analysis | Equipment / Matériel |  |  |  | YES | HOS | 2022-02-17 | 2022-05-15 | 2022-04-19 | YES |  |  |  |  | N/A | 588 | 200 | 788 |  | A faire 12/23 |  | 22010 Abbott | 22010 Abbott : Water leak
CAP_EMISES 2022\22011 Sucro - incohérence PID-3D\22011 SUCRO_3D Skid NF not updated.docx | 22011 | SMB | 2022-03-02 | TCC | IER | SUCRO | ZIYOU | Internal Anomaly |  | 2113 | 16809 | NF | Inconsistences between PID and 3D Model of NF Skid | SYSTEMS | I&R process | Process design | Method / Méthode |  |  |  | YES | JGO | 2022-03-03 | 2022-06-02 | 2022-05-17 | YES |  |  |  |  | N/A | 2994 | 0 | 2994 |  | A faire 12/23 |  | 22011 SUCRO | 22011 SUCRO : Inconsistences between PID and 3D Model of NF Skid
CAP_EMISES 2022\22012 Beneo Oreyes- InaceInox\22012 Beneo Oreye - InaceInox.docx | 22012 | SMB | 2022-03-02 | TPI | CS | Beneo Oreye | InaceInox | Supplier Dysfonctionning |  | CS3290 | 17223 | IEX | Reliability of supplier (deadlines and quality) | Cust. Sce | After sales process | Revamping | Material / Matière |  |  |  | NO |  |  | 2022-06-02 | 2022-05-17 | YES |  |  |  |  | N/A | 490 | 0 | 490 |  | A faire 12/23 |  | 22012 Beneo Oreye | 22012 Beneo Oreye : Reliability of supplier (deadlines and quality)
S:\archieve\QA-NVA IB\CAP | 22013 | NVSA | 2022-03-07 | TWI | IER | ENSIGN | SPA | Claim |  |  | 14619 | IEX | Rubber lining cracking | SYSTEMS | I&R process | commissioning | Material / Matière |  |  |  | YES | TWI | 2022-03-07 | 2022-06-07 | 2022-12-16 | NO | 2022-02-17 | 2022-02-17 | 2022-12-31 | 2022-12-16 | YES | 5125 | 32166 | 37291 |  |  |  | 22013 ENSIGN | 22013 ENSIGN : Rubber lining cracking
CAP_EMISES 2022\22014 Parry Sugar\22014 Parry Sugar-liste de colisage.docx | 22014 | SMB | 2022-03-17 | SSI | ADV | Parry Sugar | Welcoop | Claim |  |  | CVS-2201-0011 |  | Wrong packing list | Cust. Sce | After sales process | Logistic | Material / Matière |  |  |  | YES | CJA | 2022-03-21 | 2022-06-17 | 2022-05-02 | YES | 2022-03-09 | 2022-03-11 | 2022-06-30 | 2022-05-02 | YES | 98 | 0 | 98 | YES | 2022-11-09 |  | 22014 Parry Sugar | 22014 Parry Sugar : Wrong packing list
S:\archieve\QA-NVA IB\CAP | 22015 | NVSA | 2022-03-31 | KYU | IER | SUCRO | ZFLZ | Supplier Dysfonctionning |  | 2113 | 16809 |  | FRP sand filter nozzle plate thickness issue | SYSTEMS | I&R process | Pre-Mouting | Material / Matière |  |  |  | YES | KYU | 2022-03-25 | 2022-06-30 | 2022-05-31 | YES |  |  |  |  | N/A | 500 | 0 | 500 |  |  |  | 22015 SUCRO | 22015 SUCRO : FRP sand filter nozzle plate thickness issue
CAP_EMISES 2022\22016 Cargill BOZ-Manholes & davit design\22016 Cargill BOZ-Manholes and davit design.docx | 22016 | SMB | 2022-04-07 | CDV | IER | Cargill BOZ | Gree | Internal Anomaly |  | 2104 | 15841 | IEX | Manholes and davit design | SYSTEMS | I&R process | Meca design | Method / Méthode |  |  |  | YES | JGO | 2022-04-14 | 2022-07-07 | 2022-07-07 | YES |  |  |  |  | N/A | 980 | 21000 | 21980 | YES | 2023-11-07 |  | 22016 Cargill BOZ | 22016 Cargill BOZ : Manholes and davit design
CAP_EMISES 2022\22017 Fuite eau chaude atelier membrane\22017 Deconnexion tuyau eau chaude atelier membrane.docx | 22017 | SMB | 2022-04-07 | SGU | CS | interne | Vinci | Safety |  |  |  |  | Hot water leakage | Cust. Sce | After sales process | mbre assembly | Equipment / Matériel |  |  |  | YES | SGU | 2022-04-12 | 2022-07-07 | 2022-06-20 | YES |  |  |  |  | N/A | 1470 | 0 | 1470 | YES | 2022-11-09 |  | 22017 interne | 22017 interne : Hot water leakage
CAP_EMISES 2022\22018 Savola-doc expédition\22018 Savola-expédition ACID Cargo X.docx | 22018 | SMB | 2022-04-08 | RDA | IER | Savola |  | Internal Anomaly |  | 2105 | 15099 | Decolo | Shipping documents and custom clearance issues | SYSTEMS | Purchase | Shipment | Method / Méthode |  |  |  | YES | CBL | 2022-05-04 | 2022-07-08 | 2022-06-30 | YES |  |  |  |  | N/A | 490 | 0 | 490 | YES | 2023-11-10 |  | 22018 Savola | 22018 Savola : Shipping documents and custom clearance issues
CAP_EMISES 2022\22019 ADM CHAMTOR - Erreur chiffrage tuyauterie\22019 ADM CHAMTOR - Chiffrage budget tuyauterie.docx | 22019 | SMB | 2022-04-12 | LPR | CS | ADM Chamtor | STCL | Internal Anomaly | X | CS3293 | 18076 | SSMB | Piping budget underestimated | Cust. Sce | After sales process | Budget Quotation | Method / Méthode |  |  |  | YES | SOV | 2022-05-03 | 2022-07-12 | 2022-06-20 | YES |  |  |  |  | N/A | 294 | 9500 | 9794 | YES | 2023-11-06 | idem 22007 | 22019 ADM Chamtor | 22019 ADM Chamtor : Piping budget underestimated
CAP_EMISES 2022\22020 Fuite IBC saumure Tredi\22020 Fuite Saumure Trédi.docx | 22020 | SMB | 2022-04-26 | TEB | R&D | TREDI |  | Safety |  | EN-3214 |  |  | Brine IBC leak | R&D | PPD Process | Piloting | Equipment / Matériel |  |  |  | YES | HOS | 2022-05-09 | 2022-07-26 | 2022-06-21 | YES |  |  |  |  | N/A | 294 | 0 | 294 | YES | 2023-11-08 |  | 22020 TREDI | 22020 TREDI : Brine IBC leak
CAP_EMISES 2022\22021 Fuite eau glycolée\22021 Fuite Eau Glycolée.docx | 22021 | SMB | 2022-04-26 | TEB | R&D | Damhert |  | Safety |  | EN-3293 |  | Evapo | Glycol water leak on 7l evapo | R&D | PPD Process | Piloting | Equipment / Matériel |  |  |  | YES | HOS | 2022-05-09 | 2022-07-26 | 2022-06-21 | YES |  |  |  |  | N/A | 490 | 1163 | 1653 | YES | 2023-11-08 |  | 22021 Damhert | 22021 Damhert : Glycol water leak on 7l evapo
CAP_EMISES 2022\22022 CJ Bio\22022 CJ Bio.docx | 22022 | SMB | 2022-05-19 | MGL | CS | CJ Bio |  | Claim |  |  | CVS-2107-0006 | IEX | Automatic by pass cell procedure cIEX | Cust. Sce | After sales process | Upgrade automation | Management / Management |  |  |  | YES | CLE | 2022-05-16 | 2022-08-19 | 2022-08-30 | NO | 2022-05-10 | 2022-05-10 | 2022-08-31 | 2022-08-30 | YES | 2450 | 0 | 2450 |  | A faire 12/23 |  | 22022 CJ Bio | 22022 CJ Bio : Automatic by pass cell procedure cIEX
S:\archieve\QA-NVA IB\CAP | 22023 | NVSA | 2022-05-24 | MYU | CS | BBCA | CTI | Claim |  |  | 75.2331 | MF | Order placing late | Cust. Sce | After sales process | Purchase | Method / Méthode |  |  |  | YES | MYU | 2022-05-06 | 2022-08-24 | 2022-08-23 | YES | 2022-05-16 | 2022-05-16 | 2022-08-31 | 2022-08-23 | YES | 0 | 6595 | 6595 |  |  |  | 22023 BBCA | 22023 BBCA : Order placing late
S:\archieve\QA-NVA IB\CAP | 22024 | NVSA | 2022-05-30 | KYU | IER | SQ12 | Guanxing | Prevent / improve |  | 2092 | 15490 | SSMB | Internal leakage in rubber lining connection piping | SYSTEMS | I&R process | Process design | Method / Méthode |  |  |  | YES | KYU | 2022-05-25 | 2022-08-30 | 2022-08-03 | YES |  |  |  |  | N/A | 1000 | 1667 | 2667 |  |  |  | 22024 SQ12 | 22024 SQ12 : Internal leakage in rubber lining connection piping
S:\archieve\QA-NVA IB\CAP\22025 SQ 10 -Fine particle in gravel of SQ10 SSMB.docx | 22025 | NVSA | 2022-05-30 | MPE | IER | SQ10 | Mingliang | Pdt unconformity |  | 2082 | 14552 | SSMB | Fine particle in gravel of SQ10 SSMB | SYSTEMS | I&R process | commissioning | Material / Matière |  |  |  | YES | MPE | 2022-05-23 | 2022-08-30 | 2022-08-26 | YES |  |  |  |  | N/A | 1500 | 1103 | 2603 |  |  |  | 22025 SQ10 | 22025 SQ10 : Fine particle in gravel of SQ10 SSMB
CAP_EMISES 2022\22026 Bénéo\22026 Beneo - Montage FT sur façades.docx | 22026 | SMB | 2022-06-03 | SML | IER | BENEO Chili |  | Internal Anomaly |  | 2066 | 13829 | CPL | Wrong installation of Flowmeters on front pipings | SYSTEMS | I&R process | AEI Design | Method / Méthode |  |  |  | YES | JGO | 2022-06-07 | 2022-09-03 | 2022-08-24 | YES |  |  |  |  | N/A | 784 | 0 | 784 |  | A faire 12/23 | à la fin du projet | 22026 BENEO Chili | 22026 BENEO Chili : Wrong installation of Flowmeters on front pipings
CAP_EMISES 2022\22027 LEKAI - civil works drawing\22027 LEKAI-Civil works drawing.docx | 22027 | SMB | 2022-06-03 | TCC | IER | LEKAI |  | Claim |  | 2137 | 18080 | SSMB | Layout and Civil work drawings | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | JGO | 2022-06-07 | 2022-09-03 | 2022-07-26 | YES | 2022-05-13 | 2022-05-19 | 2022-09-30 | 2022-07-26 | YES | 588 | 0 | 588 |  | A faire 12/23 |  | 22027 LEKAI | 22027 LEKAI : Layout and Civil work drawings
CAP_EMISES 2022\22028 Kirsanov-envoi Silex\22026 Kirsanov-envoi Silex.docx | 22028 | SMB | 2022-07-18 | LCA | IER | KIRSANOV | Bollore | Internal Anomaly |  | 2107 | 13737 | DK NRS | Forgot to ship the gravel | SYSTEMS | Purchase | Logistic | Method / Méthode |  |  |  | YES | LCA | 2022-07-20 | 2022-10-18 | 2022-10-10 | YES |  |  |  |  | N/A | 490 | 2680 | 3170 | YES | 2023-11-03 |  | 22028 KIRSANOV | 22028 KIRSANOV : Forgot to ship the gravel
CAP_EMISES 2022\22029 Beneo Oreye-Inace Inox\22029 Beneo Oreye-Inace Inox ramification IEX.docx | 22029 | SMB | 2022-07-20 | TPI | CS | Beneo Oreye | InaceInox | Supplier Dysfonctionning |  | CS3291 | 18021 | IEX | Hole diameter error in lower network | Cust. Sce | After sales process | Revamping | Material / Matière |  | Inace Inox |  | NO |  |  | 2022-10-20 | 2022-10-17 | YES |  |  |  |  | N/A | 490 | 0 | 490 |  | A faire 12/23 |  | 22029 Beneo Oreye | 22029 Beneo Oreye : Hole diameter error in lower network
CAP_EMISES 2022\22030 CTI pollution mbre\22030 Pollution membranes KERASEP- CTI.docx | 22030 | SMB | 2022-07-25 | SGU | CS | OLON | CTI | Supplier Dysfonctionning |  |  | CVS-2112-0016 | MF | Pollution on the end of Kerasep membranes | Cust. Sce | After sales process | Purchase | Material / Matière |  | CTI |  | YES | SGU | 2022-07-25 | 2022-10-25 | 2022-10-17 | YES |  |  |  |  | N/A | 6174 | 200 | 6374 | YES | 2023-11-09 |  | 22030 OLON | 22030 OLON : Pollution on the end of Kerasep membranes
CAP_EMISES 2022\22031 Cristal Union - Inace Inox crépines\22031 Cristal Union - crépines inox 10.16573.docx | 22031 | SMB | 2022-07-26 | CDV | IER | Cristal Union | InaceInox | Supplier Dysfonctionning |  | 2115 | 16573 | DK NRS | Defective strainers | SYSTEMS | I&R process | Meca Design | Material / Matière |  |  |  | NO |  |  | 2022-10-26 | 2022-10-10 | YES |  |  |  |  | N/A | 392 | 1936 | 2328 | YES | 2023-11-07 |  | 22031 Cristal Union | 22031 Cristal Union : Defective strainers
| 22032 | NVSA | 2022-08-23 | KYU | IER | SQ21 | FDS | Internal Anomaly |  | 2131 | 18072 | SSMB | Cylinder positioning issue for internal mounting | SYSTEMS | Purchase | Pre-Mouting | Method / Méthode |  | FDS |  | YES | KYU | 2022-08-12 | 2022-11-23 | 2022-09-28 | YES |  |  |  |  | N/A | 1000 |  | 1000 |  |  |  | 22032 SQ21 | 22032 SQ21 : Cylinder positioning issue for internal mounting
CAP_EMISES 2022\22033 Bonumose\22033 Bonumose - Small column design.docx | 22033 | SMB | 2022-08-29 | LPR | IER | Bonumose |  | Prevent / improve |  | 2116 | 16253 | IEX | Difficult access inside small diameter IEX columns | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | JGO | 2022-09-02 | 2022-11-29 | 2022-11-24 | YES |  |  |  |  | N/A | 1274 | 0 | 1274 |  | A faire 12/23 |  | 22033 Bonumose | 22033 Bonumose : Difficult access inside small diameter IEX columns
CAP_EMISES 2022\22034 Bonumose-Silex\22034 Bonumose - Silex.docx | 22034 | SMB | 2022-09-01 | RDA | IER | Bonumose |  | Internal Anomaly | X | 2116 | 16253 | IEX | Gravels not been sent on site before commissioning | SYSTEMS | Purchase | Logistic | Method / Méthode |  |  |  | YES | RDA | 2022-09-07 | 2022-12-01 | 2022-11-29 | YES |  |  |  |  | N/A | 294 | 1500 | 1794 | YES | 2023-11-10 |  | 22034 Bonumose | 22034 Bonumose : Gravels not been sent on site before commissioning
CAP_EMISES 2022\22035 Bénéo-Certificat Etalonnage\22035 Beneo-Certificat étalonnage IN.docx | 22035 | SMB | 2022-09-19 | SML | IER | Beneo Chili | E&H | Supplier Dysfonctionning |  | 2066 | 13829 | CPL | Calibration certificates missing for Instrumentation | SYSTEMS | I&R process | AEI Design | Material / Matière |  | E&H |  | YES | SML | 2022-09-29 | 2022-12-19 | 2022-11-18 | YES |  |  |  |  | N/A | 686 | 0 | 686 |  | A faire 12/23 |  | 22035 Beneo Chili | 22035 Beneo Chili : Calibration certificates missing for Instrumentation
CAP_EMISES 2022\22036 GSK - Etanchement\22036 GSK - étanchement (4).docx | 22036 | SMB | 2022-09-20 | SGU | CS | GSK Hamilton | CTI | Supplier Dysfonctionning |  |  |  | MF/UF | End sealing peeling off inside membrane | Cust. Sce | After sales process | Purchase | Material / Matière |  |  |  | YES | SGU | 2022-09-20 | 2022-12-20 | 2022-12-16 | YES |  |  |  |  | N/A | 784 | 0 | 784 | YES | 2023-11-09 |  | 22036 GSK Hamilton | 22036 GSK Hamilton : End sealing peeling off inside membrane
CAP_EMISES 2022\22037 Cristal union- FT\22037 Cristal Union-Espace insuffisant pour démontage débitmètre.docx | 22037 | SMB | 2022-09-26 | JPL | IER | Cristal Union | STCL | Internal Anomaly |  | 2115 | 16573 | DK NRS | Insufficient space for FT uncabling | SYSTEMS | I&R process | AEI Design | Method / Méthode |  |  |  | YES | JGO | 2022-10-07 | 2022-12-26 | 2022-11-18 | YES |  |  |  |  | N/A | 490 | 0 | 490 | YES | 2023-11-09 |  | 22037 Cristal Union | 22037 Cristal Union : Insufficient space for FT uncabling
CAP_EMISES 2022\22038 Nexira-sonde conductivité\22038 Nexira - Sonde de conductivité.docx | 22038 | SMB | 2022-09-26 | JPL | IER | Nexira | STCL | Internal Anomaly |  | 2126 | 17697 |  | Pb pipe connection diameter for CT installation | SYSTEMS | I&R process | AEI Design | Method / Méthode |  |  |  | YES | SML | 2022-10-07 | 2022-12-26 | 2022-11-30 | YES |  |  |  |  | N/A | 882 | 1500 | 2382 | YES | 2023-11-09 |  | 22038 Nexira | 22038 Nexira : Pb pipe connection diameter for CT installation
CAP_EMISES 2022\22039 HPLC Métrologie\22039 HPLC métrologie.docx | 22039 | SMB | 2022-09-27 | LLR | R&D | Interne | VWR | Pdt unconformity |  | NA | NA | NA | Annual HPLC checking date exceeded | R&D | PPD Process | Metrology | Material / Matière |  | VWR |  | YES | HOS | 2022-09-30 | 2022-12-27 | 2022-12-08 | YES |  |  |  |  | N/A | 784 | 0 | 784 | YES | 2023-11-07 |  | 22039 Interne | 22039 Interne : Annual HPLC checking date exceeded
CAP_EMISES 2022\22040 Sanofi-Etiquette\22040 Sanofi-Etiquette caisse (4).docx | 22040 | SMB | 2022-09-30 | SGU | CS | Sanofi |  | Claim |  |  | CVS-2208-0003 | MF/UF | Missing label on shipping crate | Cust. Sce | After sales process | Shipment | Material / Matière |  |  |  | NO |  |  | 2022-12-30 | 2022-12-08 | YES | 2022-09-19 | 2021-09-21 | 2022-12-30 | 2022-12-08 | YES | 294 | 0 | 294 | YES | 2023-11-09 |  | 22040 Sanofi | 22040 Sanofi : Missing label on shipping crate
CAP_EMISES 2022\22041 Lesaffre - casse membrane transport\22041 Lesaffre-Casse membranes transport.docx | 22041 | SMB | 2022-10-10 | SGU | CS | Lesaffre | INOPOR | Supplier Dysfonctionning |  | 2142 | CVS-2206-0012 | MF/UF | Kerasep Alpha membrane breakage during delivery | Cust. Sce | After sales process | Shipment | Material / Matière |  | Inopor |  | YES | SGU | 2022-10-11 | 2023-01-10 | 2023-01-09 | YES |  |  |  |  | N/A | 784 | 250 | 1034 | YES | 2023-11-09 |  | 22041 Lesaffre | 22041 Lesaffre : Kerasep Alpha membrane breakage during delivery
CAP_EMISES 2022\22042 Commande ISIS-Navision\22042 Transfert commande ISIS-Navision.docx | 22042 | SMB | 2022-10-18 | JNJ | Achat | Interne | IORGA | Internal Anomaly |  | NA | NA | NA | Order transfert from ISIS to Navision | SYSTEMS | Purchase | Order validation | Manpower / Main d'œuvre |  |  |  | YES | PWT | 2022-11-20 | 2023-01-18 | 2023-01-13 | YES |  |  |  |  | N/A | 490 | 0 | 490 | YES | 2023-11-09 |  | 22042 Interne | 22042 Interne : Order transfert from ISIS to Navision
CAP_EMISES 2022\22043 Rousselot-Crépines trop longues\22043 Rousselot- longuer crépines inox.docx | 22043 | SMB | 2022-10-21 | CDV | IER | Rousselot | Andritz | Internal Anomaly |  | 2139 | 17596 | IEX | Strainer mounting issue (too long) | SYSTEMS | I&R process | Meca design | Manpower / Main d'œuvre |  |  |  | NO |  |  | 2023-01-21 | 2023-01-19 | YES |  |  |  |  | N/A | 784 | 4700 | 5484 | YES | 2023-11-07 |  | 22043 Rousselot | 22043 Rousselot : Strainer mounting issue (too long)
| 22044 | NVSA | 2022-10-24 | TWI | IER | SQ21 | FDS | Pdt unconformity |  | 2131 | 18072 | IEX | Installation issue of manhole for IEX column | SYSTEMS | I&R process | Pre-Mouting | Method / Méthode |  |  |  | YES | TWI | 2022-10-18 | 2023-01-24 | 2023-01-09 | YES |  |  |  |  | N/A | 500 |  | 500 |  |  |  | 22044 SQ21 | 22044 SQ21 : Installation issue of manhole for IEX column
CAP_EMISES 2022\22045 Cristal Union- Gonflement résine\22045 Cristal Union Erstein-gonflement résine.docx | 22045 | SMB | 2022-10-26 | DBA | CS | Cristal Union Erstein | Dupont | Supplier Dysfonctionning |  |  | CVS-2112-0016 |  | Abnormal resins swelling | Cust. Sce | After sales process | Purchase | Material / Matière |  | Dupont |  | YES | DBA/LRE | 2022-11-16 | 2023-01-26 | 2023-04-14 | NO |  |  |  |  | N/A | 5160.95 | 0 | 5160.95 |  | A faire 12/23 |  | 22045 Cristal Union Erstein | 22045 Cristal Union Erstein : Abnormal resins swelling
| 22046 | NVSA | 2022-10-28 | KYU | IER | SQ21 | FDS | Claim |  | 2131 | 18072 | IEX | Material and welding issues on IEX front piping | SYSTEMS | I&R process | Pre-Mouting | Material / Matière |  |  |  | YES | TWI | 2022-10-16 | 2023-01-28 | 2022-12-19 | YES | 2022-09-22 | 2022-09-23 | 2022-11-30 | 2022-12-19 | NO | 2500 | 0 | 2500 |  |  |  | 22046 SQ21 | 22046 SQ21 : Material and welding issues on IEX front piping
| 22047 | NVSA | 2022-10-28 | MPE | IER | SQ10 | GREE | Claim |  | 2082 | 14552 | IEX | Lack welding on the vent pipe inside SSMB | SYSTEMS | I&R process | Pre-Mouting | Material / Matière |  |  |  | YES | TWI | 2022-10-19 | 2023-01-28 | 2022-12-16 | YES | 2022-09-27 | 2022-09-28 | 2022-12-19 | 2022-12-16 | YES | 500 |  | 500 |  |  |  | 22047 SQ10 | 22047 SQ10 : Lack welding on the vent pipe inside SSMB
| 22048 | NVSA | 2022-11-21 | ESH | IER | COFCO | LIVIC | Pdt unconformity |  |  | 11608 | IEX | filter not matching | SYSTEMS | I&R process | Pre-Mouting | Method / Méthode |  |  |  | YES | ESH | 2022-11-21 | 2023-02-21 | 2022-12-12 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 22048 COFCO | 22048 COFCO : filter not matching
| 22049 | NVSA | 2022-11-21 | ESH | IER | COFCO | FDS | Pdt unconformity |  |  | 11608 | IEX | different ball valves were mixed | SYSTEMS | I&R process | Pre-Mouting | Method / Méthode |  |  |  | YES | ESH | 2022-11-21 | 2023-02-21 | 2022-11-28 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  |  |  | 22049 COFCO | 22049 COFCO : different ball valves were mixed
| 22050 | NVSA | 2022-11-28 | ESH | IER | Natureworks | SPA | Pdt unconformity |  |  | 16753 | IEX | Rubber lining thickness is lower than the standard | SYSTEMS | I&R process | Pre-Mouting | Equipment / Matériel |  |  |  | YES | ESH | 2022-11-28 | 2023-02-28 | 2023-01-06 | YES | 2022-11-29 | 2022-11-29 | 2022-12-31 | 2023-12-30 | N/A | 2500 |  | 2500 |  |  |  | 22050 Natureworks | 22050 Natureworks : Rubber lining thickness is lower than the standard
| 22051 | NVSA | 2022-12-05 | ESH | IER | Natureworks | Jhenten | Pdt unconformity |  |  | 16753 | IEX | filter halar thickness | SYSTEMS | I&R process | Pre-Mouting | Equipment / Matériel |  |  |  | YES | FLI | 2022-12-05 | 2023-03-05 | 2023-01-09 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 22051 Natureworks | 22051 Natureworks : filter halar thickness
CAP_EMISES 2023\23001 Sanofi DNE membranes\23001 Sanofi-Evolution anormale débit eau membrane Kerasep BP BX 50 kD.docx | 23001 | SMB | 2023-01-11 | SGU | CS | Sanofi | CTI | Claim |  |  | CVS-2106-0002 | MF/UF | Abnormal evolution of water flow Kerasep membranes | Cust. Sce | After sales process | Purchase | Material / Matière |  | CTI |  | YES | SGU | 2023-02-06 | 2023-04-11 | 2023-06-20 | NO | 2023-01-05 | 2023-01-06 | 2023-06-30 | 2023-06-20 | YES | 3430 | 0 | 3430 |  | A faire 12/23 |  | 23001 Sanofi | 23001 Sanofi : Abnormal evolution of water flow Kerasep membranes
CAP_EMISES 2023\23002 Friesland-résine Halal\23002 - Friesland résine Halal.docx | 23002 | SMB | 2023-01-20 | ENA | CS | Friesland | Dupont | Internal Anomaly |  |  | CVS-2204-0025 | IEX | Non halal resin delivered | Cust. Sce | After sales process | Order validation | Method / Méthode |  |  |  | YES | NPA | 2023-01-16 | 2023-04-20 | 2024-09-03 | NO |  |  |  |  | N/A | 980 | 5000 | 5980 |  | A faire 12/24 |  | 23002 Friesland | 23002 Friesland : Non halal resin delivered
CAP_EMISES 2023\23003 Cargill BOZ- joints EPDM\23003 Cargill BOZ-gasket of side glasses.docx | 23003 | SMB | 2023-01-23 | CDV | IER | Cargill BOZ | Gree | Claim |  | 2104 | 15841 | IEX | Side glasses gaskets of columns not conform | SYSTEMS | I&R process | QC | Method / Méthode |  |  |  | YES | XRO | 2023-01-31 | 2023-04-23 | 2023-04-27 | NO | 2023-01-16 | 2023-01-23 | 2023-06-30 | 2023-04-27 | YES | 196 | 5077 | 5273 |  | A faire 12/23 |  | 23003 Cargill BOZ | 23003 Cargill BOZ : Side glasses gaskets of columns not conform
CAP_EMISES 2023\23004 Cevital- déformation buses\23004 Cevital-déformation buses .docx | 23004 | SMB | 2023-01-26 | MGL | CS | Cevital | Composites Vec | Prevent / improve |  |  | CVS-2201-0025 | Decolo | Deformation of column nozzles | Cust. Sce | After sales process | Production | Material / Matière |  |  |  | YES | MGL | 2023-01-24 | 2023-04-26 | 2023-04-03 | YES |  |  |  |  | N/A | 490 | 0 | 490 |  | A faire 12/23 |  | 23004 Cevital | 23004 Cevital : Deformation of column nozzles
CAP_EMISES 2023\23005 GSK - gestion interne envoi information client\23005 GSK - Gestion interne envoi information client .docx | 23005 | SMB | 2023-01-30 | SGU | CS | GSK Hamilton |  | Internal Anomaly |  |  | CVS-2209-0004 | MF/UF | Internal management of customer requests | Cust. Sce | After sales process | Shipment | Method / Méthode |  |  |  | NO |  |  | 2023-04-30 | 2023-04-05 | YES |  |  |  |  | N/A | 686 | 0 | 686 |  | A faire 12/24 |  | 23005 GSK Hamilton | 23005 GSK Hamilton : Internal management of customer requests
| 23006 | NVSA | 2023-02-10 | ESH | IER | Natureworks | Wuxi fandesi/FDS | Pdt unconformity |  |  | 16753 |  |  | SYSTEMS | I&R process | QC | Method / Méthode |  |  |  | YES | ESH | 2023-02-10 | 2023-05-10 | 2023-02-24 | YES |  |  | 2023-02-21 | 2023-02-20 | N/A | 1500 | 0 | 1500 |  |  |  | 23006 Natureworks | 23006 Natureworks :
C:\Users\nscpt\OneDrive - Novasep Process Solutions\AQHSE\1-Qualite\1-FICHES_CAP\CAP_EMISES 2023\23007 DSM-Qualifiltre\23007 DSM-Qualifiltre.docx | 23007 | SMB | 2023-02-28 | DBA | CS | DSM | Quali-filtre | Claim |  |  | CVS-2211-0004 | IEX | Early tearing of filter bags | Cust. Sce | After sales process | Purchase | Material / Matière |  | DSM |  | YES | DBA | 2023-03-17 | 2023-05-28 | 2023-05-31 | NO | 2023-02-24 | 2023-02-27 | 2023-06-30 | 2023-05-31 | YES | 784 | 0 | 784 |  | A faire 12/23 |  | 23007 DSM | 23007 DSM : Early tearing of filter bags
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23008%20VRS-%20Bolloré%20erreur%20expédition%20ref%20résine/23008%20VRS%20Bolloré-erreur%20d'expédition%20ref%20résines.docx | 23008 | SMB | 2023-03-01 | CJA | CS | VRS | Bolloré | Claim |  |  | CVS-2211-0019 | IEX | Wrong resin delivered | Cust. Sce | After sales process | Logistic | Material / Matière |  | Bolloré |  | NO |  |  | 2023-06-01 | 2023-06-28 | NO | 2023-02-12 |  | 2023-06-30 | 2023-06-28 | YES | 784 | 0 | 784 |  | A faire 12/23 |  | 23008 VRS | 23008 VRS : Wrong resin delivered
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23009%20Cévital-%20Bolloré%20erreur%20démarquage/23009%20Cévital-Bolloré%20erreur%20démarquage.docx | 23009 | SMB | 2023-03-01 | CJA | CS | Cevital | Bolloré | Claim |  |  | CVS-2205-0036 | Decolo | Forgotten supplier label on BB of resins | Cust. Sce | After sales process | Logistic | Material / Matière |  | Bolloré |  | NO |  |  | 2023-06-01 | 2023-06-28 | NO | 2023-02-09 | 2023-02-22 | 2023-06-30 | 2023-06-28 | YES | 588 | 0 | 588 |  | A faire 02/24 |  | 23009 Cevital | 23009 Cevital : Forgotten supplier label on BB of resins
| 23010 | NVSA | 2023-03-03 | ESH | IER | LEKAI | FDS | Supplier Dysfonctionning |  | 2137 | 18080 | SSMB | Piping fabrication quality | SYSTEMS | I&R process | Commissioning | Material / Matière |  |  |  | YES | ESH | 2023-03-03 | 2023-06-03 | 2023-05-05 | YES |  |  |  |  | N/A |  |  | 0 |  |  |  | 23010 LEKAI | 23010 LEKAI : Piping fabrication quality
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23011%20Lier%20-membranes%2015%20KD/23011%20Lier-membranes%2015%20KD.docx | 23011 | SMB | 2023-03-13 | SGU | CS | LIER | CTI | Supplier Dysfonctionning |  |  | CVS-2101-0078 | MF/UF | 15 KD Kerasep membrane layer detachment | Cust. Sce | After sales process | Purchase | Material / Matière |  | CTI |  | YES | SGU | 2023-03-09 | 2023-06-13 | 2023-06-06 | YES |  |  |  |  | N/A | 882 | 0 | 882 |  | A faire 02/24 |  | 23011 LIER | 23011 LIER : 15 KD Kerasep membrane layer detachment
C:\Users\nscpt\OneDrive - Novasep Process Solutions\AQHSE\1-Qualite\1-FICHES_CAP\CAP_EMISES 2023\23012 Capua 1880 - erreur de membrane\23012 CAPUA- erreur membrane (4).docx | 23012 | SMB | 2023-03-20 | SGU | CS | CAPUA |  | Internal Anomaly |  |  | CVS-2003-0051 | MF/UF | Membrane cut off error in client installation | Cust. Sce | After sales process | Article creation | Manpower / Main d'œuvre |  |  |  | NO |  |  | 2023-06-20 | 2023-05-26 | YES |  |  |  |  | N/A | 196 | 0 | 196 |  | A faire 02/24 |  | 23012 CAPUA | 23012 CAPUA : Membrane cut off error in client installation
| 23013 | NVSA | 2023-04-11 | ESH | IER | Cofco Tangshan |  | Internal Anomaly |  |  | 23013_16608 |  | Cofco_issue control valve on drawing | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | ESH | 2023-04-10 | 2023-07-11 | 2023-05-04 | YES |  |  |  |  | N/A |  | 278 | 278 |  |  |  | 23013 Cofco Tangshan | 23013 Cofco Tangshan : Cofco_issue control valve on drawing
| 23014 | NVSA | 2023-04-11 | ESH | IER | Huitong SSMB | FDS | Claim |  |  | 10.1779 |  | SSMB internals material (SS304 instead of SS316) | SYSTEMS | I&R process | Pre-Mouting | Material / Matière |  |  |  | YES | ESH | 2023-04-10 | 2023-07-11 | 2023-05-04 | YES | 2023-03-29 | 2023-03-29 | 2023-07-31 | 2023-05-04 | YES | 1000 |  | 1000 |  |  |  | 23014 Huitong SSMB | 23014 Huitong SSMB : SSMB internals material (SS304 instead of SS316)
| 23015 | NVSA | 2023-04-11 | ESH | IER | Ensign 2 | SPA | Claim |  |  | 18251 | IEX | Ensign site issues rubber lining leakage | SYSTEMS | I&R process | Commissioning | Material / Matière |  |  |  | YES | ESH | 2023-04-10 | 2023-07-11 | 2023-06-12 | YES | 2023-03-08 | 2023-03-08 | 2023-07-31 | 2023-06-12 | YES | 2500 | 2583 | 5083 |  |  |  | 23015 Ensign 2 | 23015 Ensign 2 : Ensign site issues rubber lining leakage
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23016%20Sanofi%20DE%20membranes%20anormal/23016%20Sanofi-Débit%20eau%20membrane%20Kerasep%20BP%20BX%2050%20kD%20anormal.docx | 23016 | SMB | 2023-04-14 | SGU | CS | Sanofi | CTI | Claim | X |  | CVS-2211-0014 | MF/UF | Abnormal water flow Kerasep membranes 50 kD | Cust. Sce | After sales process | Purchase | Material / Matière |  |  |  | YES | SGU | 2023-04-14 | 2023-07-14 | 2024-06-10 | NO | 2023-04-04 | 2023-04-07 | 2023-12-31 | 2024-06-10 | NO | 13916 | 10550 | 24466 |  | A faire 12/24 |  | 23016 Sanofi | 23016 Sanofi : Abnormal water flow Kerasep membranes 50 kD
C:\Users\christine.potier\OneDrive - Novasep Process Solutions\AQHSE\1-Qualite\1-FICHES_CAP\CAP_EMISES 2023\23017 Cévital-doc d'expédition\23017 Cevital expédition.docx | 23017 | SMB | 2023-04-24 | SSI | CS | Cevital | Bolloré | Internal Anomaly |  |  | CVS-2205-0036_CVS-2208-0014 | Decolo | Wrong shipping documents | Cust. Sce | After sales process | Logistic | Manpower / Main d'œuvre |  |  |  | YES | CBL | 2023-04-25 | 2023-07-24 | 2023-07-21 | YES |  |  |  |  | N/A | 294 | 0 | 294 |  | A faire 01/24 |  | 23017 Cevital | 23017 Cevital : Wrong shipping documents
| 23018 | NVSA | 2023-05-15 | MYU | CS | HUAKANG | Finex | Claim |  |  | 15333 | SSMB | Poor performance of Xylose ML SSMB/Resin issue | Cust. Sce | After sales process | project closed | Material / Matière |  |  |  | YES | MYU | 2023-05-15 | 2023-08-15 | 2023-07-19 | YES | 2023-04-14 | 2023-04-17 | 2023-08-31 | 2023-07-19 | YES | 0 | 3000 | 3000 |  |  |  | 23018 HUAKANG | 23018 HUAKANG : Poor performance of Xylose ML SSMB/Resin issue
| 23019 | NVSA | 2023-06-02 | MYU | CS | DYG | Inopor | Claim | X |  | 75.2269 | MF | Alpha KBW 0.1U membranes abrasion issue | Cust. Sce | After sales process | project closed | Material / Matière |  | Inopor |  | YES | MYU | 2023-06-02 | 2023-09-02 | 2023-07-19 | YES | 2023-02-05 | 2023-02-05 | 2023-10-31 | 2023-07-19 | YES | 0 | 130000 | 130000 |  |  |  | 23019 DYG | 23019 DYG : Alpha KBW 0.1U membranes abrasion issue
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23020%20fuite%20eau%20bureau%20membrane/23020%20Fuite%20eau%20bureau%20atelier%20membrane.docx | 23020 | SMB | 2023-06-23 | SGU | CS | Interne |  | Safety |  |  |  |  | Water leakage in the membrane office | Cust. Sce | After sales process | membrane | Equipment / Matériel |  |  |  | NO |  |  | 2023-09-23 | 2023-08-28 | YES |  |  |  |  | N/A | 490 | 450 | 940 |  | A faire 02/24 |  | 23020 Interne | 23020 Interne : Water leakage in the membrane office
C:\Users\christine.potier\OneDrive - Novasep Process Solutions\AQHSE\1-Qualite\1-FICHES_CAP\CAP_EMISES 2023\23021 Bonumose-corrosion tank\23021 Bonumose - pb corrosion tank-piping.docx | 23021 | SMB | 2023-07-10 | LPR | IER | Bonumose |  | Claim |  | 2116 | 16253 | IEX | Acid corrosion on piping and tank | SYSTEMS | I&R process | Meca design | Method / Méthode |  |  |  | YES | JGO | 2023-07-10 | 2023-10-10 | 2023-08-30 | YES | 2023-02-14 |  | 2023-10-31 | 2023-08-30 | YES | 1473 | 5431 | 6904 |  | A faire 02/24 |  | 23021 Bonumose | 23021 Bonumose : Acid corrosion on piping and tank
C:\Users\christine.potier\OneDrive - Novasep Process Solutions\AQHSE\1-Qualite\1-FICHES_CAP\CAP_EMISES 2023\23022 Inovyn-Défaut ébonitage\23022 Inovyn - défaut ébonite colonnes.docx | 23022 | SMB | 2023-07-12 | TCC | IER | Inovyn | Beugin-ONEX | Supplier Dysfonctionning |  | 2144 | 18147 | IEX | Default of IEX columns rubber lining | SYSTEMS | I&R process | Purchase | Material / Matière |  |  |  | YES | JGO | 2023-07-20 | 2023-10-12 | 2024-01-15 | NO |  |  |  |  | N/A | 980 | 0 | 980 |  | A faire 07/24 |  | 23022 Inovyn | 23022 Inovyn : Default of IEX columns rubber lining
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23023%20Fuite%20toiture%20Halle%20R&D%20N°2/23023%20Fuite%20toiture%20halle%20R&D%20N°2.docx | 23023 | SMB | 2023-09-26 | MRN | R&D | Interne |  | Safety |  |  |  |  | R&D hall N°2 roof leak | R&D | PPD Process | Piloting | Equipment / Matériel |  |  |  | YES | HOS | 2023-10-27 | 2023-12-26 | 2023-11-03 | YES |  |  |  |  | N/A | 784 | 0 | 784 |  | A faire 02/24 |  | 23023 Interne | 23023 Interne : R&D hall N°2 roof leak
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23024%20Bénéo-%20corrosion/23024%20Bénéo%20-%20Corrosion%20Piping%20Dem1.docx | 23024 | SMB | 2023-10-03 | XRO | IER | Bénéo Chili |  | Claim |  | 2066 | 13829 | IEXc | 304L piping corrosion | SYSTEMS | I&R process | Meca design | Method / Méthode |  |  |  | YES | XRO | 2023-10-03 | 2024-01-03 | 2024-01-10 | NO | 2023-05-12 | 2023-05-15 | 2024-04-30 | 2024-01-10 | YES | 18830 | 107477 | 126307 |  | A faire 07/24 |  | 23024 Bénéo Chili | 23024 Bénéo Chili : 304L piping corrosion
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23025%20Cargill%20Zest-%20Lining/23025%20Cargill%20Zest-Problématique%20Ebonite.docx | 23025 | SMB | 2023-10-16 | XRO | IER | Cargill Zest | SPA | Claim |  | 2087 | 13086 | IEX | Degradation of Lining inside IEX Column | SYSTEMS | I&R process | Process design | Material / Matière |  |  |  | YES | XRO | 2023-10-17 | 2024-01-16 |  | NO | 2023-01-05 | 2023-01-06 | 2024-10-31 |  | NO |  |  | 0 |  |  |  | 23025 Cargill Zest | 23025 Cargill Zest : Degradation of Lining inside IEX Column
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23026%20COPAM-billes%20noires%20résine/23026%20COPAM-billes%20noires%20résines.docx | 23026 | SMB | 2023-10-16 | LCA | IER | COPAM | Dupont | Supplier Dysfonctionning |  | 2148 | 18201 | IEX | Black beads in resin | SYSTEMS | I&R process | Commissioning | Material / Matière |  | Dupont |  | YES | LCA | 2023-10-19 | 2024-01-16 | 2024-01-16 | YES |  |  |  |  | N/A | 2352 | 0 | 2352 |  | A faire 07/24 |  | 23026 COPAM | 23026 COPAM : Black beads in resin
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23027%20Inovyn-Défaut%20cablâge%20électrique/23027%20Inovyn%20-%20problèmes%20câblage%20électriques.docx | 23027 | SMB | 2023-10-16 | JPL | IER | Inovyn | SPIE | Claim |  | 2144 | 18147 | IEX | Skid wiring default | SYSTEMS | I&R process | AEI design | Method / Méthode |  |  |  | YES | RDA | 2023-10-19 | 2024-01-16 | 2024-01-22 | NO | 2023-09-27 | 2023-10-05 | 2024-01-31 | 2024-01-22 | YES | 1078 | 14493.69 | 15571.69 |  | A faire 07/24 |  | 23027 Inovyn | 23027 Inovyn : Skid wiring default
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23028%20Via%20Séparation-%20pompes%20Sulzer/23028%20Via%20Separation%20-%20pompes%20Sulzer.docx | 23028 | SMB | 2023-10-23 | JNJ | Achat | Via Separation | Sulzer | Supplier Dysfonctionning |  | 2153 | 18336 |  | Late delivery of centrigugal pumps | SYSTEMS | Purchase | Delivery | Material / Matière |  | Sulzer |  | NO |  |  | 2024-01-23 | 2024-01-10 | YES |  |  |  |  | N/A | 2450 | 0 | 2450 |  | A faire 07/24 |  | 23028 Via Separation | 23028 Via Separation : Late delivery of centrigugal pumps
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23029%20Inovyn%20-%20Montage%20Interconnection/23029%20Inovyn%20-%20pb%20tuyauteries%20interconnection.docx | 23029 | SMB | 2023-10-23 | TCC | IER | Inovyn | ONEX-PACT SNZ | Claim |  | 2144 | 18147 | IEX | Interconnexion piping issues/columns | SYSTEMS | I&R process | Meca design | Method / Méthode |  | PACT SNZ |  | YES | RDA | 2023-11-03 | 2024-01-23 | 2024-01-15 | YES | 2023-10-04 | 2023-10-09 | 2024-01-31 | 2024-01-15 | YES | 1372 | 3800 | 5172 |  | A faire 07/24 |  | 23029 Inovyn | 23029 Inovyn : Interconnexion piping issues/columns
| 23030 | NVSA | 2023-10-28 | MPE | IER | SQ Nansha | Runlu | Supplier Dysfonctionning |  | 2128 | 17951 | IEX | Loose nozzles found inside columns of SQ20 on Site | SYSTEMS | I&R process | Commissioning | Method / Méthode |  |  |  | YES | ESH | 2023-11-17 | 2024-01-28 | 2024-01-12 | YES |  |  |  |  | N/A | 3000 | 1892 | 4892 |  |  |  | 23030 SQ Nansha | 23030 SQ Nansha : Loose nozzles found inside columns of SQ20 on Site
| 23031 | NVSA | 2023-11-06 | MHA | IER | Lier | Xiangming | Internal Anomaly |  | 2151 | 18281 | MF/UF | Unproper MF housings site installation | SYSTEMS | I&R process | Installation | Method / Méthode |  |  |  | YES | ESH | 2023-12-06 | 2024-02-06 | 2024-02-01 | YES |  |  |  |  | N/A | 250 | 139 | 389 |  |  |  | 23031 Lier | 23031 Lier : Unproper MF housings site installation
| 23032 | NVSA | 2023-11-06 | MHA | IER | Rousselot | kaiyuan/Biteng | Claim |  | 2150 | 18178 | IEX | Painting damage during transportation | SYSTEMS | I&R process | Delivery | Method / Méthode |  |  |  | YES | ESH | 2023-11-27 | 2024-02-06 | 2024-04-26 | NO | 2023-08-04 | 2023-08-04 | 2024-04-30 | 2024-04-26 | YES | 938 | 0 | 938 |  |  |  | 23032 Rousselot | 23032 Rousselot : Painting damage during transportation
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202023/23033%20ADM-pilotage%20SSMB/23033%20ADM-pilotage%20SSMB%20mélange%20Raffinat-Extrait.docx | 23033 | SMB | 2023-11-08 | IFM | R&D | ADM |  | Internal Anomaly |  | 3012 | 2023-006 | SSMB | Extract/Raffinate handling error | R&D | PPD Process | Piloting | Manpower / Main d'œuvre |  |  |  | YES | IFM | 2023-11-16 | 2024-02-08 | 2024-01-12 | YES |  |  |  |  | N/A | 2352 | 0 | 2352 |  | A faire 07/24 |  | 23033 ADM | 23033 ADM : Extract/Raffinate handling error
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202024/24001%20Omnia/24001%20Omnia.docx | 24001 | SMB | 2024-01-05 | NPA | CS | Omnia | Jinlong | Claim |  | 2044 | 13042 | SSMB | Product leak on SSMB column at weld level | Cust. Sce | After sales process | Purchase | Environment / Milieu |  |  |  | YES | NPA | 2024-01-05 | 2024-04-05 | 2024-07-19 | NO | 2023-11-07 | 2023-11-10 | 2024-09-30 | 2024-07-19 | YES | 16268 | 11298 | 27566 |  | A faire 12/24 |  | 24001 Omnia | 24001 Omnia : Product leak on SSMB column at weld level
| 24002 | NVSA | 2024-01-16 | ESH | IER | Xinlv | FDS | Supplier Dysfonctionning |  |  | 18418 | SSMB | Xinlv SSMB cell height | SYSTEMS | I&R process | QC at client site | Method / Méthode |  |  |  | YES | ESH | 2024-03-01 | 2024-04-16 | 2024-04-15 | YES |  |  |  |  | N/A | 750 | 0 | 750 |  |  |  | 24002 Xinlv | 24002 Xinlv : Xinlv SSMB cell height
| 24003 | NVSA | 2024-01-22 | TWI | IER | SQ13 | GREE | Claim |  | 2097 | 16108 | IEX | SQ13 LS MB140 column internals deformation | SYSTEMS | I&R process | commissioning | Method / Méthode |  |  |  | YES | TWI | 2024-01-30 | 2024-04-22 | 2024-05-06 | NO | 2024-01-13 | 2024-01-13 | 2024-05-31 | 2024-05-06 | YES | 7000 | 3832 | 10832 |  |  |  | 24003 SQ13 | 24003 SQ13 : SQ13 LS MB140 column internals deformation
| 24004 | SMB | 2024-02-02 | FCA/SOV | IER | Etihad | CTI/Beugin | Supplier Dysfonctionning |  | 2159 | 18307 | Decolo | Piping defects and lack of supply for strainers | SYSTEMS | I&R process | commissioning | Method / Méthode |  |  |  | YES | SOV | 2024-02-02 | 2024-05-02 | 2024-04-19 | YES |  |  |  |  | N/A | 14308 | 1500 | 15808 |  | A faire 12/24 |  | 24004 Etihad | 24004 Etihad : Piping defects and lack of supply for strainers
| 24005 | NVSA | 2024-02-20 | ESH | IER | Huitong |  | Internal Anomaly |  | 2136 | 17789 | SSMB | Backwashing tank volume issue | SYSTEMS | I&R process | commissioning | Method / Méthode |  |  |  | YES | ESH | 2024-03-28 | 2024-05-20 | 2024-05-20 | YES |  |  |  |  | N/A | 1278 |  | 1278 |  |  |  | 24005 Huitong | 24005 Huitong : Backwashing tank volume issue
| 24006 | SMB | 2024-02-21 | JNJ | Achat | Bénéo Chili | Bolloré | Prevent / improve |  | 2066 | 13829 | IEXc | Late delivery of a piping box | SYSTEMS | I&R process | Logistic | Method / Méthode |  |  |  | YES | JNJ | 2024-02-29 | 2024-05-21 | 2024-04-23 | YES |  |  |  |  | N/A | 196 | 0 | 196 |  | A faire 12/24 |  | 24006 Bénéo Chili | 24006 Bénéo Chili : Late delivery of a piping box
https://novasepps.sharepoint.com/sites/NPS_DATA/AQHSE/1-Qualite/1-FICHES_CAP/CAP_EMISES%202024/24007%20Friesland/24007%20Friesland-sac%2025l%20dans%20BB.docx | 24007 | SMB | 2024-02-21 | CJA | CS | Friesland | Bolloré | Claim |  |  | FRA-SON0000291 |  | Empty supplier resin bag in reconditioned BB of resin | Cust. Sce | After sales process | Logistic | Material / Matière |  | Bolloré |  | YES | NPA | 2024-03-19 | 2024-05-21 | 2024-04-30 | YES | 2024-02-19 | 2024-02-19 | 2024-06-30 | 2024-04-30 | YES | 196 | 0 | 196 |  | A faire 12/24 |  | 24007 Friesland | 24007 Friesland : Empty supplier resin bag in reconditioned BB of resin
| 24008 | SMB | 2024-02-28 | LCA | IER | BMA Bengladesh | STCL | Supplier Dysfonctionning |  | 2120 | 17042 | Evapo | Absence of calculation note for evapo piping | SYSTEMS | I&R process | Meca design | Material / Matière |  |  |  | YES | LCA | 2024-03-01 | 2024-05-28 | 2024-05-14 | YES |  |  |  |  | N/A | 1960 | 0 | 1960 |  | A faire 12/24 |  | 24008 BMA Bengladesh | 24008 BMA Bengladesh : Absence of calculation note for evapo piping
| 24009 | SMB | 2024-02-28 | XRO | IER | Via Separation | XM | Internal Anomaly |  | 2153 | 18336 | MF | Studs missing on Kerasep modules delivered by Applexion SHA | SYSTEMS | I&R process | Meca design | Method / Méthode |  |  |  | YES | JGO | 2024-03-05 | 2024-05-28 | 2024-05-24 | YES |  |  |  |  | N/A | 11662 | 58608 | 70270 |  | A faire 12/24 |  | 24009 Via Separation | 24009 Via Separation : Studs missing on Kerasep modules delivered by Applexion SHA
| 24010 | SMB | 2024-02-28 | XRO | IER | Via Separation |  | Internal Anomaly |  | 2153 | 18336 | MF | MF maintenance kit no compliant | SYSTEMS | I&R process | Meca design | Method / Méthode |  |  |  | YES | SGU/JGO | 2024-03-12 | 2024-05-28 | 2024-05-24 | YES |  |  |  |  | N/A | 2352 | 5000 | 7352 |  | A faire 12/24 |  | 24010 Via Separation | 24010 Via Separation : MF maintenance kit no compliant
| 24011 | SMB | 2024-02-28 | XRO | IER | Via Separation |  | Internal Anomaly |  | 2153 | 18336 | MF | Female SMS cap nuts delivered instead of male | SYSTEMS | I&R process | Meca design | Method / Méthode |  |  |  | YES | JGO | 2024-03-12 | 2024-05-28 | 2024-05-24 | YES |  |  |  |  | N/A | 3136 | 1960 | 5096 |  | A faire 12/24 |  | 24011 Via Separation | 24011 Via Separation : Female SMS cap nuts delivered instead of male
| 24012 | SMB | 2024-02-29 | XRO | IER | Via Separation | Bolloré | Internal Anomaly |  | 2153 | 18336 | MF | Package lost on site - Difficulties to identify Shipment from APX - Tagging issue | SYSTEMS | I&R process | Logistic | Method / Méthode |  |  |  | YES | JNJ | 2024-03-07 | 2024-05-29 | 2024-04-26 | YES |  |  |  |  | N/A | 4018 | 1105 | 5123 |  | A faire 07/24 |  | 24012 Via Separation | 24012 Via Separation : Package lost on site - Difficulties to identify Shipment from APX - Tagging issue
| 24013 | SMB | 2024-03-05 | JAH | IER | Carbocode | IWAKI | Safety |  | 2155 | 18332 | IEX | Acid/base projection risk when priming dosing pumps | Cust. Sce | After sales process | Commissioning | Method / Méthode |  |  |  | YES | JGO | 2024-04-25 | 2024-06-05 | 2024-06-07 | NO |  |  |  |  | N/A | 1176 | 0 | 1176 |  | A faire 12/24 |  | 24013 Carbocode | 24013 Carbocode : Acid/base projection risk when priming dosing pumps
| 24014 | NVSA | 2024-04-02 | MHA | IER | SQ CQ | FDS/Runjia | Internal Anomaly |  | 3022 | 18448 | SSMB | Unproper internals manufacturing and installation for SSMB | SYSTEMS | I&R process | QC | Equipment / Matériel |  |  |  | YES | ESH | 2024-04-10 | 2024-07-02 | 2024-07-01 | YES |  |  |  |  | N/A | 5139 |  | 5139 |  |  |  | 24014 SQ CQ | 24014 SQ CQ : Unproper internals manufacturing and installation for SSMB
| 24015 | SMB | 2024-04-17 | DMA | R&D | ADM | Saint Ex-Emballages | Prevent / improve |  | 3012 | 2023-006 | SSMB | Samples shipping issues to US | R&D | PPD Process | Logistic | Method / Méthode |  |  |  | YES | DMA | 2024-05-02 | 2024-07-17 | 2024-07-12 | YES |  |  |  |  | N/A | 2352 | 1383 | 3735 |  | A faire 12/24 |  | 24015 ADM | 24015 ADM : Samples shipping issues to US
| 24016 | NVSA | 2024-04-18 | MYU | CS | Fufeng Qiqihaer | Mitsubishi | Claim |  | 3087 | 75.2406 | IEX | Fufeng Qiqihaer- Frozen lysine resin | Cust. Sce | After sales process | Logistic | Environment / Milieu |  |  |  | YES | MYU | 2024-04-22 | 2024-07-18 | 2024-06-20 | YES | 2024-04-06 | 2024-04-06 | 2024-07-31 | 2024-06-20 | YES | 1333 | 0 | 1333 |  |  |  | 24016 Fufeng Qiqihaer | 24016 Fufeng Qiqihaer : Fufeng Qiqihaer- Frozen lysine resin
| 24017 | SMB | 2024-04-18 | PDU | R&D | Heliobiosys |  | Prevent / improve |  | 3079 |  | MF | MF pilot return blocked in customs | R&D | PPD Process | Logistic | Method / Méthode |  |  |  | YES | PDU | 2024-04-23 | 2024-07-18 | 2024-07-12 | YES |  |  |  |  | N/A | 1960 | 0 | 1960 |  | A faire 12/24 |  | 24017 Heliobiosys | 24017 Heliobiosys : MF pilot return blocked in customs
| 24018 | SMB | 2024-05-27 | ADP | Process | COPAM |  | Prevent / improve |  | 2148 | 18201 | IEX | Resin loss on demineralization unit L1 | Cust. Sce | After sales process | After sales | Equipment / Matériel |  |  |  | NO |  |  | 2024-08-27 | 2024-08-02 | YES |  |  |  |  | N/A | 392 | 0 | 392 |  | A faire 12/24 |  | 24018 COPAM | 24018 COPAM : Resin loss on demineralization unit L1
| 24019 | NVSA | 2024-06-11 | YLI | IER | SQ Nansha | SPA | Claim |  | 2128 | 17951 | IEX | SQ20 F55MB CL6510 Rubber Lining Issue of Insert Tube | SYSTEMS | I&R process | Commissioning | Equipment / Matériel |  |  |  | YES | YLI | 2024-06-24 | 2024-09-11 | 2024-09-05 | YES | 2024-04-27 | 2024-04-28 | 2024-09-30 | 2024-09-05 | YES | 500 |  | 500 |  | A faire 12/24 |  | 24019 SQ Nansha | 24019 SQ Nansha : SQ20 F55MB CL6510 Rubber Lining Issue of Insert Tube
| 24020 | SMB | 2024-06-17 | ASO | CS | Prolactal | Mega | Claim |  |  | FRA-SON0000469-2 | ED | non payment of invoice, low life of electrodes | Cust. Sce | After sales process | Purchase | Material / Matière |  |  |  | NO |  |  | 2024-09-17 | 2024-10-01 | NO | 2023-09-05 | 2023-09-19 | 2024-11-30 | 2024-10-01 | YES | 980 | 10732 | 11712 |  | A faire 04/25 |  | 24020 Prolactal | 24020 Prolactal : non payment of invoice, low life of electrodes
| 24021 | SMB | 2024-06-19 | ASO | CS | ADM | DHL | Claim |  |  | FRA-SON0000570 | SSMB | Strainers order - Delivery without ATR document | Cust. Sce | After sales process | Shipping doc | Method / Méthode |  |  |  | YES | CBL | 2024-06-24 | 2024-09-19 | 2024-09-09 | YES | 2024-06-07 | 2024-06-07 | 2024-10-31 | 2024-09-09 | YES | 588 | 0 | 588 |  | A faire 02/25 |  | 24021 ADM | 24021 ADM : Strainers order - Delivery without ATR document
| 24022 | NVSA | 2024-06-20 | TWI | IER | Huaantang |  | Internal Anomaly |  | 3123 | 18323 | SSMB | Functional Analysis assignement and workload France-Asia | SYSTEMS | I&R process | Process Design | Management/management |  |  |  | YES | TWI | 2024-06-27 | 2024-09-20 | 2024-09-19 | YES |  |  |  |  | N/A | 250 | 0 | 250 |  | A faire 02/25 |  | 24022 Huaantang | 24022 Huaantang : Functional Analysis assignement and workload France-Asia
| 24023 | SMB | 2024-07-03 | TBB | IER | ADM Lysine | SPA | Claim |  | 2048 | 12194 | IEXc | Rubber lining failure of IEXc columns | SYSTEMS | I&R process | After sales | Material / Matière |  |  |  | YES | TBB | 2024-07-08 | 2024-10-03 | 2024-09-09 | YES | 2024-01-11 | 2024-01-11 | 2024-10-31 | 2024-09-09 | YES | 5880 | 4599 | 10479 |  | A faire 02/25 |  | 24023 ADM Lysine | 24023 ADM Lysine : Rubber lining failure of IEXc columns
| 24024 | SMB | 2024-07-05 | LCA | IER | Etihad | CTI/OTIME | Claim |  | 2159 | 18307 | Decolo | Piping defects and lack of documentation | SYSTEMS | I&R process | commissioning | Method / Méthode |  | OTIME |  | YES | LCA | 2024-07-09 | 2024-10-05 |  | NO | 2024-06-29 | 2024-07-01 | 2024-12-31 |  | NO |  |  | 0 |  |  |  | 24024 Etihad | 24024 Etihad : Piping defects and lack of documentation
| 24025 | SMB | 2024-07-05 | XRO | IER | Beneo Chili | KSB | Claim |  | 2066 | 13829 | IEXc | Leaks on 3 pumps bodies KSB | SYSTEMS | I&R process | commissioning | Material / Matière |  | KSB |  | YES | XRO/JNJ | 2024-07-11 | 2024-10-05 |  | NO | 2024-05-10 | 2024-06-03 | 2024-12-31 |  | NO |  |  | 0 |  |  |  | 24025 Beneo Chili | 24025 Beneo Chili : Leaks on 3 pumps bodies KSB
| 24026 | SMB | 2024-07-10 | CDV | CS | Beneo Oreye | InaceInox | Internal Anomaly |  | CS3291 | 18021 | IEX | Internal network anomaly | Cust. Sce | After sales process | Process Design ? | Method / Méthode |  |  |  | NO |  |  | 2024-10-10 | 2024-10-07 | YES |  |  |  |  | N/A | 0 | 0 | 0 |  | A faire 06/25 |  | 24026 Beneo Oreye | 24026 Beneo Oreye : Internal network anomaly
| 24027 | SMB | 2024-07-15 | LCA | IER | BMA Angola | ZFLZ | Supplier Dysfonctionning |  | 3096 | 16242 |  | Design error for sand filter and linked nozzles | SYSTEMS | I&R process | Meca design | Method / Méthode |  |  |  | YES | JGO | 2024-07-18 | 2024-10-15 | 2024-10-11 | YES |  |  |  |  | N/A | 3038 | 2151 | 5189 |  | A faire 03/25 |  | 24027 BMA Angola | 24027 BMA Angola : Design error for sand filter and linked nozzles
| 24028 | PSA | 2024-07-18 | JLA | CS | Casa Grande | Sunresin | Claim |  |  | FRA-SON0000615 | IEX | Strong smell from IEX | Cust. Sce | After sales process | Purchase | Material / Matière |  |  |  | YES | NPA | 2024-07-17 | 2024-10-18 | 2024-10-15 | YES | 2024-07-11 | 2024-07-18 | 2024-10-31 | 2024-10-15 | YES | 712 | 0 | 712 |  | A faire 06/25 |  | 24028 Casa Grande | 24028 Casa Grande : Strong smell from IEX
| 24029 | SMB | 2024-07-24 | TBB | IER | Via Separation | Bray | Claim |  | 2153 | 18336 |  | Bray valves damage | SYSTEMS | I&R process | commissioning | Material / Matière |  | Bray |  | YES | TBB | 2024-07-25 | 2024-10-24 | 2024-11-22 | NO | 2024-07-22 | 2024-07-26 | 2024-12-31 | 2024-11-22 | YES | 980 | 36394 | 37374 |  | A faire 04/25 |  | 24029 Via Separation | 24029 Via Separation : Bray valves damage
| 24030 | NVSA | 2024-08-02 | RRU | CS | Lesaffre | INOPOR | Claim |  | 2142 | 18146 | MF/UF | KBE alpha Membrane Abrasion | Cust. Sce | After sales process | After sales | Material / Matière |  |  |  | YES | TWI | 2024-08-27 | 2024-11-02 |  | NO | 2024-07-25 | 2024-07-25 | 2024-12-31 |  | NO |  |  | 0 |  |  |  | 24030 Lesaffre | 24030 Lesaffre : KBE alpha Membrane Abrasion
| 24031 | SMB | 2024-09-05 | SGU | CS | GSK Hamilton | CTI | Claim |  |  | FRA-SON0000711 | MF/UF | Marks on Kerasep Biopharma Membranes | Cust. Sce | After sales process | After sales | Material / Matière |  | CTI |  | NO |  |  | 2024-12-05 | 2024-10-30 | YES | 2024-08-08 | 2024-08-09 | 2024-12-31 | 2024-10-30 | YES | 98 | 0 | 98 |  | A faire 04/25 |  | 24031 GSK Hamilton | 24031 GSK Hamilton : Marks on Kerasep Biopharma Membranes
| 24032 | SMB | 2024-09-18 | FCA | IER | BMA Bengladesh | Aquacom | Supplier Dysfonctionning | X | 2120 | 17042 | NF | Pressure vessels design defect | SYSTEMS | I&R process | commissioning | Material / Matière |  |  |  | YES | APL | 2024-09-25 | 2024-12-18 | 2024-10-30 | YES |  |  |  |  | N/A | 98 | 77 | 175 |  | A faire 04/25 |  | 24032 BMA Bengladesh | 24032 BMA Bengladesh : Pressure vessels design defect
| 24033 | SMB | 2024-10-01 | FPO | R&D | TEREOS |  | Safety |  | 3204 |  |  | Left fingers pinched in stirred tank | R&D | PPD Process | Piloting | Manpower / Main d'œuvre |  |  |  | YES | HOS | 2024-10-08 | 2025-01-01 |  | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 24033 TEREOS | 24033 TEREOS : Left fingers pinched in stirred tank
| 24034 | PSA | 2024-10-04 | MPA | CS | CJ US | Lanxess | Supplier Dysfonctionning |  |  | USA-PON0000149 |  | Resin delivered delayed | Cust. Sce | After sales process | Purchase | Material / Matière |  | Lanxess |  | NO |  |  | 2025-01-04 |  | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 24034 CJ US | 24034 CJ US : Resin delivered delayed
| 24035 | SMB | 2024-10-14 | XRO | IER | Bénéo Chili |  | Claim |  | 2066 | 13829 | IEXc | Rust of flanges and structure | SYSTEMS | I&R process |  | Equipment / Matériel |  |  |  | NO |  |  | 2025-01-14 |  | NO | 2024-10-07 | 2024-10-11 | 2025-01-31 |  | NO |  |  | 0 |  |  |  | 24035 Bénéo Chili | 24035 Bénéo Chili : Rust of flanges and structure
| 24036 | NVSA | 2024-10-18 | RRU | CS | GXSF 2 | Mitsubishi | Claim |  |  | 10.702 | IEX | High Pressure Drop in C120A upper cell | Cust. Sce | After sales process | commissioning | Material / Matière |  |  |  | YES | MYU | 2024-10-29 | 2025-01-18 |  | NO | 2024-09-16 | 2024-09-18 | 2025-01-31 |  | NO | 6389 | 156111 | 162500 |  |  |  | 24036 GXSF 2 | 24036 GXSF 2 : High Pressure Drop in C120A upper cell
| 24037 | SMB | 2024-11-07 | TEB | R&D | COSUN |  | Internal Anomaly |  | 3293 |  | SSMB | High pressure in SSMB pilot columns | R&D | PPD Process | Piloting | Material / Matière |  |  |  | YES | HOS | 2024-11-14 | 2025-02-07 |  | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 24037 COSUN | 24037 COSUN : High pressure in SSMB pilot columns
| 24038 | NVSA | 2024-11-18 | RRU | CS | Yinmore | Mitsubishi | Claim |  |  | 9801 | IEX | Large deviation in resin particle size distribution | Cust. Sce | After sales process | purchasing | Material / Matière |  |  |  | YES | MYU | 2024-11-29 | 2025-02-18 |  | NO | 2024-09-10 | 2024-11-07 |  |  |  |  | 83333.33 | 83333.33 |  |  |  | 24038 Yinmore | 24038 Yinmore : Large deviation in resin particle size distribution
| 24039 | NVSA | 2024-11-19 | YLI | IER | Huaantang | SPA | Supplier Dysfonctionning |  | 3123 | 18323 | SSMB | Columns Name plate & Tag No. Installation Mistake | SYSTEMS | I&R process | QC | Equipment / Matériel |  |  |  | YES | YLI | 2024-11-28 | 2025-02-19 |  | NO |  |  |  |  | N/A | 625 | 486 | 1111 |  |  |  | 24039 Huaantang | 24039 Huaantang : Columns Name plate & Tag No. Installation Mistake
| 24040 | NVSA | 2024-11-19 | YLI | IER | Huaantang | FDS | Supplier Dysfonctionning |  | 3123 | 18323 | SSMB | Column-B Resin Nozzle Orientation Mistake | SYSTEMS | I&R process | QC | Equipment / Matériel |  |  |  | YES | YLI | 2024-11-28 | 2025-02-19 |  | NO |  |  |  |  | N/A | 625 |  | 625 |  |  |  | 24040 Huaantang | 24040 Huaantang : Column-B Resin Nozzle Orientation Mistake
| 24041 | NVSA | 2024-11-20 | MHA | IER | LIER | Runyuan | Claim |  | 3165 | 18466 | CA | The carbon backwashing is not efficient | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | ACH | 2024-11-27 | 2025-02-20 |  | NO | 2024-09-19 | 2024-09-19 |  |  |  | 2188 | 1388 | 3576 |  |  |  | 24041 LIER | 24041 LIER : The carbon backwashing is not efficient
| 24042 | NVSA | 2024-11-20 | MHA | IER | LIER | LongYU, Ziyou | Internal Anomaly |  | 3165 | 18466 | CA | Mismatching of Nozzle A1 and A2 betweent column and front piping | SYSTEMS | I&R process | Meca Design | Method / Méthode |  |  |  | YES | ACH | 2024-11-27 | 2025-02-20 |  | NO |  |  |  |  | N/A | 1876 | 1416 | 3292 |  |  |  | 24042 LIER | 24042 LIER : Mismatching of Nozzle A1 and A2 betweent column and front piping
| 24043 | NVSA | 2024-11-25 | MYU | CS | SQ18 | Dupont | Internal Anomaly |  |  | 17093 | IEX | SQ18 IRA458 Resin missing in SHA warehouse | Cust. Sce | After sales process | stock | Management / Management |  |  |  | YES | MYU | 2024-11-29 | 2025-02-25 |  | NO |  |  |  |  | N/A |  | 105944.44 | 105944.44 |  |  |  | 24043 SQ18 | 24043 SQ18 : SQ18 IRA458 Resin missing in SHA warehouse
| 24044 | NVSA | 2024-12-02 | TWI | IER | PLIITH HUITONG | ZIMA | Claim |  | 2135 | 18103 | CA | Huitong Claim on GAC revamping program delay | SYSTEMS | I&R process | automation | Management/management |  |  |  | YES |  |  | 2025-03-02 |  | NO | [7 empty] | 0 |  |  |  | 24044 PLIITH HUITONG | 24044 PLIITH HUITONG : Huitong Claim on GAC revamping program delay
| 24045 | NVSA | 2024-12-02 | MHA | IER | SQ nansha |  | Internal Anomaly |  | 3075 | 45.0037 | SSMB | SQ1 revamping program didn't complete on time | SYSTEMS | I&R process | automation | Management/management |  |  |  | YES |  |  | 2025-03-02 |  | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 24045 SQ nansha | 24045 SQ nansha : SQ1 revamping program didn't complete on time
| 24046 | SMB | 2024-12-02 | LPU | R&D | Interne |  | Safety |  |  |  |  | Corrosion in the AKTA laboratory | R&D | PPD Process | Laboratory tests | Environment / Milieu |  |  |  | YES |  |  | 2025-03-02 |  | NO |  |  |  |  | N/A |  |  | 0 |  |  |  | 24046 Interne | 24046 Interne : Corrosion in the AKTA laboratory
Formulas:
Date of effic. measure = EDATE([Date of effic. measure, row below],-3)
Closure Date = EDATE([Recording Date],3)
Claim Date = IF([Closed under 3 months]="",IF(TODAY()>[Closure Date],"NO","YES"),IF([Closed under 3 months]>[Closure Date],"NO",IF([Closed under 3 months]<[Closure Date],"YES",IF([Closure Date]=[Closed under 3 months],"YES","N/A"))))
Hours (€) = IF([CAP TYPE]="Claim",IF([Date of acting plan closure]="","",IF([closed in delay?]="",IF(TODAY()>[Date of acting plan closure],"NO","YES"),IF([closed in delay?]>[Date of acting plan closure],"NO",IF([closed in delay?]<[Date of acting plan closure],"YES",IF([Date of acting plan closure]=[closed in delay?],"YES","N/A"))))),"N/A")
Note on M6: Codes Techno : ED (Electrodialyse) SSMB (Chromato) IEX (Echange Ions) MF/UF (Micro/Ultrafiltation) NF (Nanofiltration) OI (Osmose Inverse) EVAPO (Evaporation) CA (Charbon Actif)
Note on I164: Christine POTIER: anomalie requalifiée en REC le 29/04/15
Note on I183: Christine POTIER: Dysf fnr requalifié en REC le 9/10/15
Note on R261: Christine POTIER: modifié suite réunion du 02/02/17
Note on AD263: Christine POTIER: client a décalé visite expert.
Note on G276: Christine POTIER: Dysfonctionnement Frn requalifié en réclamation le 22/03/17
Note on H276: Christine POTIER: modification frn incriminé : Valorel en lieu et place de Grayel
Note on R285: Christine POTIER: Method au lieu de Material suite analyse approfondie.
Note on AD288: Christine POTIER: report 01/18 pour statuer à la clôture du projet
Note on AH293: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MàJ le 05/07/21 avec bad debt de 166 K€ à la demande de DBR (2000 mbres)
Note on R300: Christine POTIER: modif CPT MO en matière
Note on R301: Christine POTIER: modif CPT, méthode en matiere
Note on R302: Christine POTIER: modif CPT, méthode en matière
Note on I331: Christine POTIER: Anomalie requalifiée en REC le 14/05 suite FNC émise par GOI
Note on I350: Christine POTIER: requalifié en claim le 23/10/18.
Note on AD447: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Attente date d'ouverture TP possible par Téréos et si nécessité d'expertise par SUEZ. Au 26/07 : Suez souhaite un retour mbre pour expertise, délai + long.
Note on X449: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vu avec Monica le 8/07
Note on AD451: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6 mois de fabrication des 3 colonnes à réception cde par Gree. Négociation prix en cours.
Note on G453: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CNQ (bad debt 166 K€) already impute on CAP17033 the 05/07/2021.
Note on AD454: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: too short to solve the pb. Reply: i put 6 months
Note on AD469: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: dépend si expertise par Suez des 2 élt NF
Note on I481: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CAP ouverte en NC prodt en Mars et requalifié en REC en Mai par NVSA Reply: Maintien de la CAP ouverte (cf mail erratum du 13/06/22)
Note on AB490: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Insatisfaction orale durant réunion CLE/CJ du 10/05/22
Note on AC490: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AR/prise en compte de l'insatisfaction orale durant la réunion proprement dîte par CLE
Note on AD520: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: À confirmer SGU
Note on AD526: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pb client pour retour filtre poche abîmé
Note on AD535: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: À confirmer SGU, pb complexe, dépend CTI, suite PA du 16/05/23 : 31/12/23
Note on AD543: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10 semaines après cde vannes régul, devis tjrs en attente
Note on AD544: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Attente résultats des échantillons en cours de test dans colonne pour valider date de clôture
Note on AD551: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Postpone from client : mail ALI "client haven’t asked us for delivery till now, probably will happen in one or two months"
Note on AD553: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dépendra du résultat des étapes 2 et 3 du plan d'action en cours, à redéfinir à l'issue
Note on AH561: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mail XRO du 17/06/24 : Sur Via separation, nous venons de faire une Credit Note au client de 46 kUSD, à rajouter aux coût NQ
Note on AD572: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lié au fait que Prolactal passe une nouvelle cde, pourra être réajuster en fonction.
Note on AD576: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lié à la remise de doc EN manquante par CTI
Note on AD577: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A confirmer selon négo avec KSB.
Note on AD580: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A réajuster en fonction info Casa Grande et retour résines pour analyse
Note on AK580: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Après réception et mise en service nvelle cde résine
Note on AD581: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A réajuster en fonction négo avec Bray et délai d'appro
Note on AD583: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: À valider selon retour CTI, besoin d'échantillon ou pas, et actions à engager

## AutoList (hidden)
Site | Cap_Type | Techno | 5M | SCOPE | YES/NO | Codes Technologie* :
Colonne1 | Claim | ED | Manpower / Main d'œuvre | SYSTEMS | YES | ED (Electrodialyse)
SMB | Internal Anomaly | SSMB | Material / Matière | Cust. Sce | NO | SSMB (Chromato)
NVSA | Supplier Dysfonctionning | IEX | Method / Méthode | R&D | Close | IEX (Echange Ions)
PSA | Prevent / improve | MF/UF | Environment / Milieu |  |  | MF/UF (Micro/Ultrafiltation)
| Safety | Decolo | Management/management |  |  | NF (Nanofiltration)
| Pdt unconformity | NF | Equipment / Matériel |  |  | OI (Osmose Inverse)
|  | OI | Management / Management |  |  | EVAPO (Evaporation)
|  | EVAPO | Measure / Mesure |  |  | CA (Charbon Actif)
CA
CPL

## SHA IER (hidden)
CAP Nr | Recording Date | Issuer | Dpt | Customer | Supplier | CAP TYPE | Compt Nr | Project Nr | Techno* | Description | Scope | Step of Process | 7M | Hours (€) | Eqmt (€) | TOTAL (€)
22003 | 2022-01-24 | KYU | IER | SQ13 | SPA | Supplier Dysfonctionning | 2097 | 16108 | SSMB | Name plates misplaced | SYSTEMS | commissioning | Material / Matière | 1250 | 243 | 1493
22004 | 2022-01-24 | KYU | IER | SQ12 | Guanxing | Supplier Dysfonctionning | 2092 | 15490/16979 | SSMB/IEX | Column rods broken or missing | SYSTEMS | Pre-Mouting | Material / Matière | 1250 | 243 | 1493
22013 | 2022-03-07 | TWI | IER | ENSIGN | SPA | Claim |  | 14619 | IEX | Rubber lining cracking | SYSTEMS | commissioning | Material / Matière | 5125 | 32166 | 37291
22015 | 2022-03-31 | KYU | IER | SUCRO | ZFLZ | Supplier Dysfonctionning | 2113 | 16809 |  | FRP sand filter nozzle plate thickness issue | SYSTEMS | Pre-Mouting | Material / Matière | 500 | 0 | 500
22024 | 2022-05-30 | KYU | IER | SQ12 | Guanxing | Prevent / improve | 2092 | 15490 | SSMB | Internal leakage in rubber lining connection piping | SYSTEMS | Process design | Method / Méthode | 1000 | 1667 | 2667
22025 | 2022-05-30 | MPE | IER | SQ10 | Mingliang | Pdt unconformity | 2082 | 14552 | SSMB | Fine particle in gravel of SQ10 SSMB | SYSTEMS | commissioning | Material / Matière | 1500 | 1103 | 2603
22032 | 2022-08-23 | KYU | IER | SQ21 | FDS | Internal Anomaly | 2131 | 18072 | SSMB | Cylinder positioning issue for internal mounting | SYSTEMS | Pre-Mouting | Method / Méthode | 1000 |  | 1000
22044 | 2022-10-24 | TWI | IER | SQ21 | FDS | Pdt unconformity | 2131 | 18072 | IEX | Installation issue of manhole for IEX column | SYSTEMS | Pre-Mouting | Method / Méthode | 500 |  | 500
22046 | 2022-10-28 | KYU | IER | SQ21 | FDS | Claim | 2131 | 18072 | IEX | Material and welding issues on IEX front piping | SYSTEMS | Pre-Mouting | Material / Matière | 2500 | 0 | 2500
22047 | 2022-10-28 | MPE | IER | SQ10 | GREE | Claim | 2082 | 14552 | IEX | Lack welding on the vent pipe inside SSMB | SYSTEMS | Pre-Mouting | Material / Matière | 500 |  | 500
22048 | 2022-11-21 | ESH | IER | COFCO | LIVIC | Pdt unconformity |  | 11608 | IEX | filter not matching | SYSTEMS | Pre-Mouting | Method / Méthode | 0 | 0 | 0
22049 | 2022-11-21 | ESH | IER | COFCO | FDS | Pdt unconformity |  | 11608 | IEX | different ball valves were mixed | SYSTEMS | Pre-Mouting | Method / Méthode | 0 | 0 | 0
22050 | 2022-11-28 | ESH | IER | Natureworks | SPA | Pdt unconformity |  | 16753 | IEX | Rubber lining thickness is lower than the standard | SYSTEMS | Pre-Mouting | Equipment / Matériel | 2500 |  | 2500
22051 | 2022-12-05 | ESH | IER | Natureworks | Jhenten | Pdt unconformity |  | 16753 | IEX | filter halar thickness | SYSTEMS | Pre-Mouting | Equipment / Matériel |  |  | 0
23006 | 2023-02-10 | ESH | IER | Natureworks | Wuxi fandesi/FDS | Pdt unconformity |  | 16753 |  |  | SYSTEMS | QC | Method / Méthode | 1500 | 0 | 1500
23010 | 2023-03-03 | ESH | IER | LEKAI | FDS | Supplier Dysfonctionning | 2137 | 18080 | SSMB | Piping fabrication quality | SYSTEMS | Commissioning | Material / Matière |  |  | 0
23013 | 2023-04-11 | ESH | IER | Cofco Tangshan |  | Internal Anomaly |  | 23013_16608 |  | Cofco_issue control valve on drawing | SYSTEMS | Meca Design | Method / Méthode |  | 278 | 278
23014 | 2023-04-11 | ESH | IER | Huitong SSMB | FDS | Claim |  | 10.1779 |  | SSMB internals material (SS304 instead of SS316) | SYSTEMS | Pre-Mouting | Material / Matière | 1000 |  | 1000
23015 | 2023-04-11 | ESH | IER | Ensign 2 | SPA | Claim |  | 18251 | IEX | Ensign site issues rubber lining leakage | SYSTEMS | Commissioning | Material / Matière | 2500 | 2583 | 5083
23030 | 2023-10-28 | MPE | IER | SQ Nansha | Runlu | Supplier Dysfonctionning | 2128 | 17951 | IEX | Loose nozzles found inside columns of SQ20 on Site | SYSTEMS | Commissioning | Method / Méthode | 3000 | 1892 | 4892
23031 | 2023-11-06 | MHA | IER | Lier | Xiangming | Internal Anomaly | 2151 | 18281 | MF/UF | Unproper MF housings site installation | SYSTEMS | Installation | Method / Méthode | 250 | 139 | 389
23032 | 2023-11-06 | MHA | IER | Rousselot | kaiyuan/Biteng | Claim | 2150 | 18178 | IEX | Painting damage during transportation | SYSTEMS | Delivery | Method / Méthode | 938 | 0 | 938
24002 | 2024-01-16 | ESH | IER | Xinlv | FDS | Supplier Dysfonctionning |  | 18418 | SSMB | Xinlv SSMB cell height | SYSTEMS | QC at client site | Method / Méthode | 750 | 0 | 750
24003 | 2024-01-22 | TWI | IER | SQ13 | GREE | Claim | 2097 | 16108 | IEX | SQ13 LS MB140 column internals deformation | SYSTEMS | commissioning | Method / Méthode | 7000 | 3832 | 10832
24005 | 2024-02-20 | ESH | IER | Huitong |  | Internal Anomaly | 2136 | 17789 | SSMB | Backwashing tank volume issue | SYSTEMS | commissioning | Method / Méthode | 1278 |  | 1278
24014 | 2024-04-02 | MHA | IER | SQ CQ | FDS/Runjia | Internal Anomaly | 3022 | 18448 | SSMB | Unproper internals manufacturing and installation for SSMB | SYSTEMS | QC | Equipment / Matériel | 5139 |  | 5139
24019 | 2024-06-11 | YLI | IER | SQ Nansha | SPA | Claim | 2128 | 17951 | IEX | SQ20 F55MB CL6510 Rubber Lining Issue of Insert Tube | SYSTEMS | Commissioning | Equipment / Matériel | 500 |  | 500
24022 | 2024-06-20 | TWI | IER | Huaantang |  | Internal Anomaly | 3123 | 18323 | SSMB | Functional Analysis assignement and workload France-Asia | SYSTEMS | Process Design | Management/management | 250 | 0 | 250
24039 | 2024-11-19 | YLI | IER | Huaantang | SPA | Supplier Dysfonctionning | 3123 | 18323 | SSMB | Columns Name plate & Tag No. Installation Mistake | SYSTEMS | QC | Equipment / Matériel | 625 | 486 | 1111
24040 | 2024-11-19 | YLI | IER | Huaantang | FDS | Supplier Dysfonctionning | 3123 | 18323 | SSMB | Column-B Resin Nozzle Orientation Mistake | SYSTEMS | Meca Design | Equipment / Matériel | 625 |  | 625
24041 | 2024-11-20 | MHA | IER | LIER | Runyuan | Claim | 3165 | 18466 | CA | The carbon backwashing is not efficient | SYSTEMS | Meca Design | Method / Méthode | 2188 | 1388 | 3576
24042 | 2024-11-20 | MHA | IER | LIER | LongYU, Ziyou | Internal Anomaly | 3165 | 18466 | CA | Mismatching of Nozzle A1 and A2 betweent column and front piping | SYSTEMS | Meca Design | Method / Méthode | 1876 | 1416 | 3292
24044 | 2024-12-02 | TWI | IER | PLIITH HUITONG | ZIMA | Claim | 2135 | 18103 | CA | Huitong Claim on GAC revamping program delay | SYSTEMS | Commissioning | Method / Méthode |  |  | 0
24045 | 2024-12-02 | MHA | IER | SQ nansha |  | Internal Anomaly | 3075 | 45.0037 | SSMB | SQ1 revamping program didn't complete on time | SYSTEMS | Commissioning | Method / Méthode |  |  | 0
Note on K2: Codes Techno : ED (Electrodialyse) SSMB (Chromato) IEX (Echange Ions) MF/UF (Micro/Ultrafiltation) NF (Nanofiltration) OI (Osmose Inverse) EVAPO (Evaporation) CA (Charbon Actif)
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CAP ouverte en NC prodt en Mars et requalifié en REC en Mai par NVSA Reply: Maintien de la CAP ouverte (cf mail erratum du 13/06/22)

## SHA CS (hidden)
CAP Nr | Recording Date | Issuer | Dpt | Customer | Supplier | CAP TYPE | Compt Nr | Project Nr | Techno* | Description | Scope | Step of Process | 7M | Hours (€) | Eqmt (€) | TOTAL (€)
22009 | 2022-02-11 | MYU | CS | DYG | Inopor | Supplier Dysfonctionning |  | 75.2269 | MF | Ends of alpha mbre worn out after 3 months usage | Cust. Sce | Purchase | Material / Matière | 1500 | 694 | 2194
22023 | 2022-05-24 | MYU | CS | BBCA | CTI | Claim |  | 75.2331 | MF | Order placing late | Cust. Sce | Purchase | Method / Méthode | 0 | 6595 | 6595
23018 | 2023-05-15 | MYU | CS | HUAKANG | Finex | Claim |  | 15333 | SSMB | Poor performance of Xylose ML SSMB/Resin issue | Cust. Sce | project closed | Material / Matière | 0 | 3000 | 3000
23019 | 2023-06-02 | MYU | CS | DYG | Inopor | Claim |  | 75.2269 | MF | Alpha KBW 0.1U membranes abrasion issue | Cust. Sce | project closed | Material / Matière | 0 | 130000 | 130000
24016 | 2024-04-18 | MYU | CS | Fufeng Qiqihaer | Mitsubishi | Claim | 3087 | 75.2406 | IEX | Fufeng Qiqihaer- Frozen lysine resin | Cust. Sce | Logistic | Environment / Milieu | 1333 | 0 | 1333
24030 | 2024-08-02 | RRU | CS | Lesaffre | INOPOR | Claim | 2142 | 18146 | MF/UF | KBE alpha Membrane Abrasion | Cust. Sce | After sales | Material / Matière |  |  | 0
24036 | 2024-10-18 | RRU | CS | GXSF 2 | Mitsubishi | Claim |  | 10.702 | IEX | High Pressure Drop in C120A upper cell | Cust. Sce | commissioning | Material / Matière | 6389 | 156111 | 162500
24038 | 2024-11-18 | RRU | CS | Yinmore | Mitsubishi | Claim |  | 9801 | IEX | Large deviation in resin particle size distribution | Cust. Sce | purchasing | Material / Matière |  | 83333.33 | 83333.33
24043 | 2024-11-25 | MYU | CS | SQ18 | Dupont | Internal Anomaly |  | 17093 | IEX | SQ18 IRA458 Resin missing in SHA warehouse | Cust. Sce | stock | Management / Management |  | 105944.44 | 105944.44
Note on K2: Codes Techno : ED (Electrodialyse) SSMB (Chromato) IEX (Echange Ions) MF/UF (Micro/Ultrafiltation) NF (Nanofiltration) OI (Osmose Inverse) EVAPO (Evaporation) CA (Charbon Actif)